## MDL
#VALUE! |  | پروژه احداث نیروگاه خورشیدی 20 مگاواتی زارچ یزد شماره قرارداد: PKPS-P2-C2-0410 | [8 empty] | #VALUE!
DOCUMENT NO. : 410-DE-PM-LST-0084 |  | Document Name : Master Document List | [8 empty] | Unit | Rev.
[11 empty] | PM | 03
PAGE 1 of 1
Tag | Document Title | Category | Phase | 410 | Cat. | 000Tag | Dis. | Discipline | Document No. | Weighting Factor | Engineering Man-Hour | Weight (Out of 100)
1 | Solar Panel Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0001 | EL | Electrical | 410-BE-EL-DSH-0001 | 0.1 | 10 | 0.35
2 | Inverter Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0002 | EL | Electrical | 410-BE-EL-DSH-0002 | 0.1 | 10 | 0.35
3 | MV Station Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0003 | EL | Electrical | 410-BE-EL-DSH-0003 | 0.1 | 10 | 0.35
4 | DC Connection (MC4) Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0004 | EL | Electrical | 410-BE-EL-DSH-0004 | 0.1 | 10 | 0.35
5 | DC Cable Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0005 | EL | Electrical | 410-BE-EL-DSH-0005 | 0.1 | 10 | 0.35
6 | LV Cable Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0006 | EL | Electrical | 410-BE-EL-DSH-0006 | 0.1 | 10 | 0.35
7 | MV Cable Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0007 | EL | Electrical | 410-BE-EL-DSH-0007 | 0.1 | 10 | 0.35
8 | MV Switchgear (CT, PT, Relay) Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0008 | EL | Electrical | 410-BE-EL-DSH-0008 | 0.1 | 10 | 0.35
9 | Earthing and Lightning Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0009 | EL | Electrical | 410-BE-EL-DSH-0009 | 0.1 | 10 | 0.35
10 | Monitoring System Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0010 | TL | Telecom | 410-BE-TL-DSH-0010 | 2 | 16 | 0.56
11 | Data Logger Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0011 | TL | Telecom | 410-BE-TL-DSH-0011 | 2 | 16 | 0.56
12 | Weather Station Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0012 | TL | Telecom | 410-BE-TL-DSH-0012 | 5 | 16 | 0.56
13 | Auxiliary Transformer Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0013 | EL | Electrical | 410-BE-EL-DSH-0013 | 0.1 | 10 | 0.35
14 | CCTV and NVR Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0014 | TL | Telecom | 410-BE-TL-DSH-0014 | 2 | 16 | 0.56
15 | UPS and Battery Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0015 | EL | Electrical | 410-BE-EL-DSH-0015 | 0.1 | 10 | 0.35
16 | Diesel Generator Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0016 | EL | Electrical | 410-BE-EL-DSH-0016 | 0.1 | 10 | 0.35
17 | HVAC Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0017 | ME | Mechanical | 410-BE-ME-DSH-0017 | 5 | 15 | 0.525
18 | Piping Material, Plumbing Fittings, Pumps Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0018 | ME | Mechanical | 410-BE-ME-DSH-0018 | 5 | 15 | 0.525
19 | Fire Alarm System Technical Specification and Datasheet | Specification & Datasheet | BE | 410 | DSH | 0019 | SF | Safety | 410-BE-SF-DSH-0019 | 10 | 16 | 0.56
20 | General Single Line Diagram (GSLD) | Drawing | BE | 410 | DRW | 0020 | EL | Electrical | 410-BE-EL-DRW-0020 | 5 | 23 | 0.805
21 | General Layout | Drawing | BE | 410 | DRW | 0021 | EL | Electrical | 410-BE-EL-DRW-0021 | 7 | 23 | 0.805
22 | PV System Calculation Study (String Size, Optimum Tilt and Pitch) | Calculation | DE | 410 | CAL | 0022 | EL | Electrical | 410-DE-EL-CAL-0022 | 2 | 30 | 1.05
23 | PVSYST Report | Report | BE | 410 | REP | 0023 | EL | Electrical | 410-BE-EL-REP-0023 | 7 | 22 | 0.77
24 | Plant Detailed Report | Report | BE | 410 | REP | 0024 | EL | Electrical | 410-BE-EL-REP-0024 | 5 | 22 | 0.77
25 | Solar Module, Connector, Inverter and MV station MTO | Material Take Off | BE | 410 | MTO | 0025 | EL | Electrical | 410-BE-EL-MTO-0025 | 0.2 | 19 | 0.665
26 | Strings Connection Diagram & Inverter Arrangement (DC Side) | Drawing | DE | 410 | DRW | 0026 | EL | Electrical | 410-DE-EL-DRW-0026 | 7 | 23 | 0.805
27 | Module & Table Arrangement (DC Side) | Drawing | DE | 410 | DRW | 0027 | EL | Electrical | 410-DE-EL-DRW-0027 | 5 | 23 | 0.805
28 | DC Cable Calculation | Calculation | DE | 410 | CAL | 0028 | EL | Electrical | 410-DE-EL-CAL-0028 | 2 | 30 | 1.05
29 | DC Cable List, Labeling Code and MTO | Material Take Off | DE | 410 | MTO | 0029 | EL | Electrical | 410-DE-EL-MTO-0029 | 7 | 19 | 0.665
30 | LVAC Cable Calculation | Calculation | DE | 410 | CAL | 0030 | EL | Electrical | 410-DE-EL-CAL-0030 | 2 | 30 | 1.05
31 | LV Cable Termination List and MTO | List | DE | 410 | LST | 0031 | EL | Electrical | 410-DE-EL-LST-0031 | 1 | 14 | 0.49
32 | LV Cable List, Labeling Code and MTO | Material Take Off | DE | 410 | MTO | 0032 | EL | Electrical | 410-DE-EL-MTO-0032 | 1 | 19 | 0.665
33 | MV Cable Calculations | Calculation | DE | 410 | CAL | 0033 | EL | Electrical | 410-DE-EL-CAL-0033 | 2 | 30 | 1.05
34 | MV Cable List, Labeling Code and MTO | Material Take Off | DE | 410 | MTO | 0034 | EL | Electrical | 410-DE-EL-MTO-0034 | 1 | 19 | 0.665
35 | MV Cable Termination List and MTO | List | DE | 410 | LST | 0035 | EL | Electrical | 410-DE-EL-LST-0035 | 1 | 14 | 0.49
36 | Electrical Cable Route and Section | Drawing | DE | 410 | DRW | 0036 | EL | Electrical | 410-DE-EL-DRW-0036 | 4 | 23 | 0.805
37 | Cable Trench Layout | Drawing | DE | 410 | DRW | 0037 | EL | Electrical | 410-DE-EL-DRW-0037 | 4 | 23 | 0.805
38 | Earthing System Calculation | Calculation | DE | 410 | CAL | 0038 | EL | Electrical | 410-DE-EL-CAL-0038 | 6 | 30 | 1.05
39 | Earthing System Layout | Drawing | DE | 410 | DRW | 0039 | EL | Electrical | 410-DE-EL-DRW-0039 | 2 | 23 | 0.805
40 | Lightning Protection Calculation | Calculation | DE | 410 | CAL | 0040 | EL | Electrical | 410-DE-EL-CAL-0040 | 2 | 30 | 1.05
41 | Lightning Protection Layout | Drawing | DE | 410 | DRW | 0041 | EL | Electrical | 410-DE-EL-DRW-0041 | 3 | 23 | 0.805
42 | Earthing and Lightning Protection MTO | Material Take Off | DE | 410 | MTO | 0042 | EL | Electrical | 410-DE-EL-MTO-0042 | 1 | 19 | 0.665
43 | Protection Single Line Diagram (PSLD) | Drawing | DE | 410 | DRW | 0043 | EL | Electrical | 410-DE-EL-DRW-0043 | 2 | 23 | 0.805
44 | CT and PT Calculations | Calculation | DE | 410 | CAL | 0044 | EL | Electrical | 410-DE-EL-CAL-0044 | 2 | 30 | 1.05
45 | MV Switchgear Logic Diagram | Drawing | DE | 410 | DRW | 0045 | EL | Electrical | 410-DE-EL-DRW-0045 | 1 | 23 | 0.805
46 | Trip Table | Report | DE | 410 | REP | 0046 | EL | Electrical | 410-DE-EL-REP-0046 | 2 | 22 | 0.77
47 | Alarm List | List | DE | 410 | LST | 0047 | EL | Electrical | 410-DE-EL-LST-0047 | 1 | 14 | 0.49
48 | Indoor and Outdoor Electrical Plan & Details for Building | Drawing | DE | 410 | DRW | 0048 | EL | Electrical | 410-DE-EL-DRW-0048 | 3 | 23 | 0.805
49 | MV Switchgear MTO | Material Take Off | DE | 410 | MTO | 0049 | EL | Electrical | 410-DE-EL-MTO-0049 | 1 | 19 | 0.665
50 | Load List | List | DE | 410 | LST | 0050 | EL | Electrical | 410-DE-EL-LST-0050 | 1 | 14 | 0.49
51 | LVAC Auxiliary Panel Single Line Diagram | Drawing | DE | 410 | DRW | 0051 | EL | Electrical | 410-DE-EL-DRW-0051 | 2 | 23 | 0.805
52 | UPS Calculation | Calculation | DE | 410 | CAL | 0052 | EL | Electrical | 410-DE-EL-CAL-0052 | 2 | 30 | 1.05
53 | AUX Equipment MTO (AUX Transformer, Diesel, UPS, Battery) | Material Take Off | DE | 410 | MTO | 0053 | EL | Electrical | 410-DE-EL-MTO-0053 | 1 | 19 | 0.665
54 | CCTV System Block Diagram | Drawing | DE | 410 | DRW | 0054 | TL | Telecom | 410-DE-TL-DRW-0054 | 15 | 23 | 0.805
55 | CCTV System Arrangement & Layout | Drawing | DE | 410 | DRW | 0055 | TL | Telecom | 410-DE-TL-DRW-0055 | 20 | 23 | 0.805
56 | CCTV Pole Detail Drawing, Switchboard, CAFU Details | Drawing | DE | 410 | DRW | 0056 | TL | Telecom | 410-DE-TL-DRW-0056 | 4 | 23 | 0.805
57 | CCTV System MTO | Material Take Off | DE | 410 | MTO | 0057 | TL | Telecom | 410-DE-TL-MTO-0057 | 10 | 19 | 0.665
58 | Indoor and Outdoor Lighting Calculation | Calculation | DE | 410 | CAL | 0058 | EL | Electrical | 410-DE-EL-CAL-0058 | 1 | 30 | 1.05
59 | Outdoor Lighting Pole Drawing | Drawing | DE | 410 | DRW | 0059 | EL | Electrical | 410-DE-EL-DRW-0059 | 0.1 | 23 | 0.805
60 | Outdoor Lighting Layout and Switchboard | Drawing | DE | 410 | DRW | 0060 | EL | Electrical | 410-DE-EL-DRW-0060 | 1 | 23 | 0.805
61 | Lighting System MTO | Material Take Off | DE | 410 | MTO | 0061 | EL | Electrical | 410-DE-EL-MTO-0061 | 0.5 | 19 | 0.665
62 | Solar Panel Cleaning & Maintenance Procedures | Report | DE | 410 | REP | 0062 | ME | Mechanical | 410-DE-ME-REP-0062 | 5 | 15 | 0.525
63 | SCADA System I/O List | List | DE | 410 | LST | 0063 | TL | Telecom | 410-DE-TL-LST-0063 | 10 | 14 | 0.49
64 | Monitoring System Overall Diagram | Drawing | DE | 410 | DRW | 0064 | TL | Telecom | 410-DE-TL-DRW-0064 | 20 | 23 | 0.805
65 | Telecommunication and Monitoring System MTO | Material Take Off | DE | 410 | MTO | 0065 | TL | Telecom | 410-DE-TL-MTO-0065 | 10 | 19 | 0.665
66 | HVAC Equipment Calculation | Calculation | DE | 410 | CAL | 0066 | ME | Mechanical | 410-DE-ME-CAL-0066 | 20 | 21 | 0.735
67 | HVAC Equipment Layout for Building | Drawing | DE | 410 | DRW | 0067 | ME | Mechanical | 410-DE-ME-DRW-0067 | 20 | 20 | 0.7
68 | HVAC and Piping System MTO | Material Take Off | DE | 410 | MTO | 0068 | ME | Mechanical | 410-DE-ME-MTO-0068 | 15 | 19 | 0.665
69 | Fire Fighting Equipment Arrangement of MV Switchgear Buildings | Drawing | DE | 410 | DRW | 0069 | SF | Safety | 410-DE-SF-DRW-0069 | 10 | 23 | 0.805
70 | Outdoor Fire Fighting Equipment & Shelter Arrangement | Drawing | DE | 410 | DRW | 0070 | SF | Safety | 410-DE-SF-DRW-0070 | 10 | 23 | 0.805
71 | Fire Alarm System Layout and Block Diagram | Drawing | DE | 410 | DRW | 0071 | SF | Safety | 410-DE-SF-DRW-0071 | 30 | 23 | 0.805
72 | Fire and Safety and F & G System MTO | Material Take Off | DE | 410 | MTO | 0072 | SF | Safety | 410-DE-SF-MTO-0072 | 40 | 19 | 0.665
73 | Solar Panel Installation Manual & Operation & Maintenance | Report | DE | 410 | REP | 0073 | QA | Quality | 410-DE-QA-REP-0073 | 5 | 22 | 0.77
74 | Inverter Installation Manual & Operation & Maintenance | Report | DE | 410 | REP | 0074 | QA | Quality | 410-DE-QA-REP-0074 | 5 | 22 | 0.77
75 | MV Station Installation Manual & Operation & Maintenance | Report | DE | 410 | REP | 0075 | QA | Quality | 410-DE-QA-REP-0075 | 5 | 22 | 0.77
76 | UPS Installation Manual & Operation & Maintenance | Report | DE | 410 | REP | 0076 | QA | Quality | 410-DE-QA-REP-0076 | 5 | 22 | 0.77
77 | AUX Transformer Installation Manual & Operation & Maintenance | Report | DE | 410 | REP | 0077 | QA | Quality | 410-DE-QA-REP-0077 | 5 | 22 | 0.77
78 | Diesel Generator Installation Manual & Operation & Maintenance | Report | DE | 410 | REP | 0078 | QA | Quality | 410-DE-QA-REP-0078 | 5 | 22 | 0.77
79 | Weather Station Installation Manual & Operation & Maintenance | Report | DE | 410 | REP | 0079 | QA | Quality | 410-DE-QA-REP-0079 | 5 | 22 | 0.77
80 | Solar Structure Installation Manual & Operation & Maintenance | Report | DE | 410 | REP | 0080 | QA | Quality | 410-DE-QA-REP-0080 | 5 | 22 | 0.77
81 | SCADA and Monitoring System Installation Manual & Operation & Maintenance | Report | DE | 410 | REP | 0081 | QA | Quality | 410-DE-QA-REP-0081 | 5 | 22 | 0.77
82 | Special Tools | Report | DE | 410 | REP | 0082 | EL | Electrical | 410-DE-EL-REP-0082 | 1 | 22 | 0.77
83 | Project O&M General Instructions | Report | DE | 410 | REP | 0083 | QA | Quality | 410-DE-QA-REP-0083 | 10 | 22 | 0.77
84 | Master Document List | List | DE | 410 | LST | 0084 | PM | Project Management | 410-DE-PM-LST-0084 | 50 | 14 | 0.49
85 | Time Schedule | Report | DE | 410 | REP | 0085 | PM | Project Management | 410-DE-PM-REP-0085 | 30 | 22 | 0.77
86 | Two-Weekly Report | Report | DE | 410 | REP | 0086 | PM | Project Management | 410-DE-PM-REP-0086 | 20 | 22 | 0.77
87 | Topography of Field | Report | DE | 410 | REP | 0087 | CV | Civil | 410-DE-CV-REP-0087 | 0.2 | 22 | 0.77
88 | Geotechnical Test Report | Report | DE | 410 | REP | 0088 | CV | Civil | 410-DE-CV-REP-0088 | 0.2 | 22 | 0.77
89 | Ramming and Pull-Out Test Report | Report | DE | 410 | REP | 0089 | CV | Civil | 410-DE-CV-REP-0089 | 0.2 | 22 | 0.77
90 | Hydrology Study Report | Report | DE | 410 | REP | 0090 | CV | Civil | 410-DE-CV-REP-0090 | 0.2 | 22 | 0.77
91 | Site Fence Detail Drawing | Drawing | DE | 410 | DRW | 0091 | CV | Civil | 410-DE-CV-DRW-0091 | 0.2 | 23 | 0.805
92 | Logistic Area | Drawing | DE | 410 | DRW | 0092 | CV | Civil | 410-DE-CV-DRW-0092 | 1 | 23 | 0.805
93 | Buildings Foundation & Structure Calculation | Calculation | DE | 410 | CAL | 0093 | CV | Civil | 410-DE-CV-CAL-0093 | 6 | 30 | 1.05
94 | Buildings Foundation & Structure Drawing | Drawing | DE | 410 | DRW | 0094 | CV | Civil | 410-DE-CV-DRW-0094 | 6 | 23 | 0.805
95 | Mechanical Drawing (Water Supply and Sewage Systems) | Drawing | DE | 410 | DRW | 0095 | ME | Mechanical | 410-DE-ME-DRW-0095 | 20 | 20 | 0.7
96 | Septic Tank Technical Specification and Datasheet | Specification & Datasheet | DE | 410 | DSH | 0096 | ME | Mechanical | 410-DE-ME-DSH-0096 | 5 | 15 | 0.525
97 | Water Tank Technical Specification and Datasheet | Specification & Datasheet | DE | 410 | DSH | 0097 | ME | Mechanical | 410-DE-ME-DSH-0097 | 5 | 15 | 0.525
98 | Parking Foundation & Structure Detail Drawing | Drawing | DE | 410 | DRW | 0098 | CV | Civil | 410-DE-CV-DRW-0098 | 6 | 23 | 0.805
99 | Power Plant Entrance Gate Drawing | Drawing | DE | 410 | DRW | 0099 | CV | Civil | 410-DE-CV-DRW-0099 | 2 | 23 | 0.805
100 | Parking Architectural Drawing | Drawing | DE | 410 | DRW | 0100 | CV | Civil | 410-DE-CV-DRW-0100 | 6 | 23 | 0.805
101 | Landscaping Layout | Drawing | DE | 410 | DRW | 0101 | CV | Civil | 410-DE-CV-DRW-0101 | 6 | 23 | 0.805
102 | Buildings Architectural Detail drawing | Drawing | DE | 410 | DRW | 0102 | CV | Civil | 410-DE-CV-DRW-0102 | 6 | 23 | 0.805
103 | Fence MTO | Material Take Off | DE | 410 | MTO | 0103 | CV | Civil | 410-DE-CV-MTO-0103 | 1 | 19 | 0.665
104 | Site Grading and Leveling | Drawing | DE | 410 | DRW | 0104 | CV | Civil | 410-DE-CV-DRW-0104 | 11 | 23 | 0.805
105 | Drainage For Insite of Plant & Implementation Detail Drawing | Drawing | DE | 410 | DRW | 0105 | CV | Civil | 410-DE-CV-DRW-0105 | 14 | 23 | 0.805
106 | Flood Managmant For Outsite of Plant & Implementation Detail Drawing | Drawing | DE | 410 | DRW | 0106 | CV | Civil | 410-DE-CV-DRW-0106 | 0.5 | 23 | 0.805
107 | Internal Road Layout & Implementation Detail Drawing | Drawing | DE | 410 | DRW | 0107 | CV | Civil | 410-DE-CV-DRW-0107 | 3 | 23 | 0.805
108 | Access Road Layout & Implementation Detail Drawing | Drawing | DE | 410 | DRW | 0108 | CV | Civil | 410-DE-CV-DRW-0108 | 6 | 23 | 0.805
109 | MV Station Foundation Calculation | Calculation | DE | 410 | CAL | 0109 | CV | Civil | 410-DE-CV-CAL-0109 | 1 | 30 | 1.05
110 | MV Station Foundation Drawings | Drawing | DE | 410 | DRW | 0110 | CV | Civil | 410-DE-CV-DRW-0110 | 1.5 | 23 | 0.805
111 | Auxiliary Transformer Foundation Detail Drawings | Drawing | DE | 410 | DRW | 0111 | CV | Civil | 410-DE-CV-DRW-0111 | 0.5 | 23 | 0.805
112 | Calculation Report for Structure | Calculation | DE | 410 | CAL | 0112 | CV | Civil | 410-DE-CV-CAL-0112 | 11 | 30 | 1.05
113 | Structure Detail Drawings | Drawing | DE | 410 | DRW | 0113 | CV | Civil | 410-DE-CV-DRW-0113 | 1 | 23 | 0.805
114 | PV Structure Ramming Location Details Drawing (Stacking) | Drawing | DE | 410 | DRW | 0114 | CV | Civil | 410-DE-CV-DRW-0114 | 0.5 | 23 | 0.805
115 | Solar Module Structure MTO | Material Take Off | DE | 410 | MTO | 0115 | CV | Civil | 410-DE-CV-MTO-0115 | 0.5 | 19 | 0.665
116 | Table UTM Point | Drawing | DE | 410 | DRW | 0116 | CV | Civil | 410-DE-CV-DRW-0116 | 4 | 23 | 0.805
117 | Structure, Entrance Gate and Foundation of Building MTO | Material Take Off | DE | 410 | MTO | 0117 | CV | Civil | 410-DE-CV-MTO-0117 | 0.5 | 19 | 0.665
118 | Test Report of Solar Structure | Report | DE | 410 | DRW | 0118 | CV | Quality | 410-DE-QA-REP-0118 | 4 | 22 | 0.77
119 | Test Reports for PV Modules | Report | DE | 410 | REP | 0119 | QA | Quality | 410-DE-QA-REP-0119 | 5 | 22 | 0.77
120 | Test Reports for Inverter | Report | DE | 410 | REP | 0120 | QA | Quality | 410-DE-QA-REP-0120 | 5 | 22 | 0.77
121 | Test Reports for MV Sation | Report | DE | 410 | REP | 0121 | QA | Quality | 410-DE-QA-REP-0121 | 5 | 22 | 0.77
122 | Test Reports for AC and DC Cables | Report | DE | 410 | REP | 0122 | QA | Quality | 410-DE-QA-REP-0122 | 5 | 22 | 0.77
123 | Test Reports for Diesel Generators | Report | DE | 410 | REP | 0123 | QA | Quality | 410-DE-QA-REP-0123 | 5 | 22 | 0.77
124 | Test Reports for AUX Transformer | Report | DE | 410 | REP | 0124 | QA | Quality | 410-DE-QA-REP-0124 | 5 | 22 | 0.77
125 | Test Reports for Earthing and Ligthtning | Report | DE | 410 | REP | 0125 | QA | Quality | 410-DE-QA-REP-0125 | 5 | 22 | 0.77
126 | Test Reports for MV Switchgear (CT, PT, Relay, …) | Report | DE | 410 | REP | 0126 | QA | Quality | 410-DE-QA-REP-0126 | 5 | 22 | 0.77
127 | Test Reports for UPS and Battery | Report | DE | 410 | REP | 0127 | QA | Quality | 410-DE-QA-REP-0127 | 5 | 22 | 0.77
128 | MV Switchgear Schematic Diagram | Drawing | [5 empty] | Electrical | 410-DE-EL-DRW-0128 |  | 23 | 0.805
129 | MV Switchgear Front View Drawing | Drawing | [5 empty] | Electrical | 410-DE-EL-DRW-0129 |  | 23 | 0.805
130 | System Drainage Calculation | Calculation | [5 empty] | Civil | 410-DE-CV-CAL-0130 |  | 30 | 1.05
131 | Lighting Foundation Calculation | Calculation | [5 empty] | Civil | 410-DE-CV-CAL-0131 |  | 30 | 1.05
132 | Lightning Foundation Calculation | Calculation | [5 empty] | Civil | 410-DE-CV-CAL-0132 |  | 30 | 1.05
133 | Lightning Foundation Drawing | Drawing | [5 empty] | Civil | 410-DE-CV-DRW-0133 |  | 23 | 0.805
134 | Lighting and CCTV Pole Calculation | Calculation | [5 empty] | Civil | 410-DE-CV-CAL-0134 |  | 30 | 1.05
135 | Septic Tank Detail Drawing | Drawing | [5 empty] | Civil | 410-DE-CV-DRW-0135 |  | 23 | 0.805
136 | Water Tank Foundation Detail Drawing | Drawing | [5 empty] | Civil | 410-DE-CV-DRW-0136 |  | 23 | 0.805