## Cover
PKSP
20 MW Zarch Solar Power Planet Project
Contract No: |  |  | Document No: 2 |  | Rev: 00 |  | Issue date: |  | 2026-06-14
Document Title: |  |  | Work Breakdown Structure |  |  |  | Page: 1 of 6
Work Breakdown Structure
`
00 | 2026-06-14 | Issued for Review |  | E.Razavirad |  | E.Razavirad |  | MH.Mehdi nia
Rev. | Date | Purpose of Issue |  | Prepared By |  | Checked By |  | Approved By

## Rev
PKSP
20 MW Zarch Solar Power Planet Project
Contract No: |  |  |  |  | Document No: 2 | [12 empty] | Rev: 00 |  |  | Issue date: |  |  | 2026-06-14
Document Title: |  |  |  |  | Work Breakdown Structure | [15 empty] | Page: 2 of 6
Tabulation of Revised Page
| Sheet | Revisions | [10 empty] | Sheet | Revisions
|  | 00 | 01 | 02 |  | 03 | 04 | 05 | 06 | 07 | 08 | 09 |  | 00 | 01 | 02 | 03 |  | 04 | 05 | 06 | 07 | 08 | 09
| 1 | ✓ | [10 empty] | 41
| 2 | ✓ | [10 empty] | 42
| 3 | ✓ | [10 empty] | 43
| 4 | ✓ | [10 empty] | 44
| 5 | ✓ | [10 empty] | 45
| 6 | ✓ | [10 empty] | 46
| 7 | [11 empty] | 47
| 8 | [11 empty] | 48
| 9 | [11 empty] | 49
| 10 | [11 empty] | 50
| 11 | [11 empty] | 51
| 12 | [11 empty] | 52
| 13 | [11 empty] | 53
| 14 | [11 empty] | 54
| 15 | [11 empty] | 55
| 16 | [11 empty] | 56
| 17 | [11 empty] | 57
| 18 | [11 empty] | 58
| 19 | [11 empty] | 59
| 20 | [11 empty] | 60
| 21 | [11 empty] | 61
| 22 | [11 empty] | 62
| 23 | [11 empty] | 63
| 24 | [11 empty] | 64
| 25 | [11 empty] | 65
| 26 | [11 empty] | 66
| 27 | [11 empty] | 67
| 28 | [11 empty] | 68
| 29 | [11 empty] | 69
| 30 | [11 empty] | 70
| 31 | [11 empty] | 71
| 32 | [11 empty] | 72
| 33 | [11 empty] | 73
| 34 | [11 empty] | 74
| 35 | [11 empty] | 75
| 36 | [11 empty] | 76
| 37 | [11 empty] | 77
| 38 | [11 empty] | 78
| 39 | [11 empty] | 79
| 40 | [11 empty] | 80

## WBS
احداث خط انتقال نیروي 20kv نیروگاه خورشیدي زارچ شماره قرارداد: 0754 / ت/ 1405
تاریخ: 1405/03/24 | Work Breakdown Structure |  |  | عنوان مدرک:
صفحه 3 از 6 | ویرایش 00 | 2 |  | شماره مدرک:
WBS | Task Name | W/F | Level 1 | Level 2 | Level 3 | Level 4
1 | احداث خط انتقال نیروی 20 کیلوولت نیروگاه خورشیدی زارچ | 100% | 100%
1.1 | مایلستون | 0% |  | 0%
1.1.1 | شروع پروژه | 0% |  |  | 0%
1.1.2 | پیش پرداخت | 0% |  |  | 0%
1.1.3 | تحویل زمین | 0% |  |  | 0%
1.1.4 | تایید نقشه های نهایی از کارفرما | 0% |  |  | 0%
1.1.5 | پایان پروژه | 0% |  |  | 0%
1.2 | مهندسی | 2.5% |  | 2.5%
1.2.1 | مسیریابی و نقشه برداری | 0.25% |  |  | 10%
1.2.2 | تهیه نقشه های اجرایی (شامل کلیه مدارک مهندسی اتصال سوئیچگیر ها و سیستم مخابراتی) و اخذ تاییدیه از کارفرما | 0.75% |  |  | 30%
1.2.3 | تهیه مشخصات فنی و اخذ تاییدیه از کارفرما | 1.5% |  |  | 60%
1.3 | خرید | 83.5% |  | 83.5%
1.3.1 | سفارش گذاری | 12.53% |  |  | 15%
1.3.1.1 | پایه سیمانی | 2.055% |  |  |  | 16.41%
1.3.1.2 | OPGW سیم هادی و سیم | 5.749% |  |  |  | 45.9%
1.3.1.3 | سیم مهار | 0.05991% |  |  |  | 0.4784%
1.3.1.4 | مقره و یراق آلات و ملحقات | 1.976% |  |  |  | 15.78%
1.3.1.5 | خرید مصالح (سنگ لاشه، بتن و…) | 0.02877% |  |  |  | 0.2297%
1.3.1.6 | کابل آلومینیومی | 0.6338% |  |  |  | 5.06%
1.3.1.7 | تابلو های 20 کیلو ولت | 1.905% |  |  |  | 15.21%
1.3.1.8 | کابل کنترل و قدرت | 0.1166% |  |  |  | 0.9307%
1.3.2 | ساخت در کارگاه سازنده | 12.53% |  |  | 15%
1.3.2.1 | پایه سیمانی | 2.055% |  |  |  | 16.41%
1.3.2.2 | OPGW سیم هادی و سیم | 5.749% |  |  |  | 45.9%
1.3.2.3 | سیم مهار | 0.05991% |  |  |  | 0.4784%
1.3.2.4 | مقره و یراق آلات و ملحقات | 1.976% |  |  |  | 15.78%
1.3.2.5 | خرید مصالح (سنگ لاشه، بتن و…) | 0.02877% |  |  |  | 0.2297%
1.3.2.6 | کابل آلومینیومی | 0.6338% |  |  |  | 5.06%
1.3.2.7 | تابلو های 20 کیلو ولت | 1.905% |  |  |  | 15.21%
1.3.2.8 | کابل کنترل و قدرت | 0.1166% |  |  |  | 0.9307%
1.3.3 | حمل و تحویل در کارگاه (سایت) | 58.45% |  |  | 70%
1.3.3.1 | پایه سیمانی | 9.592% |  |  |  | 16.41%
1.3.3.2 | OPGW سیم هادی و سیم | 26.83% |  |  |  | 45.9%
1.3.3.3 | سیم مهار | 0.2796% |  |  |  | 0.4784%
1.3.3.4 | مقره و یراق آلات و ملحقات | 9.221% |  |  |  | 15.78%
1.3.3.5 | خرید مصالح (سنگ لاشه، بتن و…) | 0.1343% |  |  |  | 0.2297%
1.3.3.6 | کابل آلومینیومی | 2.958% |  |  |  | 5.06%
1.3.3.7 | تابلو های 20 کیلو ولت | 8.892% |  |  |  | 15.21%
1.3.3.8 | کابل کنترل و قدرت | 0.544% |  |  |  | 0.9307%
1.4 | اجرا | 14% |  | 14%
1.4.1 | تجهیز کارگاه | 2.45% |  |  | 17.5%
1.4.1.1 | تجهیز کارگاه ثابت | 1.47% |  |  |  | 60%
1.4.1.2 | تجهیز کارگاه مستمر | 0.98% |  |  |  | 40%
1.4.2 | انجام عملیات اجرایی | 11.27% |  |  | 80.5%
1.4.2.1 | پیکتاژ مسیر | 0.1863% |  |  |  | 1.653%
1.4.2.2 | میخکوبی موقعیت تیرها | 0.302% |  |  |  | 2.68%
1.4.2.3 | حفاری و گوده زنی پایه ها | 1.738% |  |  |  | 15.43%
1.4.2.4 | تسطیح و ریگلاژ | 1.738% |  |  |  | 15.43%
1.4.2.5 | نصب پایه بتنی به همراه سنگ لاشه و دوغاب ریزی | 2.457% |  |  |  | 21.81%
1.4.2.6 | نصب یراق آلات | 0.5769% |  |  |  | 5.119%
1.4.2.7 | سیم کشی | 2.388% |  |  |  | 21.19%
1.4.2.8 | اجرای سیم مهار | 0.0445% |  |  |  | 0.3949%
1.4.2.9 | اجرای کابل زمینی | 1.194% |  |  |  | 10.6%
1.4.2.10 | نصب تابلو و سکسیونر و سکشنلایزر | 0.2886% |  |  |  | 2.561%
1.4.2.11 | نصب اتوریکلوزر و آشکار ساز خطا | 0.02973% |  |  |  | 0.2638%
1.4.2.12 | اتصال کابلهای قدرت و انجام وارنینگ های مربوط به کنترل و حفاظت | 0.1705% |  |  |  | 1.513%
1.4.2.13 | تست و راه اندازی | 0.1238% |  |  |  | 1.098%
1.4.2.14 | اصلاح و رفع نواقص | 0.03094% |  |  |  | 0.2745%
1.4.3 | تحویل و عملیات نهایی | 0.28% |  |  | 2%
1.4.3.1 | تهیه نقشه های نهایی ( AS BUILT) | 0.07% |  |  |  | 25%
1.4.3.2 | تحویل موقت | 0.182% |  |  |  | 65%
1.4.3.3 | برچیدن کارگاه | 0.028% |  |  |  | 10%