## MDR
Master Document List
Row | Document No. | Document Name | Discipline | %Complete | %MDR
Electrical |  |  |  | 26.01% | 26.01%
1 | 410-BE-EL-SPC-0001 | Solar Panel Technical Specification | Electrical | 100% | 100%
2 | 410-BE-EL-SPC-0002 | Inverter Technical Specification | Electrical | 100% | 100%
3 | 410-BE-EL-SPC-0003 | MV Station Technical Specification | Electrical | 100% | 100%
4 | 410-BE-EL-SPC-0004 | DC Connection (MC4) Technical Specification | Electrical | 100% | 100%
5 | 410-BE-EL-SPC-0005 | DC Cable Technical Specification | Electrical | 100% | 100%
6 | 410-BE-EL-SPC-0006 | LV Cable Technical Specification | Electrical | 0% | 0%
7 | 410-BE-EL-SPC-0007 | MV Cable Technical Specification | Electrical | 0% | 0%
8 | 410-BE-EL-SPC-0008 | MV Switchgear (CT, PT, Relay) Technical Specification | Electrical | 75% | 75%
9 | 410-BE-EL-SPC-0009 | Earthing and Lightning Technical Specification | Electrical | 0% | 0%
10 | 410-BE-EL-SPC-0013 | Auxiliary Transformer Technical Specification | Electrical | 0% | 0%
11 | 410-BE-EL-SPC-0015 | UPS and Battery Technical Specification | Electrical | 0% | 0%
12 | 410-BE-EL-SPC-0016 | Diesel Generator Technical Specification | Electrical | 0% | 0%
13 | 410-BE-EL-DRW-0020 | General Single Line Diagram (GSLD) | Electrical | 75% | 75%
14 | 410-BE-EL-DRW-0021 | General Layout | Electrical | 100% | 100%
15 | 410-DE-EL-CAL-0022 | PV System Calculation Study (String Size, Optimum Tilt and Pitch) | Electrical | 0% | 0%
16 | 410-BE-EL-REP-0023 | PVSYST Report | Electrical | 75% | 75%
17 | 410-BE-EL-REP-0024 | Plant Detailed Report | Electrical | 100% | 100%
18 | 410-BE-EL-MTO-0025 | Solar Module, Connector, Inverter and MV station MTO | Electrical | 75% | 75%
19 | 410-DE-EL-DRW-0026 | Strings Connection Diagram & Inverter Arrangement (DC Side) | Electrical | 75% | 75%
20 | 410-DE-EL-DRW-0027 | Module & Table Arrangement (DC Side) | Electrical | 75% | 75%
21 | 410-DE-EL-CAL-0028 | DC Cable Calculation | Electrical | 75% | 75%
22 | 410-DE-EL-MTO-0029 | DC Cable List, Labeling Code and MTO | Electrical | 75% | 75%
23 | 410-DE-EL-CAL-0030 | LVAC Cable Calculation | Electrical | 100% | 100%
24 | 410-DE-EL-LST-0031 | LV Cable Termination List and MTO | Electrical | 0% | 0%
25 | 410-DE-EL-MTO-0032 | LV Cable List, Labeling Code and MTO | Electrical | 90% | 90%
26 | 410-DE-EL-CAL-0033 | MV Cable Calculations | Electrical | 100% | 100%
27 | 410-DE-EL-MTO-0034 | MV Cable List, Labeling Code and MTO | Electrical | 100% | 100%
28 | 410-DE-EL-LST-0035 | MV Cable Termination List and MTO | Electrical | 0% | 0%
29 | 410-DE-EL-DRW-0036 | Electrical Cable Route and Section | Electrical | 0% | 0%
30 | 410-DE-EL-DRW-0037 | Cable Trench Layout | Electrical | 0% | 0%
31 | 410-DE-EL-CAL-0038 | Earthing System Calculation | Electrical | 60% | 60%
32 | 410-DE-EL-DRW-0039 | Earthing System Layout | Electrical | 60% | 60%
33 | 410-DE-EL-CAL-0040 | Lightning Protection Calculation | Electrical | 60% | 60%
34 | 410-DE-EL-DRW-0041 | Lightning Protection Layout | Electrical | 60% | 60%
35 | 410-DE-EL-MTO-0042 | Earthing and Lightning Protection MTO | Electrical | 0% | 0%
36 | 410-DE-EL-DRW-0043 | Protection Single Line Diagram (PSLD) | Electrical | 60% | 60%
37 | 410-DE-EL-CAL-0044 | CT and PT Calculations | Electrical | 0% | 0%
38 | 410-DE-EL-DRW-0045 | MV Switchgear Logic Diagram | Electrical | 0% | 0%
39 | 410-DE-EL-REP-0046 | Trip Table | Electrical | 0% | 0%
40 | 410-DE-EL-LST-0047 | Alarm List | Electrical | 0% | 0%
41 | 410-DE-EL-DRW-0048 | Indoor and Outdoor Electrical Plan & Details for Building | Electrical | 0% | 0%
42 | 410-DE-EL-MTO-0049 | MV Switchgear MTO | Electrical | 0% | 0%
43 | 410-DE-EL-LST-0050 | Load List | Electrical | 0% | 0%
44 | 410-DE-EL-DRW-0051 | LVAC Auxiliary Panel Single Line Diagram | Electrical | 0% | 0%
45 | 410-DE-EL-CAL-0052 | UPS Calculation | Electrical | 0% | 0%
46 | 410-DE-EL-MTO-0053 | AUX Equipment MTO (AUX Transformer, Diesel, UPS, Battery) | Electrical | 0% | 0%
47 | 410-DE-EL-CAL-0058 | Indoor and Outdoor Lighting Calculation | Electrical | 0% | 0%
48 | 410-DE-EL-DRW-0059 | Outdoor Lighting Pole Drawing | Electrical | 0% | 0%
49 | 410-DE-EL-DRW-0060 | Outdoor Lighting Layout and Switchboard | Electrical | 0% | 0%
50 | 410-DE-EL-MTO-0061 | Lighting System MTO | Electrical | 0% | 0%
51 | 410-DE-EL-REP-0082 | Special Tools | Electrical | 60% | 60%
52 | 410-DE-EL-DRW-0128 | MV Switchgear Schematic Diagram | Electrical | 0% | 0%
53 | 410-DE-EL-DRW-0129 | MV Switchgear Front View Drawing | Electrical | 0% | 0%
54 | 410-BE-EL-DSH-0146 | Solar Panel Datasheet | Electrical | 100% | 100%
55 | 410-BE-EL-DSH-0147 | Inverter Datasheet | Electrical | 45% | 45%
56 | 410-BE-EL-DSH-0148 | MV Station Datasheet | Electrical | 75% | 75%
57 | 410-BE-EL-DSH-0149 | DC Connection (MC4) Datasheet | Electrical | 100% | 100%
58 | 410-BE-EL-DSH-0150 | DC Cable Datasheet | Electrical | 100% | 100%
59 | 410-BE-EL-DSH-0151 | LV Cable Datasheet | Electrical | 0% | 0%
60 | 410-BE-EL-DSH-0152 | MV Cable Datasheet | Electrical | 0% | 0%
61 | 410-BE-EL-DSH-0153 | MV Switchgear (CT, PT, Relay) Datasheet | Electrical | 0% | 0%
62 | 410-BE-EL-DSH-0154 | Earthing and Lightning Datasheet | Electrical | 60% | 60%
63 | 410-BE-EL-DSH-0155 | Auxiliary Transformer Datasheet | Electrical | 0% | 0%
64 | 410-BE-EL-DSH-0156 | UPS and Battery Datasheet | Electrical | 0% | 0%
65 | 410-BE-EL-DSH-0157 | Diesel Generator Datasheet | Electrical | 0% | 0%
66 | 410-DE-EL-MRE-0168 | Material Requisition for Indoor Power and Lighting Distribution Panel | Electrical | 0% | 0%
67 | 410-DE-EL-MRE-0169 | Material Requisition for Auxiliary Transformer | Electrical | 0% | 0%
68 | 410-DE-EL-MRE-0170 | Material Requisition for PCC | Electrical | 0% | 0%
69 | 410-DE-EL-MRE-0171 | Material Requisition for MV Switchgear (CT, PT, Relay) | Electrical | 0% | 0%
70 | 410-DE-EL-MRE-0172 | Material Requisition for AC Cable | Electrical | 0% | 0%
71 | 410-DE-EL-MRE-0173 | Material Requisition for DC Cable | Electrical | 0% | 0%
72 | 410-DE-EL-MRE-0174 | Material Requisition for Earthing and Lightning | Electrical | 0% | 0%
73 | 410-DE-EL-MRE-0175 | Material Requisition for DC Connection (MC4) | Electrical | 0% | 0%
74 | 410-DE-EL-MRE-0176 | Material Requisition for Lighting System | Electrical | 0% | 0%
75 | 410-DE-EL-MRE-0177 | Material Requisition for UPS and Battery | Electrical | 0% | 0%
76 | 410-BE-EL-MRE-0186 | Material Requisition for Diesel Generator | Electrical | 0% | 0%
Civil |  |  |  | 37.94% | 37.94%
77 | 410-DE-CV-REP-0087 | Topography of Field | Civil | 100% | 100%
78 | 410-DE-CV-REP-0088 | Geotechnical Test Report | Civil | 90% | 90%
79 | 410-DE-CV-REP-0089 | Ramming and Pull-Out Test Report | Civil | 90% | 90%
80 | 410-DE-CV-REP-0090 | Hydrology Study Report | Civil | 60% | 60%
81 | 410-DE-CV-DRW-0091 | Site Fence Detail Drawing | Civil | 100% | 100%
82 | 410-DE-CV-DRW-0092 | Logistic Area | Civil | 75% | 75%
83 | 410-DE-CV-CAL-0093 | Buildings Foundation & Structure Calculation | Civil | 0% | 0%
84 | 410-DE-CV-CAL-0187 | Swichgear Building Foundation & Structure Calculation | Civil | 0% | 0%
85 | 410-DE-CV-CAL-0188 | Control Building Foundation & Structure Calculation | Civil | 0% | 0%
86 | 410-DE-CV-CAL-0189 | Guard Building Foundation & Structure Calculation | Civil | 0% | 0%
87 | 410-DE-CV-DRW-0094 | Buildings Foundation & Structure Drawing | Civil | 0% | 0%
88 | 410-DE-CV-DRW-0190 | Swichgear Building Foundation & Structure Drawing | Civil | 0% | 0%
89 | 410-DE-CV-DRW-0191 | Control Building Foundation & Structure Drawing | Civil | 0% | 0%
90 | 410-DE-CV-DRW-0192 | Guard Building Foundation & Structure Drawing | Civil | 0% | 0%
91 | 410-DE-CV-DRW-0098 | Parking Foundation & Structure Detail Drawing | Civil | 0% | 0%
92 | 410-DE-CV-DRW-0099 | Power Plant Entrance Gate Drawing | Civil | 0% | 0%
93 | 410-DE-CV-DRW-0100 | Parking Architectural Drawing | Civil | 0% | 0%
94 | 410-DE-CV-DRW-0101 | Landscaping Layout | Civil | 0% | 0%
95 | 410-DE-CV-DRW-0102 | Buildings Architectural Detail drawing | Civil | 65% | 0%
96 | 410-DE-CV-DRW-0193 | Swichgear Building Architectural Detail drawing | Civil | 75% | 75%
97 | 410-DE-CV-DRW-0194 | Control Building Architectural Detail drawing | Civil | 60% | 60%
98 | 410-DE-CV-DRW-0195 | Guard Building Architectural Detail drawing | Civil | 60% | 60%
99 | 410-DE-CV-MTO-0103 | Fence MTO | Civil | 75% | 75%
100 | 410-DE-CV-DRW-0104 | Site Grading and Leveling | Civil | 60% | 60%
101 | 410-DE-CV-DRW-0105 | Drainage For Insite of Plant & Implementation Detail Drawing | Civil | 45% | 45%
102 | 410-DE-CV-DRW-0106 | Flood Managmant For Outsite of Plant & Implementation Detail Drawing | Civil | 45% | 45%
103 | 410-DE-CV-DRW-0107 | Internal Road Layout & Implementation Detail Drawing | Civil | 60% | 60%
104 | 410-DE-CV-DRW-0108 | Access Road Layout & Implementation Detail Drawing | Civil | 0% | 0%
105 | 410-DE-CV-CAL-0109 | MV Station Foundation Calculation | Civil | 75% | 75%
106 | 410-DE-CV-DRW-0110 | MV Station Foundation Drawings | Civil | 75% | 75%
107 | 410-DE-CV-DRW-0111 | Auxiliary Transformer Foundation Detail Drawings | Civil | 0% | 0%
108 | 410-DE-CV-CAL-0112 | Calculation Report for Structure | Civil | 60% | 60%
109 | 410-DE-CV-DRW-0113 | Structure Detail Drawings | Civil | 60% | 60%
110 | 410-DE-CV-DRW-0114 | PV Structure Ramming Location Details Drawing (Stacking) | Civil | 0% | 0%
111 | 410-DE-CV-MTO-0115 | Solar Module Structure MTO | Civil | 75% | 75%
112 | 410-DE-CV-DRW-0116 | Table UTM Point | Civil | 0% | 0%
113 | 410-DE-CV-MTO-0117 | Structure, Entrance Gate and Foundation of Building MTO | Civil | 0% | 0%
114 | 410-DE-CV-CAL-0130 | System Drainage Calculation | Civil | 45% | 45%
115 | 410-DE-CV-CAL-0131 | Lighting Foundation Calculation | Civil | 0% | 0%
116 | 410-DE-CV-CAL-0132 | Lightning Foundation Calculation | Civil | 0% | 0%
117 | 410-DE-CV-DRW-0133 | Lightning Foundation Drawing | Civil | 0% | 0%
118 | 410-DE-CV-CAL-0134 | Lighting and CCTV Pole Calculation | Civil | 0% | 0%
119 | 410-DE-CV-DRW-0135 | Septic Tank Detail Drawing | Civil | 0% | 0%
120 | 410-DE-CV-DRW-0136 | Water Tank Foundation Detail Drawing | Civil | 0% | 0%
121 | 410-DE-CV-CAL-0137 | Calculation for Fence | Civil | 75% | 75%
122 | 410-DE-CV-MRE-0167 | Material Requisition for Fence | Civil | 60% | 60%
Quality |  |  |  | 9% | 9%
123 | 410-DE-QA-REP-0073 | Solar Panel Installation Manual & Operation & Maintenance | Quality | 0% | 0%
124 | 410-DE-QA-REP-0074 | Inverter Installation Manual & Operation & Maintenance | Quality | 0% | 0%
125 | 410-DE-QA-REP-0075 | MV Station Installation Manual & Operation & Maintenance | Quality | 90% | 90%
126 | 410-DE-QA-REP-0076 | UPS Installation Manual & Operation & Maintenance | Quality | 0% | 0%
127 | 410-DE-QA-REP-0077 | AUX Transformer Installation Manual & Operation & Maintenance | Quality | 0% | 0%
128 | 410-DE-QA-REP-0078 | Diesel Generator Installation Manual & Operation & Maintenance | Quality | 0% | 0%
129 | 410-DE-QA-REP-0079 | Weather Station Installation Manual & Operation & Maintenance | Quality | 0% | 0%
130 | 410-DE-QA-REP-0080 | Solar Structure Installation Manual & Operation & Maintenance | Quality | 0% | 0%
131 | 410-DE-QA-REP-0081 | SCADA and Monitoring System Installation Manual & Operation & Maintenance | Quality | 0% | 0%
132 | 410-DE-QA-REP-0083 | Project O&M General Instructions | Quality | 0% | 0%
133 | 410-DE-QA-REP-0118 | Test Report of Solar Structure | Quality | 90% | 90%
134 | 410-DE-QA-REP-0119 | Test Reports for PV Modules | Quality | 0% | 0%
135 | 410-DE-QA-REP-0120 | Test Reports for Inverter | Quality | 0% | 0%
136 | 410-DE-QA-REP-0121 | Test Reports for MV Sation | Quality | 0% | 0%
137 | 410-DE-QA-REP-0122 | Test Reports for AC and DC Cables | Quality | 0% | 0%
138 | 410-DE-QA-REP-0196 | Test Reports for AC Cables | Quality | 0% | 0%
139 | 410-DE-QA-REP-0197 | Test Reports for DC Cables | Quality | 0% | 0%
140 | 410-DE-QA-REP-0123 | Test Reports for Diesel Generators | Quality | 0% | 0%
141 | 410-DE-QA-REP-0124 | Test Reports for AUX Transformer | Quality | 0% | 0%
142 | 410-DE-QA-REP-0125 | Test Reports for Earthing and Ligthtning | Quality | 0% | 0%
143 | 410-DE-QA-REP-0126 | Test Reports for MV Switchgear (CT, PT, Relay, …) | Quality | 0% | 0%
144 | 410-DE-QA-REP-0127 | Test Reports for UPS and Battery | Quality | 0% | 0%
Telecom |  |  |  | 12.31% | 12.31%
145 | 410-BE-TL-SPC-0010 | Monitoring System Technical Specification | Telecom | 75% | 75%
146 | 410-BE-TL-SPC-0011 | Data Logger Technical Specification | Telecom | 0% | 0%
147 | 410-BE-TL-SPC-0012 | Weather Station Technical Specification | Telecom | 60% | 60%
148 | 410-BE-TL-SPC-0014 | CCTV and NVR Technical Specification | Telecom | 60% | 60%
149 | 410-DE-TL-DRW-0054 | CCTV System Block Diagram | Telecom | 0% | 0%
150 | 410-DE-TL-DRW-0055 | CCTV System Arrangement & Layout | Telecom | 0% | 0%
151 | 410-DE-TL-DRW-0056 | CCTV Pole Detail Drawing, Switchboard, CAFU Details | Telecom | 0% | 0%
152 | 410-DE-TL-MTO-0057 | CCTV System MTO | Telecom | 0% | 0%
153 | 410-DE-TL-LST-0063 | SCADA System I/O List | Telecom | 0% | 0%
154 | 410-DE-TL-DRW-0064 | Monitoring System Overall Diagram | Telecom | 0% | 0%
155 | 410-DE-TL-MTO-0065 | Telecommunication and Monitoring System MTO | Telecom | 0% | 0%
156 | 410-BE-TL-DSH-0158 | Monitoring System Datasheet | Telecom | 60% | 60%
157 | 410-BE-TL-DSH-0159 | Data Logger Datasheet | Telecom | 0% | 0%
158 | 410-BE-TL-DSH-0160 | Weather Station Datasheet | Telecom | 0% | 0%
159 | 410-BE-TL-DSH-0161 | CCTV and NVR Datasheet | Telecom | 0% | 0%
160 | 410-DE-TL-MRE-0178 | Material Requisition forTelecommunication and Monitoring Cable | Telecom | 0% | 0%
161 | 410-BE-TL-MRE-0179 | Material Requisition forFiber Optics | Telecom | 0% | 0%
162 | 410-DE-TL-MRE-0180 | Material Requisition for CCTV and NVR | Telecom | 0% | 0%
163 | 410-BE-TL-MRE-0185 | Material Requisition for Weather Station | Telecom | 60% | 60%
Mechanical |  |  |  | 6.173% | 6.173%
164 | 410-BE-ME-SPC-0017 | HVAC Technical Specification | Mechanical | 0% | 0%
165 | 410-BE-ME-SPC-0018 | Piping Material, Plumbing Fittings, Pumps Technical Specification | Mechanical | 0% | 0%
166 | 410-DE-ME-REP-0062 | Solar Panel Cleaning & Maintenance Procedures | Mechanical | 60% | 60%
167 | 410-DE-ME-CAL-0066 | HVAC Equipment Calculation | Mechanical | 0% | 0%
168 | 410-DE-ME-DRW-0067 | HVAC Equipment Layout for Building | Mechanical | 0% | 0%
169 | 410-DE-ME-DRW-0198 | HVAC Equipment Layout for Swichgear Building | Mechanical | 0% | 0%
170 | 410-DE-ME-DRW-0199 | HVAC Equipment Layout for Control Building | Mechanical | 0% | 0%
171 | 410-DE-ME-DRW-0200 | HVAC Equipment Layout for Guard Building | Mechanical | 0% | 0%
172 | 410-DE-ME-MTO-0068 | HVAC and Piping System MTO | Mechanical | 0% | 0%
173 | 410-DE-ME-DRW-0095 | Mechanical Drawing (Water Supply and Sewage Systems) | Mechanical | 0% | 0%
174 | 410-DE-ME-SPC-0096 | Septic Tank Technical Specification | Mechanical | 45% | 45%
175 | 410-DE-ME-SPC-0097 | Water Tank Technical Specification | Mechanical | 0% | 0%
176 | 410-BE-ME-DSH-0162 | HVAC Datasheet | Mechanical | 0% | 0%
177 | 410-BE-ME-DSH-0163 | Piping Material, Plumbing Fittings, Pumps Datasheet | Mechanical | 0% | 0%
178 | 410-BE-ME-DSH-0164 | Septic Tank Datasheet | Mechanical | 45% | 45%
179 | 410-BE-ME-DSH-0165 | Water Tank Datasheet | Mechanical | 0% | 0%
180 | 410-BE-ME-MRE-0183 | Material Requisition for Septic Tank | Mechanical | 0% | 0%
181 | 410-BE-ME-MRE-0184 | Material Requisition for Water | Mechanical | 0% | 0%
Safety |  |  |  | 14.19% | 14.19%
182 | 410-BE-SF-SPC-0019 | Fire Alarm System Technical Specification | Safety | 45% | 45%
183 | 410-DE-SF-DRW-0069 | Fire Fighting Equipment Arrangement of MV Switchgear Buildings | Safety | 0% | 0%
184 | 410-DE-SF-DRW-0070 | Outdoor Fire Fighting Equipment & Shelter Arrangement | Safety | 45% | 45%
185 | 410-DE-SF-DRW-0071 | Fire Alarm System Layout and Block Diagram | Safety | 0% | 0%
186 | 410-DE-SF-MTO-0072 | Fire and Safety and F & G System MTO | Safety | 0% | 0%
187 | 410-BE-SF-DSH-0166 | Fire Alarm System Datasheet | Safety | 0% | 0%
188 | 410-DE-SF-MRE-0181 | Material Requisition for Fire Alarm System | Safety | 0% | 0%
189 | 410-DE-SF-MRE-0182 | Material Requisition for Fire Fighting Equipment Arrangement | Safety | 0% | 0%
190 | 410-DE-SF-REP-0201 | HSE Plan | Safety | 60% | 60%
Project Management |  |  |  | 62.04% | 62.04%
191 | 410-DE-PM-LST-0084 | Master Document List | Project Management | 100% | 100%
192 | 410-DE-PM-REP-0085 | Time Schedule | Project Management | 100% | 100%
193 | 410-DE-PM-CAF-0086 | Cash Flow | Project Management | 60% | 60%
194 | 410-DE-PM-REP-0138 | Monthly Report 410-M-001 | Project Management | 100% | 100%
195 | 410-DE-PM-REP-0139 | Monthly Report 410-M-002 | Project Management | 100% | 100%
196 | 410-DE-PM-REP-0140 | Monthly Report 410-M-003 | Project Management | 100% | 100%
197 | 410-DE-PM-REP-0141 | Monthly Report 410-M-004 | Project Management | 0% | 0%
198 | 410-DE-PM-REP-0142 | Monthly Report 410-M-005 | Project Management | 0% | 0%
199 | 410-DE-PM-REP-0143 | Monthly Report 410-M-006 | Project Management | 0% | 0%
200 | 410-DE-PM-REP-0144 | Monthly Report 410-M-007 | Project Management | 0% | 0%
201 | 410-DE-PM-REP-0145 | Monthly Report 410-M-008 | Project Management | 0% | 0%

## PMS
| پروژه احداث نیروگاه خورشیدی 20 مگاواتی زارچ یزد شماره قرارداد: PKPS-P2-C2-0410 |  |  |  | 2026-05-23 |  | RJ
| Progress Measurement System (PMS) |  |  |  | AN | IFI | AP
| WBS | Task Name | Document No. | %Progress
Actual%
2 | 0 | پروژه احداث نیروگاه خورشیدی 20 مگا واتی زارچ یزد |  | 17.57
3 | 1 | شروع |  | 100
4 | 2 | مایلستون های کلیدی |  | 0
5 | 2.1 | دریافت سایر اطلاعات مقدماتی از کارفرما (آزمایش شیمیایی خاک، تست کشش پایه ها و…) |  | 100
6 | 2.2 | واریز اولین پیش پرداخت بخش مهندسی |  | 100
7 | 2.3 | دریافت مطالعات ژئوتکنیک |  | 100
8 | 2.4 | تحویل زمین |  | 100
9 | 2.5 | تاییدیه تجهیزات (پنل، اینورتر و MV Station( |  | 0
10 | 2.6 | اتمام طراحی و اخذ تاییدیه |  | 0
11 | 2.7 | اتمام استعلام قیمتی و سفارش گذاری خرید خارجی |  | 0
12 | 2.8 | اتمام تامین و تحویل خرید خارجی در سایت پروژه |  | 0
13 | 2.9 | اتمام تجهیز کارگاه |  | 0
14 | 2.1 | اتمام نصب سازه |  | 0
15 | 2.11 | اتمام نصب پنل |  | 0
16 | 2.12 | اتمام ساختمان مانیتورینگ |  | 0
17 | 2.13 | اتمام نصب MV Staion |  | 0
18 | 2.14 | اتمام نصب اینورتر |  | 0
19 | 2.15 | تست پست بالادست |  | 0
20 | 3 | مهندسی |  | 25.27
21 | 3.1 | مدیریت پروژه |  | 62.17
22 | 3.1.1 | Master Document List | 410-DE-PM-LST-0084 | 100
23 | 3.1.2 | Time Schedule | 410-DE-PM-REP-0085 | 100
24 | 3.1.3 | Cash Flow | 410-DE-PM-CAF-0086 | 60
25 | 3.1.4 | Monthly Report 410-M-001 | 410-DE-PM-REP-0138 | 100
26 | 3.1.5 | Monthly Report 410-M-002 | 410-DE-PM-REP-0139 | 100
27 | 3.1.6 | Monthly Report 410-M-003 | 410-DE-PM-REP-0140 | 100
28 | 3.1.7 | Monthly Report 410-M-004 | 410-DE-PM-REP-0141 | 0
29 | 3.1.8 | Monthly Report 410-M-005 | 410-DE-PM-REP-0142 | 0
30 | 3.1.9 | Monthly Report 410-M-006 | 410-DE-PM-REP-0143 | 0
31 | 3.1.10 | Monthly Report 410-M-007 | 410-DE-PM-REP-0144 | 0
32 | 3.1.11 | Monthly Report 410-M-008 | 410-DE-PM-REP-0145 | 0
33 | 3.2 | طراحی و اخذ تاییدیه طراحی پایه |  | 47.8
34 | 3.2.1 | ارایه و اخذ تاییدیه دیتاشیت ها |  | 27.5
35 | 3.2.1.1 | Solar Panel Datasheet | 410-BE-EL-DSH-0146 | 100
36 | 3.2.1.2 | Inverter Datasheet | 410-BE-EL-DSH-0147 | 45
37 | 3.2.1.3 | MV Station Datasheet | 410-BE-EL-DSH-0148 | 75
38 | 3.2.1.4 | DC Connection (MC4) Datasheet | 410-BE-EL-DSH-0149 | 100
39 | 3.2.1.5 | DC Cable Datasheet | 410-BE-EL-DSH-0150 | 100
40 | 3.2.1.6 | LV Cable Datasheet | 410-BE-EL-DSH-0151 | 0
41 | 3.2.1.7 | MV Cable Datasheet | 410-BE-EL-DSH-0152 | 0
42 | 3.2.1.8 | MV Switchgear (CT, PT, Relay) Datasheet | 410-BE-EL-DSH-0153 | 0
43 | 3.2.1.9 | Earthing and Lightning Datasheet | 410-BE-EL-DSH-0154 | 60
44 | 3.2.1.10 | Auxiliary Transformer Datasheet | 410-BE-EL-DSH-0155 | 0
45 | 3.2.1.11 | UPS and Battery Datasheet | 410-BE-EL-DSH-0156 | 0
46 | 3.2.1.12 | Diesel Generator Datasheet | 410-BE-EL-DSH-0157 | 0
47 | 3.2.1.13 | Monitoring System Datasheet | 410-BE-TL-DSH-0158 | 60
48 | 3.2.1.14 | Data Logger Datasheet | 410-BE-TL-DSH-0159 | 0
49 | 3.2.1.15 | Weather Station Datasheet | 410-BE-TL-DSH-0160 | 0
50 | 3.2.1.16 | CCTV and NVR Datasheet | 410-BE-TL-DSH-0161 | 0
51 | 3.2.1.17 | HVAC Datasheet | 410-BE-ME-DSH-0162 | 0
52 | 3.2.1.18 | Piping Material, Plumbing Fittings, Pumps Datasheet | 410-BE-ME-DSH-0163 | 0
53 | 3.2.1.19 | Septic Tank Datasheet | 410-BE-ME-DSH-0164 | 45
54 | 3.2.1.20 | Water TankDatasheet | 410-BE-ME-DSH-0165 | 0
55 | 3.2.1.21 | Fire Alarm System Datasheet | 410-BE-SF-DSH-0166 | 0
56 | 3.2.2 | ارایه و اخذ تاییدیه مشخصات |  | 40.06
57 | 3.2.2.1 | Solar Panel Technical Specification | 410-BE-EL-SPC-0001 | 100
58 | 3.2.2.2 | Inverter Technical Specification | 410-BE-EL-SPC-0002 | 100
59 | 3.2.2.3 | MV Station Technical Specification | 410-BE-EL-SPC-0003 | 100
60 | 3.2.2.4 | DC Connection (MC4) Technical Specification | 410-BE-EL-SPC-0004 | 100
61 | 3.2.2.5 | DC Cable Technical Specification | 410-BE-EL-SPC-0005 | 100
62 | 3.2.2.6 | LV Cable Technical Specification | 410-BE-EL-SPC-0006 | 0
63 | 3.2.2.7 | MV Cable Technical Specification | 410-BE-EL-SPC-0007 | 0
64 | 3.2.2.8 | MV Switchgear (CT, PT, Relay) Technical Specification | 410-BE-EL-SPC-0008 | 75
65 | 3.2.2.9 | Earthing and Lightning Technical Specification | 410-BE-EL-SPC-0009 | 0
66 | 3.2.2.10 | Auxiliary Transformer Technical Specification | 410-BE-EL-SPC-0013 | 0
67 | 3.2.2.11 | UPS and Battery Technical Specification | 410-BE-EL-SPC-0015 | 0
68 | 3.2.2.12 | Diesel Generator Technical Specification | 410-BE-EL-SPC-0016 | 0
69 | 3.2.2.13 | Monitoring System Technical Specification | 410-BE-TL-SPC-0010 | 75
70 | 3.2.2.14 | Data Logger Technical Specification | 410-BE-TL-SPC-0011 | 0
71 | 3.2.2.15 | Weather Station Technical Specification | 410-BE-TL-SPC-0012 | 60
72 | 3.2.2.16 | CCTV and NVR Technical Specification | 410-BE-TL-SPC-0014 | 60
73 | 3.2.2.17 | HVAC Technical Specification | 410-BE-ME-SPC-0017 | 0
74 | 3.2.2.18 | Piping Material, Plumbing Fittings, Pumps Technical Specification | 410-BE-ME-SPC-0018 | 0
75 | 3.2.2.19 | Septic Tank Technical Specification | 410-DE-ME-SPC-0096 | 45
76 | 3.2.2.20 | Water Tank Technical Specification | 410-DE-ME-SPC-0097 | 0
77 | 3.2.2.21 | Fire Alarm System Technical Specification | 410-BE-SF-SPC-0019 | 45
78 | 3.2.3 | PVSYST Report | 410-BE-EL-REP-0023 | 75
79 | 3.2.4 | General Layout | 410-BE-EL-DRW-0021 | 100
80 | 3.2.5 | General Single Line Diagram (GSLD) | 410-BE-EL-DRW-0020 | 75
81 | 3.2.6 | Plant Detailed Report | 410-BE-EL-REP-0024 | 100
82 | 3.3 | طراحی و اخذ تاییدیه عمرانی مطابق MDL ارایه شده |  | 38.64
83 | 3.3.1 | Topography of Field | 410-DE-CV-REP-0087 | 100
84 | 3.3.2 | Geotechnical Test Report | 410-DE-CV-REP-0088 | 90
85 | 3.3.3 | Ramming and Pull-Out Test Report | 410-DE-CV-REP-0089 | 90
86 | 3.3.4 | Hydrology Study Report | 410-DE-CV-REP-0090 | 60
87 | 3.3.5 | Site Fence Detail Drawing | 410-DE-CV-DRW-0091 | 100
88 | 3.3.6 | Logistic Area | 410-DE-CV-DRW-0092 | 75
89 | 3.3.7 | Buildings Foundation & Structure Calculation | 410-DE-CV-CAL-0093 | 0
90 | 3.3.8 | Buildings Foundation & Structure Drawing | 410-DE-CV-DRW-0094 | 47
91 | 3.3.9 | Parking Foundation & Structure Detail Drawing | 410-DE-CV-DRW-0098 | 0
92 | 3.3.10 | Power Plant Entrance Gate Drawing | 410-DE-CV-DRW-0099 | 0
93 | 3.3.11 | Parking Architectural Drawing | 410-DE-CV-DRW-0100 | 0
94 | 3.3.12 | Landscaping Layout | 410-DE-CV-DRW-0101 | 0
95 | 3.3.13 | Buildings Architectural Detail drawing | 410-DE-CV-DRW-0102 | 49
96 | 3.3.14 | Fence MTO | 410-DE-CV-MTO-0103 | 75
97 | 3.3.15 | Site Grading and Leveling | 410-DE-CV-DRW-0104 | 60
98 | 3.3.16 | Drainage For Insite of Plant & Implementation Detail Drawing | 410-DE-CV-DRW-0105 | 45
99 | 3.3.17 | Flood Managmant For Outsite of Plant & Implementation Detail Drawing | 410-DE-CV-DRW-0106 | 45
100 | 3.3.18 | Internal Road Layout & Implementation Detail Drawing | 410-DE-CV-DRW-0107 | 60
101 | 3.3.19 | Access Road Layout & Implementation Detail Drawing | 410-DE-CV-DRW-0108 | 0
102 | 3.3.20 | MV Station Foundation Calculation | 410-DE-CV-CAL-0109 | 75
103 | 3.3.21 | MV Station Foundation Drawings | 410-DE-CV-DRW-0110 | 75
104 | 3.3.22 | Auxiliary Transformer Foundation Detail Drawings | 410-DE-CV-DRW-0111 | 0
105 | 3.3.23 | Calculation Report for Structure | 410-DE-CV-CAL-0112 | 60
106 | 3.3.24 | Structure Detail Drawings | 410-DE-CV-DRW-0113 | 60
107 | 3.3.25 | PV Structure Ramming Location Details Drawing (Stacking) | 410-DE-CV-DRW-0114 | 0
108 | 3.3.26 | Solar Module Structure MTO | 410-DE-CV-MTO-0115 | 75
109 | 3.3.27 | Table UTM Point | 410-DE-CV-DRW-0116 | 0
110 | 3.3.28 | Structure, Entrance Gate and Foundation of Building MTO | 410-DE-CV-MTO-0117 | 0
111 | 3.3.29 | System Drainage Calculation | 410-DE-CV-CAL-0130 | 45
112 | 3.3.30 | Lighting Foundation Calculation | 410-DE-CV-CAL-0131 | 0
113 | 3.3.31 | Lightning Foundation Calculation | 410-DE-CV-CAL-0132 | 0
114 | 3.3.32 | Lightning Foundation Drawing | 410-DE-CV-DRW-0133 | 0
115 | 3.3.33 | Lighting and CCTV Pole Calculation | 410-DE-CV-CAL-0134 | 0
116 | 3.3.34 | Septic Tank Detail Drawing | 410-DE-CV-DRW-0135 | 0
117 | 3.3.35 | Water Tank Foundation Detail Drawing | 410-DE-CV-DRW-0136 | 0
118 | 3.3.36 | Calculation for Fence | 410-DE-CV-CAL-0137 | 75
119 | 3.3.37 | Material Requisition for Fence | 410-DE-CV-MRE-0167 | 60
120 | 3.4 | طراحی و اخذ تاییدیه الکتریکال مطابق MDL ارایه شده |  | 20.33
121 | 3.4.1 | Solar Module, Connector, Inverter and MV station MTO | 410-BE-EL-MTO-0025 | 75
122 | 3.4.2 | PV System Calculation Study (String Size, Optimum Tilt and Pitch) | 410-DE-EL-CAL-0022 | 0
123 | 3.4.3 | Strings Connection Diagram & Inverter Arrangement (DC Side) | 410-DE-EL-DRW-0026 | 75
124 | 3.4.4 | Module & Table Arrangement (DC Side) | 410-DE-EL-DRW-0027 | 75
125 | 3.4.5 | DC Cable Calculation | 410-DE-EL-CAL-0028 | 75
126 | 3.4.6 | DC Cable List, Labeling Code and MTO | 410-DE-EL-MTO-0029 | 75
127 | 3.4.7 | LVAC Cable Calculation | 410-DE-EL-CAL-0030 | 100
128 | 3.4.8 | LV Cable Termination List and MTO | 410-DE-EL-LST-0031 | 0
129 | 3.4.9 | LV Cable List, Labeling Code and MTO | 410-DE-EL-MTO-0032 | 90
130 | 3.4.10 | MV Cable Calculations | 410-DE-EL-CAL-0033 | 100
131 | 3.4.11 | MV Cable List, Labeling Code and MTO | 410-DE-EL-MTO-0034 | 100
132 | 3.4.12 | MV Cable Termination List and MTO | 410-DE-EL-LST-0035 | 0
133 | 3.4.13 | Electrical Cable Route and Section | 410-DE-EL-DRW-0036 | 0
134 | 3.4.14 | Cable Trench Layout | 410-DE-EL-DRW-0037 | 0
135 | 3.4.15 | Earthing System Calculation | 410-DE-EL-CAL-0038 | 60
136 | 3.4.16 | Earthing System Layout | 410-DE-EL-DRW-0039 | 60
137 | 3.4.17 | Lightning Protection Calculation | 410-DE-EL-CAL-0040 | 60
138 | 3.4.18 | Lightning Protection Layout | 410-DE-EL-DRW-0041 | 60
139 | 3.4.19 | Earthing and Lightning Protection MTO | 410-DE-EL-MTO-0042 | 0
140 | 3.4.20 | Protection Single Line Diagram (PSLD) | 410-DE-EL-DRW-0043 | 60
141 | 3.4.21 | CT and PT Calculations | 410-DE-EL-CAL-0044 | 0
142 | 3.4.22 | MV Switchgear Logic Diagram | 410-DE-EL-DRW-0045 | 0
143 | 3.4.23 | Trip Table | 410-DE-EL-REP-0046 | 0
144 | 3.4.24 | Alarm List | 410-DE-EL-LST-0047 | 0
145 | 3.4.25 | Indoor and Outdoor Electrical Plan & Details for Building | 410-DE-EL-DRW-0048 | 0
146 | 3.4.26 | MV Switchgear MTO | 410-DE-EL-MTO-0049 | 0
147 | 3.4.27 | Load List | 410-DE-EL-LST-0050 | 0
148 | 3.4.28 | LVAC Auxiliary Panel Single Line Diagram | 410-DE-EL-DRW-0051 | 0
149 | 3.4.29 | UPS Calculation | 410-DE-EL-CAL-0052 | 0
150 | 3.4.30 | AUX Equipment MTO (AUX Transformer, Diesel, UPS, Battery) | 410-DE-EL-MTO-0053 | 0
151 | 3.4.31 | Indoor and Outdoor Lighting Calculation | 410-DE-EL-CAL-0058 | 0
152 | 3.4.32 | Outdoor Lighting Pole Drawing | 410-DE-EL-DRW-0059 | 0
153 | 3.4.33 | Outdoor Lighting Layout and Switchboard | 410-DE-EL-DRW-0060 | 0
154 | 3.4.34 | Lighting System MTO | 410-DE-EL-MTO-0061 | 0
155 | 3.4.35 | Special Tools | 410-DE-EL-REP-0082 | 60
156 | 3.4.36 | MV Switchgear Schematic Diagram | 410-DE-EL-DRW-0128 | 0
157 | 3.4.37 | MV Switchgear Front View Drawing | 410-DE-EL-DRW-0129 | 0
158 | 3.4.38 | Material Requisition for Indoor Power and Lighting Distribution Panel | 410-DE-EL-MRE-0168 | 0
159 | 3.4.39 | Material Requisition for Auxiliary Transformer | 410-DE-EL-MRE-0169 | 0
160 | 3.4.40 | Material Requisition for PCC | 410-DE-EL-MRE-0170 | 0
161 | 3.4.41 | Material Requisition for MV Switchgear (CT, PT, Relay) | 410-DE-EL-MRE-0171 | 0
162 | 3.4.42 | Material Requisition for AC Cable | 410-DE-EL-MRE-0172 | 0
163 | 3.4.43 | Material Requisition for DC Cable | 410-DE-EL-MRE-0173 | 0
164 | 3.4.44 | Material Requisition for Earthing and Lightning | 410-DE-EL-MRE-0174 | 0
165 | 3.4.45 | Material Requisition for DC Connection (MC4) | 410-DE-EL-MRE-0175 | 0
166 | 3.4.46 | Material Requisition for Lighting System | 410-DE-EL-MRE-0176 | 0
167 | 3.4.47 | Material Requisition for UPS and Battery | 410-DE-EL-MRE-0177 | 0
168 | 3.4.48 | Material Requisition for Diesel Generator | 410-BE-EL-MRE-0186 | 0
169 | 3.5 | طراحی و اخذ تاییدیه مکانیکال مطابق MDL ارایه شده |  | 5.18
170 | 3.5.1 | Solar Panel Cleaning & Maintenance Procedures | 410-DE-ME-REP-0062 | 60
171 | 3.5.2 | HVAC Equipment Calculation | 410-DE-ME-CAL-0066 | 0
172 | 3.5.3 | HVAC Equipment Layout for Building | 410-DE-ME-DRW-0067 | 0
173 | 3.5.4 | HVAC and Piping System MTO | 410-DE-ME-MTO-0068 | 0
174 | 3.5.5 | Mechanical Drawing (Water Supply and Sewage Systems) | 410-DE-ME-DRW-0095 | 0
175 | 3.5.6 | Material Requisition for Septic Tank | 410-BE-ME-MRE-0183 | 0
176 | 3.5.7 | Material Requisition for Water | 410-BE-ME-MRE-0184 | 0
177 | 3.6 | طراحی و اخذ تاییدیه ایمنی مطابق MDL ارایه شده |  | 6.28
178 | 3.6.1 | Fire Fighting Equipment Arrangement of MV Switchgear Buildings | 410-DE-SF-DRW-0069 | 0
179 | 3.6.2 | Outdoor Fire Fighting Equipment & Shelter Arrangement | 410-DE-SF-DRW-0070 | 45
180 | 3.6.3 | Fire Alarm System Layout and Block Diagram | 410-DE-SF-DRW-0071 | 0
181 | 3.6.4 | Fire and Safety and F & G System MTO | 410-DE-SF-MTO-0072 | 0
182 | 3.6.5 | Material Requisition for Fire Alarm System | 410-DE-SF-MRE-0181 | 0
183 | 3.6.6 | Material Requisition for Fire Fighting Equipment Arrangement | 410-DE-SF-MRE-0182 | 0
184 | 3.7 | طراحی و اخذ تاییدیه ارتباطی مطابق MDL ارایه شده |  | 7.18
185 | 3.7.1 | CCTV System Block Diagram | 410-DE-TL-DRW-0054 | 0
186 | 3.7.2 | CCTV System Arrangement & Layout | 410-DE-TL-DRW-0055 | 0
187 | 3.7.3 | CCTV Pole Detail Drawing, Switchboard, CAFU Details | 410-DE-TL-DRW-0056 | 0
188 | 3.7.4 | CCTV System MTO | 410-DE-TL-MTO-0057 | 0
189 | 3.7.5 | SCADA System I/O List | 410-DE-TL-LST-0063 | 0
190 | 3.7.6 | Monitoring System Overall Diagram | 410-DE-TL-DRW-0064 | 0
191 | 3.7.7 | Telecommunication and Monitoring System MTO | 410-DE-TL-MTO-0065 | 0
192 | 3.7.8 | Material Requisition forTelecommunication and Monitoring Cable | 410-DE-TL-MRE-0178 | 0
193 | 3.7.9 | Material Requisition forFiber Optics | 410-BE-TL-MRE-0179 | 0
194 | 3.7.10 | Material Requisition for CCTV and NVR | 410-DE-TL-MRE-0180 | 0
195 | 3.7.11 | Material Requisition for Weather Station | 410-BE-TL-MRE-0185 | 60
196 | 3.8 | مستندات حوزه کیفیت مطابق MDL ارایه شده |  | 9
197 | 3.8.1 | Solar Panel Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0073 | 0
198 | 3.8.2 | Inverter Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0074 | 0
199 | 3.8.3 | MV Station Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0075 | 90
200 | 3.8.4 | UPS Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0076 | 0
201 | 3.8.5 | AUX Transformer Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0077 | 0
202 | 3.8.6 | Diesel Generator Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0078 | 0
203 | 3.8.7 | Weather Station Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0079 | 0
204 | 3.8.8 | Solar Structure Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0080 | 0
205 | 3.8.9 | SCADA and Monitoring System Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0081 | 0
206 | 3.8.10 | Project O&M General Instructions | 410-DE-QA-REP-0083 | 0
207 | 3.8.11 | Test Report of Solar Structure | 410-DE-QA-REP-0118 | 90
208 | 3.8.12 | Test Reports for PV Modules | 410-DE-QA-REP-0119 | 0
209 | 3.8.13 | Test Reports for Inverter | 410-DE-QA-REP-0120 | 0
210 | 3.8.14 | Test Reports for MV Sation | 410-DE-QA-REP-0121 | 0
211 | 3.8.15 | Test Reports for AC and DC Cables | 410-DE-QA-REP-0122 | 0
212 | 3.8.16 | Test Reports for Diesel Generators | 410-DE-QA-REP-0123 | 0
213 | 3.8.17 | Test Reports for AUX Transformer | 410-DE-QA-REP-0124 | 0
214 | 3.8.18 | Test Reports for Earthing and Ligthtning | 410-DE-QA-REP-0125 | 0
215 | 3.8.19 | Test Reports for MV Switchgear (CT, PT, Relay, …) | 410-DE-QA-REP-0126 | 0
216 | 3.8.20 | Test Reports for UPS and Battery | 410-DE-QA-REP-0127 | 0
217 | 3.8.21 | کدگذاری و تحویل مستندات پروژه |  | 0
218 | 4 | تامین و حمل کالا تجهیزات |  | 22.95
219 | 4.1 | خرید و حمل داخلی |  | 33.43
220 | 4.1.1 | خرید مصالح و تجهیز کارگاه |  | 98.23
221 | 4.1.1.1 | مصالح ساختمانی و ملزومات عمرانی |  | 100
222 | 4.1.1.2 | مصالح ،تجهیزات و ملزومات برقی ساختمان ها |  | 100
223 | 4.1.1.3 | تانک سپتیک و دو مخزن 10 هزار لیتری سه لایه |  | 100
224 | 4.1.1.4 | کلیه تجهیزات و ملزومات اداری |  | 90
225 | 4.1.1.5 | سایر خرید تجهیز کارگاه |  | 90
226 | 4.1.2 | فنس پیرامونی |  | 21
227 | 4.1.2.1 | سفارش گذاری فنس پیرامونی |  | 100
228 | 4.1.2.2 | ساخت و بازرسی فنس پیرامونی |  | 20
229 | 4.1.2.3 | حمل فنس پیرامونی |  | 0
230 | 4.1.3 | تابلو های توزیع داخلی و روشنایی |  | 0
231 | 4.1.3.1 | سفارش گذاری تابلو های توزیع داخلی و روشنایی |  | 0
232 | 4.1.3.2 | ساخت و بازرسی تابلو های توزیع داخلی و روشنایی |  | 0
233 | 4.1.3.3 | حمل تابلو های توزیع داخلی و روشنایی |  | 0
234 | 4.1.4 | ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 0
235 | 4.1.4.1 | سفارش گذاری ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 0
236 | 4.1.4.2 | ساخت و بازرسی ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 0
237 | 4.1.4.3 | حمل ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 0
238 | 4.1.5 | تابلوهای پست سوییچگیر |  | 0
239 | 4.1.5.1 | سفارش گذاری تابلوهای پست سوییچگیر |  | 0
240 | 4.1.5.2 | ساخت و بازرسی تابلوهای پست سوییچگیر |  | 0
241 | 4.1.5.3 | حمل تابلوهای پست سوییچگیر |  | 0
242 | 4.1.6 | ct& pt |  | 0
243 | 4.1.6.1 | سفارش گذاری ct& pt |  | 0
244 | 4.1.6.2 | ساخت و بازرسی ct& pt |  | 0
245 | 4.1.6.3 | حمل ct& pt |  | 0
246 | 4.1.7 | AC/LV و AC/MV کابل های |  | 2.5
247 | 4.1.7.1 | AC/LV و AC/MV سفارش گذاری کابل های |  | 50
248 | 4.1.7.2 | AC/LV و AC/MV ساخت و بازرسی کابل های |  | 0
249 | 4.1.7.3 | AC/LV و AC/MV حمل کابل های |  | 0
250 | 4.1.8 | DC کابل های |  | 96.25
251 | 4.1.8.1 | DC سفارش گذاری کابل های |  | 100
252 | 4.1.8.2 | DC ساخت و بازرسی کابل های |  | 100
253 | 4.1.8.3 | DC حمل کابل های |  | 75
254 | 4.1.9 | کابل های ارتباطی |  | 0
255 | 4.1.9.1 | سفارش گذاری کابل های ارتباطی |  | 0
256 | 4.1.9.2 | ساخت و بازرسی کابل های ارتباطی |  | 0
257 | 4.1.9.3 | حمل کابل های ارتباطی |  | 0
258 | 4.1.10 | Fiber Optics (انتقال دیتا داخلی نیروگاه) |  | 0
259 | 4.1.10.1 | Fiber Optics سفارش گذاری (انتقال دیتا داخلی نیروگاه) |  | 0
260 | 4.1.10.2 | Fiber Optics ساخت و بازرسی (انتقال دیتا داخلی نیروگاه) |  | 0
261 | 4.1.10.3 | Fiber Optics حمل (انتقال دیتا داخلی نیروگاه) |  | 0
262 | 4.1.11 | کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 0
263 | 4.1.11.1 | سفارش گذاری کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 0
264 | 4.1.11.2 | ساخت و بازرسی کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 0
265 | 4.1.11.3 | حمل کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 0
266 | 4.1.12 | MC4 |  | 100
267 | 4.1.12.1 | MC4 سفارش گذاری |  | 100
268 | 4.1.12.2 | MC4 ساخت و بازرسی |  | 100
269 | 4.1.12.3 | MC4 حمل |  | 100
270 | 4.1.13 | و تجهیزات جانبیCCTV سیستم |  | 0
271 | 4.1.13.1 | و تجهیزات جانبیCCTV سفارش گذاری سیستم |  | 0
272 | 4.1.13.2 | و تجهیزات جانبیCCTV ساخت و بازرسی سیستم |  | 0
273 | 4.1.13.3 | و تجهیزات جانبیCCTV حمل سیستم |  | 0
274 | 4.1.14 | تجهیزات سیستم روشنایی |  | 0
275 | 4.1.14.1 | سفارش گذاری تجهیزات سیستم روشنایی |  | 0
276 | 4.1.14.2 | ساخت و بازرسی تجهیزات سیستم روشنایی |  | 0
277 | 4.1.14.3 | حمل تجهیزات سیستم روشنایی |  | 0
278 | 4.1.15 | UPS سیستم |  | 0
279 | 4.1.15.1 | UPS سفارش گذاری سیستم |  | 0
280 | 4.1.15.2 | UPS خرید سیستم |  | 0
281 | 4.1.15.3 | UPS حمل سیستم |  | 0
282 | 4.1.16 | سیستم اعلان حریق و تجهیزات جانبی |  | 0
283 | 4.1.16.1 | سفارش گذاری سیستم اعلان حریق و تجهیزات جانبی |  | 0
284 | 4.1.16.2 | ساخت و بازرسی سیستم اعلان حریق و تجهیزات جانبی |  | 0
285 | 4.1.16.3 | حمل سیستم اعلان حریق و تجهیزات جانبی |  | 0
286 | 4.1.17 | سیستم اطفا حریق و تجهیزات جانبی |  | 0
287 | 4.1.17.1 | سفارش گذاری سیستم اطفا حریق و تجهیزات جانبی |  | 0
288 | 4.1.17.2 | ساخت و بازرسی سیستم اطفا حریق و تجهیزات جانبی |  | 0
289 | 4.1.17.3 | حمل سیستم اطفا حریق و تجهیزات جانبی |  | 0
290 | 4.1.18 | ایستگاه هواشناسی و سنسورها |  | 0
291 | 4.1.18.1 | سفارش گذاری ایستگاه هواشناسی و سنسورها |  | 0
292 | 4.1.18.2 | ساخت و بازرسی ایستگاه هواشناسی و سنسورها |  | 0
293 | 4.1.18.3 | حمل ایستگاه هواشناسی و سنسورها |  | 0
294 | 4.1.19 | لوازم یدکی |  | 0
295 | 4.1.19.1 | لوازم یدکی |  | 0
296 | 4.2 | خرید خارجی، حمل بین المللی و ترخیص |  | 7.5
297 | 4.2.1 | خرید سازه های نگهدارنده پنل ها و اینورترها |  | 7.5
298 | 4.2.1.1 | استعلام قیمت و سفارش گذاری سازه های نگهدارنده |  | 50
299 | 4.2.1.2 | ساخت سازه های نگهدارنده و بازرسی قبل حمل |  | 0
300 | 4.2.1.3 | حمل خارجی سازه های نگهدارنده |  | 0
301 | 4.2.1.4 | ترخیص سازه های نگهدارنده |  | 0
302 | 4.2.1.5 | حمل داخلی سازه های نگهدارنده و تحویل در سایت |  | 0
303 | 4.2.2 | خرید پنل های خورشیدی |  | 0
304 | 4.2.2.1 | استعلام قیمت و ثبت سفارش پنل های خورشیدی |  | 100
305 | 4.2.2.2 | ساخت پنل های خورشیدی و بازرسی قبل حمل |  | 100
306 | 4.2.2.3 | حمل خارجی پنل های خورشیدی |  | 60
307 | 4.2.2.4 | ترخیص پنل های خورشیدی |  | 0
308 | 4.2.2.5 | حمل داخلی پنل های خورشیدی و تحویل در سایت |  | 0
309 | 4.2.3 | خرید اینورترهای خورشیدی |  | 0
310 | 4.2.3.1 | استعلام قیمت و ثبت سفارش اینورترهای خورشیدی |  | 100
311 | 4.2.3.2 | ساخت اینورترهای خورشیدی و بازرسی قبل حمل |  | 95
312 | 4.2.3.3 | حمل خارجی اینورترهای خورشیدی |  | 0
313 | 4.2.3.4 | ترخیص اینورترهای خورشیدی |  | 0
314 | 4.2.3.5 | حمل داخلی اینورترهای خورشیدی و تحویل در سایت |  | 0
315 | 4.2.4 | خرید MV Station |  | 0
316 | 4.2.4.1 | استعلام قیمت و ثبت سفارش MV Station |  | 100
317 | 4.2.4.2 | ساخت MV Station و بازرسی قبل حمل |  | 30
318 | 4.2.4.3 | حمل خارجی MV Station |  | 0
319 | 4.2.4.4 | ترخیص MV Station |  | 0
320 | 4.2.4.5 | حمل داخلی MV Station و تحویل در سایت |  | 0
321 | 5 | عملیات اجرایی |  | 3.83
322 | 5.1 | تجهیز کارگاه |  | 99.54
323 | 5.1.1 | عملیات اجرایی |  | 99.54
324 | 5.1.1.1 | تانک سپتیک و دو مخزن 10 هزار لیتری سه لایه |  | 100
325 | 5.1.1.2 | کانکس نگهبانی |  | 100
326 | 5.1.1.3 | سایر تجهیز کارگاه |  | 85
327 | 5.2 | اجرای جاده دسترسی تا جاده اصلی |  | 100
328 | 5.2.1 | زیرسازی |  | 100
329 | 5.2.2 | شن ریزی |  | 100
330 | 5.3 | عملیات عمرانی |  | 2.03
331 | 5.3.1 | عملیات دسترسی و آماده سازی سایت |  | 24.75
332 | 5.3.1.1 | تسطیح و تحکیم زمین |  | 45
333 | 5.3.1.2 | اجرای گیت ورودی |  | 0
334 | 5.3.1.3 | احداث پارکینگ مسقف |  | 0
335 | 5.3.2 | اجرای سیستم زهکشی |  | 0
336 | 5.3.2.1 | اجرای سیستم زهکشی |  | 0
337 | 5.3.3 | اجرای فنس پیرامونی |  | 0.83
338 | 5.3.3.1 | اجرای فونداسیون و پایه فنس |  | 10
339 | 5.3.3.2 | اجرای فنس |  | 0
340 | 5.3.4 | اجرای فونداسیون MV Station |  | 0
341 | 5.3.4.1 | گودبرداری فونداسیون |  | 0
342 | 5.3.4.2 | بتن ریزی فونداسیون |  | 0
343 | 5.3.5 | ساختمان پست سوییچگیر |  | 0
344 | 5.3.5.1 | اجرای فونداسیون ساختمان پست سوییچگیر |  | 0
345 | 5.3.5.2 | سفت کاری ساختمان پست سوییچگیر |  | 0
346 | 5.3.5.3 | اجرای تاسیسات ساختمان پست سوییچگیر |  | 0
347 | 5.3.5.4 | نازک کاری ساختمان پست سوییچگیر |  | 0
348 | 5.3.5.5 | اجرای نمای ساختمان پست سوییچگیر |  | 0
349 | 5.3.5.6 | اجرای سیستم اعلام حریق ساختمان پست سوییچگیر |  | 0
350 | 5.3.5.7 | اجرای سیستم اطفا حریق ساختمان پست سوییچگیر |  | 0
351 | 5.3.6 | ساختمان مانیتورینگ |  | 0
352 | 5.3.6.1 | اجرای فونداسیون ساختمان مانیتورینگ |  | 0
353 | 5.3.6.2 | سفت کاری ساختمان مانیتورینگ |  | 0
354 | 5.3.6.3 | اجرای تاسیسات ساختمان مانیتورینگ |  | 0
355 | 5.3.6.4 | نازک کاری ساختمان مانیتورینگ |  | 0
356 | 5.3.6.5 | اجرای نمای ساختمان مانیتورینگ |  | 0
357 | 5.3.6.6 | اجرای سیستم اعلام حریق ساختمان مانیتورینگ |  | 0
358 | 5.3.6.7 | اجرای سیستم اطفا حریق ساختمان مانیتورینگ |  | 0
359 | 5.3.6.8 | کلیه تجهیزات و ملزومات |  | 0
360 | 5.3.7 | ساختمان نگهبانی |  | 0
361 | 5.3.7.1 | اجرای فونداسیون ساختمان نگهبانی |  | 0
362 | 5.3.7.2 | سفت کاری ساختمان نگهبانی |  | 0
363 | 5.3.7.3 | اجرای تاسیسات ساختمان نگهبانی |  | 0
364 | 5.3.7.4 | نازک کاری ساختمان نگهبانی |  | 0
365 | 5.3.7.5 | اجرای نمای ساختمان نگهبانی |  | 0
366 | 5.3.7.6 | اجرای سیستم اعلام حریق ساختمان نگهبانی |  | 0
367 | 5.3.7.7 | اجرای سیستم اطفا حریق ساختمان نگهبانی |  | 0
368 | 5.4 | عملیات مکانیکال |  | 0
369 | 5.4.1 | نقشه برداری پایه ها و میخ کوبی |  | 0
370 | 5.4.2 | پایه کوبی |  | 0
371 | 5.4.3 | نصب متعلقات استراکچرها |  | 0
372 | 5.4.4 | نصب پنل ها |  | 0
373 | 5.5 | عملیات الکتریکال |  | 0
374 | 5.5.1 | اجرای ترانشه و کانال عبور فیبر نوری |  | 0
375 | 5.5.2 | نصب سازه اینورتر و وایرینگ اینورترهای سایت |  | 0
376 | 5.5.3 | اجرای سیستم زمین نیروگاه |  | 0
377 | 5.5.4 | تابلوهای فشار متوسط و کلیه متعلقات |  | 0
378 | 5.5.5 | تابلوهای فشار ضعیف و کلیه متعلقات |  | 0
379 | 5.5.6 | کلیه کابل های فشار ضعیف نیروگاهac |  | 0
380 | 5.5.7 | کلیه کابل های فشار متوسط نیروگاهac |  | 0
381 | 5.5.8 | کابل dc |  | 0
382 | 5.5.9 | اجرای کابل های فیبر نوری |  | 0
383 | 5.5.10 | نصب ایستگاه هواشناسی و سنسورها |  | 0
384 | 5.5.11 | MV Station نصب |  | 0
385 | 5.5.12 | اجرای کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و بستر مخابراتی با پست بالادست به جز فیبر نوری |  | 0
386 | 5.5.13 | نصب ترانسفورماتور کمکی و دیزل |  | 0
387 | 5.5.14 | نصب یو پی اس |  | 0
388 | 5.5.15 | سیستم حفاظت صاعقه |  | 0
389 | 5.5.16 | اجرای کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و ارسال دیتا |  | 0
390 | 5.5.17 | کلیه متعلقات مربوط به کابل کشی و سیم کشی |  | 0
391 | 5.5.17.1 | نصب لدر |  | 0
392 | 5.5.17.2 | اجرای لوله پلی اتیلن و فلکسی |  | 0
393 | 5.5.17.3 | اجرای سرسیم و کابل شو |  | 0
394 | 5.5.17.4 | اجرای سر کابل |  | 0
395 | 5.5.18 | نصب سیستم روشنایی |  | 0
396 | 5.5.18.1 | اجرای فونداسیون سیستم روشنایی |  | 0
397 | 5.5.18.2 | کابل کشی سیستم روشنایی |  | 0
398 | 5.5.18.3 | نصب پایه ها و چراغ ها |  | 0
399 | 5.5.19 | CCTV نصب سیستم |  | 0
400 | 5.5.19.1 | اجرای فونداسیون دوربین |  | 0
401 | 5.5.19.2 | کابل کشی دوربین ها |  | 0
402 | 5.5.19.3 | نصب پایه ها و دوربین ها |  | 0
403 | 6 | تست و تحویل |  | 0
404 | 6.1 | تست و راه اندازی نیروگاه |  | 0
405 | 6.1.1 | تست کلیه کابل های فشار ضعیف نیروگاهac |  | 0
406 | 6.1.2 | تست کلیه کابل های فشار متوسط نیروگاهac |  | 0
407 | 6.1.3 | تست کابل dc |  | 0
408 | 6.1.4 | تست تابلوهای فشار متوسط و کلیه متعلقات |  | 0
409 | 6.1.5 | تست کابل شبکه مورد نیازسیستم انتقال دیتا و اسکادا |  | 0
410 | 6.1.6 | تست سیستم زمین نیروگاه |  | 0
411 | 6.1.7 | تست کلیه متعلقات مربوط به کابل کشی و سیم کشی |  | 0
412 | 6.1.8 | تست تابلوهای فشار ضعیف و کلیه متعلقات |  | 0
413 | 6.1.9 | تست کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و بستر مخابراتی با پست بالادست |  | 0
414 | 6.1.10 | تست کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و ارسال دیتا |  | 0
415 | 6.1.11 | تست یو پی اس |  | 0
416 | 6.1.12 | تست کلیه تجهیزات مربوط به دوربین |  | 0
417 | 6.1.13 | تست سیستم روشنایی |  | 0
418 | 6.1.14 | تست سیستم اعلام حریق |  | 0
419 | 6.1.15 | تست سیستم اطفا حریق |  | 0
420 | 6.1.16 | تست سیستم حفاظت صاعقه |  | 0
421 | 6.1.17 | تست ترانسفورماتور کمکی و دیزل |  | 0
422 | 6.2 | ارایه نقشه های ازبیلت |  | 0
423 | 6.2.1 | ارایه نقشه های ازبیلت الکتریکال |  | 0
424 | 6.2.2 | ارایه نقشه های ازبیلت مکانیکال |  | 0
425 | 6.2.3 | ارایه نقشه های ازبیلت civil |  | 0
426 | 6.3 | راه اندازی، اتصال به شبکه و پلمپ کنتور |  | 0
427 | 6.3.1 | راه اندازی، اتصال به شبکه و پلمپ کنتور |  | 0
428 | 6.4 | آموزش |  | 0
429 | 6.4.1 | آموزش |  | 0
430 | 6.5 | برچیدن کارگاه |  | 0
431 | 6.5.1 | برچیدن کارگاه |  | 0
432 | 7 | پایان |  | 0