## Sheet1
|  | پروژه احداث نیروگاه خورشیدی 20 مگاواتی زارچ یزد شماره قرارداد: PKPS-P2-C2-0410 | [77 empty] | 2026-05-18 |  | RJ
[80 empty] | RJ | IFC | CM
[80 empty] | CM | IFA | AN
DOCUMENT NO. : 410-DE-PM-LST-0084 |  | Document Name : Master Document List | [18 empty] | Discipline | Rev. | [57 empty] | AN | IFI | AP
[21 empty] | PM | 06 | [57 empty] | AP | AFC | IFC
[21 empty] | Page 1 of 1 | [58 empty] | AFC |  | IFA
|  | #REF! | [79 empty] | IFI
No | Document Number | Description | Discipline | Class | Plan Date |  | Status | Man-Hour | W.V | %Complete | تاریخ برنامه ای اولین ارسال | شروع طبق برنامه | پایان طبق برنامه | Hold By | Delay | Last Status | [6 empty] | REV 00 | [9 empty] | REV 01 | [9 empty] | REV 02 | [7 empty] | REV 03 | [7 empty] | REV 04 | [6 empty] | REV 05 | [6 empty] | REV 06
[5 empty] | Start | Finish
Engineering | [7 empty] | 3949 | 100% | 25.27% | [5 empty] | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Reply Date | Conclusion | Answer Date | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Reply Date | Conclusion | Answer Date | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Reply sheet | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Reply sheet | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results
Electrical | [7 empty] | 1448 | 36.67% | 26.01%
1 | 410-BE-EL-SPC-0001 | Solar Panel Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 | AP | 5 | 0.1266% | 100% |  | 1404/10/24 | 1404/11/3 |  |  | 50 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AP | 50 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AP
2 | 410-BE-EL-SPC-0002 | Inverter Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 | AP | 5 | 0.1266% | 100% |  | 1404/10/24 | 1404/11/3 |  |  | 51 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | CM | 51 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | CM | 2026-05-11 | AP | 2026-05-12
3 | 410-BE-EL-SPC-0003 | MV Station Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 | AP | 5 | 0.1266% | 100% |  | 1404/10/24 | 1404/11/3 |  |  | 52 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | CM | 52 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | CM | 2026-05-11 | AP | 2026-05-12
4 | 410-BE-EL-SPC-0004 | DC Connection (MC4) Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 | AP | 5 | 0.1266% | 100% |  | 1404/10/24 | 1404/11/3 |  |  | 22 | 2026-04-19 | IFA | 01 | - | 2026-05-02 | CM | 2 | 2026-02-02 | IFC | 00 | - | 2026-02-16 | CM | 2026-04-19 |  |  | 22 | 2026-04-19 | IFA | 01 | - | 2026-05-02 | CM | 2026-05-13 | AP | 2026-05-16
5 | 410-BE-EL-SPC-0005 | DC Cable Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 | AP | 5 | 0.1266% | 100% |  | 1404/10/24 | 1404/11/3 |  |  | 24 | 2026-04-19 | IFA | 01 | - | 2026-05-02 | AP | 2 | 2026-02-02 | IFC | 00 | - | 2026-02-15 | CM | 2026-04-13 |  |  | 24 | 2026-04-19 | IFA | 01 | - | 2026-05-02 | AP
6 | 410-BE-EL-SPC-0006 | LV Cable Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 |  | 5 | 0.1266% | 0% |  | 1404/10/24 | 1404/11/3 | [7 empty] | 0
7 | 410-BE-EL-SPC-0007 | MV Cable Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 |  | 5 | 0.1266% | 0% |  | 1404/10/24 | 1404/11/3 | [7 empty] | 0
8 | 410-BE-EL-SPC-0008 | MV Switchgear (CT, PT, Relay) Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 | AN | 5 | 0.1266% | 75% |  | 1404/10/24 | 1404/11/3 | NT | 13 | 53 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AN | 53 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AN | 2026-05-11
9 | 410-BE-EL-SPC-0009 | Earthing and Lightning Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 |  | 5 | 0.1266% | 0% |  | 1404/10/24 | 1404/11/3 | [7 empty] | 0
10 | 410-BE-EL-SPC-0013 | Auxiliary Transformer Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 |  | 5 | 0.1266% | 0% |  | 1404/10/24 | 1404/11/3 | [7 empty] | 0
11 | 410-BE-EL-SPC-0015 | UPS and Battery Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 |  | 5 | 0.1266% | 0% |  | 1404/10/24 | 1404/11/3 | [7 empty] | 0
12 | 410-BE-EL-SPC-0016 | Diesel Generator Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 |  | 5 | 0.1266% | 0% |  | 1404/10/24 | 1404/11/3 | [7 empty] | 0
13 | 410-BE-EL-DRW-0020 | General Single Line Diagram (GSLD) | Electrical | FA | 2026-01-25 | 2026-02-03 | AN | 21 | 0.5318% | 75% |  | 1404/11/5 | 1404/11/14 | NT | 89 | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AN |  | 2026-02-02 | IFC | 00 | - | 2026-02-12 | CM |  |  |  | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AN | 2026-04-19
14 | 410-BE-EL-DRW-0021 | General Layout | Electrical | FA | 2026-01-22 | 2026-01-30 | AFC | 21 | 0.5318% | 100% |  | 1404/11/2 | 1404/11/10 |  |  | 47 | 2026-05-04 | AFC | 04 | - | 2026-04-26 | AP |  | 2026-01-27 | IFC | 00 | - | 2026-02-10 | CM |  |  |  | 1 | 2026-02-16 | IFA | 1 | - | 2026-02-18 | CM |  |  |  | 17 | 2026-04-06 | IFA | 2 | - | 2026-04-20 | AN |  | 29 | 2026-04-25 | IFA | 03 | - | 2026-04-26 | AP |  | 47 | 2026-05-04 | AFC | 04
15 | 410-DE-EL-CAL-0022 | PV System Calculation Study (String Size, Optimum Tilt and Pitch) | Electrical | FA | 2026-02-01 | 2026-02-10 |  | 27 | 0.6837% | 0% |  | 1404/11/12 | 1404/11/21 | [7 empty] | 0
16 | 410-BE-EL-REP-0023 | PVSYST Report | Electrical | FA | 2026-01-22 | 2026-01-31 | AN | 18 | 0.4558% | 75% |  | 1404/11/2 | 1404/11/11 | NT | 89 | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AN |  | 2026-01-31 | IFC | 00 | - | 2026-02-10 | CM | 2026-02-14 |  |  | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AN | 2026-04-18
17 | 410-BE-EL-REP-0024 | Plant Detailed Report | Electrical | FA | 2026-01-26 | 2026-02-04 | AP | 21 | 0.5318% | 100% |  | 1404/11/6 | 1404/11/15 |  |  | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AP | 1 | 2026-01-31 | IFC | 00 | - | 2026-02-10 | CM |  |  |  | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AP
18 | 410-BE-EL-MTO-0025 | Solar Module, Connector, Inverter and MV station MTO | Electrical | FI | 2026-02-05 | 2026-02-14 | AN | 18 | 0.4558% | 75% |  | 1404/11/16 | 1404/11/25 | NT | 68 | 10 | 2026-03-07 | IFC | 00 |  | 2026-03-11 | AN | 10 | 2026-03-07 | IFC | 00 |  | 2026-03-11 | AN
19 | 410-DE-EL-DRW-0026 | Strings Connection Diagram & Inverter Arrangement (DC Side) | Electrical | FA | 2026-02-04 | 2026-02-13 | AN | 21 | 0.5318% | 75% |  | 1404/11/15 | 1404/11/24 | NT | 68 | 10 | 2026-03-07 | IFC | 00 |  | 2026-03-11 | AN | 10 | 2026-03-07 | IFC | 00 |  | 2026-03-11 | AN
20 | 410-DE-EL-DRW-0027 | Module & Table Arrangement (DC Side) | Electrical | FA | 2026-01-31 | 2026-02-09 | AN | 21 | 0.5318% | 75% |  | 1404/11/11 | 1404/11/20 | NT | 68 | 10 | 2026-03-07 | IFC | 00 | 7 | 2026-03-11 | AN | 10 | 2026-03-07 | IFC | 00 | 7 | 2026-03-11 | AN
21 | 410-DE-EL-CAL-0028 | DC Cable Calculation | Electrical | FA | 2026-02-14 | 2026-02-23 | AN | 27 | 0.6837% | 75% |  | 1404/11/25 | 1404/12/4 | NT | 68 | 10 | 2026-03-07 | IFC | 00 | 5 | 2026-03-11 | AN | 10 | 2026-03-07 | IFC | 00 | 5 | 2026-03-11 | AN
22 | 410-DE-EL-MTO-0029 | DC Cable List, Labeling Code and MTO | Electrical | FI | 2026-02-18 | 2026-02-26 | AN | 19 | 0.4811% | 75% |  | 1404/11/29 | 1404/12/7 | NT | 68 | 10 | 2026-03-07 | IFC | 00 | 8 | 2026-03-11 | AN | 10 | 2026-03-07 | IFC | 00 | 8 | 2026-03-11 | AN
23 | 410-DE-EL-CAL-0030 | LVAC Cable Calculation | Electrical | FA | 2026-02-10 | 2026-02-14 | AP | 27 | 0.6837% | 100% |  | 1404/11/21 | 1404/11/25 |  |  | 70 | 2026-05-12 | IFA | 02 | - | 2026-05-13 | AP | 17 | 2026-04-06 | IFC | 00 | - | 2026-04-20 | RJ |  |  |  | 41 | 2026-04-29 | IFC | 01 | - | 2026-05-03 | CM | 2026-05-12 |  |  | 70 | 2026-05-12 | IFA | 02 |  | 2026-05-13 | AP
24 | 410-DE-EL-LST-0031 | LV Cable Termination List and MTO | Electrical | FI | 2026-02-15 | 2026-02-23 |  | 14 | 0.3545% | 0% |  | 1404/11/26 | 1404/12/4 | [7 empty] | 0
25 | 410-DE-EL-MTO-0032 | LV Cable List, Labeling Code and MTO | Electrical | FI | 2026-02-24 | 2026-02-27 | IFI | 19 | 0.4811% | 90% |  | 1404/12/5 | 1404/12/8 | PK | 0 | 78 | 2026-05-18 | IFI | 02 | - | 2026-05-03 | CM | 17 | 2026-04-06 | IFI | 00 | - | 2026-04-20 | CM |  |  |  | 42 | 2026-04-29 | IFI | 01 | - | 2026-05-03 | CM |  |  |  | 78 | 2026-05-18 | IFI | 02
26 | 410-DE-EL-CAL-0033 | MV Cable Calculations | Electrical | FA | 2026-02-10 | 2026-02-14 | AP | 27 | 0.6837% | 100% |  | 1404/11/21 | 1404/11/25 |  |  | 65 | 2026-05-11 | IFA | 02 | - | 2026-05-11 | AP | 17 | 2026-04-06 | IFC | 00 | - | 2026-04-20 | RJ |  |  |  | 43 | 2026-05-02 | IFC | 01 | - | 2026-05-03 | AN | 2026-05-11 |  |  | 65 | 2026-05-11 | IFA | 02 |  | 2026-05-11 | AP
27 | 410-DE-EL-MTO-0034 | MV Cable List, Labeling Code and MTO | Electrical | FI | 2026-02-15 | 2026-02-23 | AP | 18 | 0.4558% | 100% |  | 1404/11/26 | 1404/12/4 |  |  | 17 | 2026-04-06 | IFI | 00 | - | 2026-04-20 | CM | 17 | 2026-04-06 | IFI | 00 | - | 2026-04-20 | CM | 2026-05-02 | AP | 2026-05-03
28 | 410-DE-EL-LST-0035 | MV Cable Termination List and MTO | Electrical | FI | 2026-02-24 | 2026-03-04 |  | 14 | 0.3545% | 0% |  | 1404/12/5 | 1404/12/13 | [7 empty] | 0
29 | 410-DE-EL-DRW-0036 | Electrical Cable Route and Section | Electrical | FA | 2026-01-31 | 2026-02-09 |  | 22 | 0.5571% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
30 | 410-DE-EL-DRW-0037 | Cable Trench Layout | Electrical | FA | 2026-01-31 | 2026-02-09 |  | 22 | 0.5571% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
31 | 410-DE-EL-CAL-0038 | Earthing System Calculation | Electrical | FA | 2026-02-10 | 2026-02-14 | CM | 27 | 0.6837% | 60% |  | 1404/11/21 | 1404/11/25 | NT | 5 | 60 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM | 60 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM
32 | 410-DE-EL-DRW-0039 | Earthing System Layout | Electrical | FA | 2026-02-15 | 2026-02-24 | CM | 22 | 0.5571% | 60% |  | 1404/11/26 | 1404/12/5 | NT | 5 | 61 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM | 61 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM
33 | 410-DE-EL-CAL-0040 | Lightning Protection Calculation | Electrical | FA | 2026-01-31 | 2026-02-04 | CM | 27 | 0.6837% | 60% |  | 1404/11/11 | 1404/11/15 | NT | 6 | 54 | 2026-05-04 | IFC | 00 |  | 2026-05-12 | CM | 54 | 2026-05-04 | IFC | 00 |  | 2026-05-12 | CM
34 | 410-DE-EL-DRW-0041 | Lightning Protection Layout | Electrical | FA | 2026-02-05 | 2026-02-14 | CM | 21 | 0.5318% | 60% |  | 1404/11/16 | 1404/11/25 | NT | 5 | 62 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM | 62 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM
35 | 410-DE-EL-MTO-0042 | Earthing and Lightning Protection MTO | Electrical | FI | 2026-02-15 | 2026-02-24 |  | 19 | 0.4811% | 0% |  | 1404/11/26 | 1404/12/5 | [7 empty] | 0
36 | 410-DE-EL-DRW-0043 | Protection Single Line Diagram (PSLD) | Electrical | FA | 2026-02-04 | 2026-02-13 | CM | 21 | 0.5318% | 60% |  | 1404/11/15 | 1404/11/24 | NT | 5 | 63 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM | 63 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM
37 | 410-DE-EL-CAL-0044 | CT and PT Calculations | Electrical | FA | 2026-02-04 | 2026-02-08 |  | 27 | 0.6837% | 0% |  | 1404/11/15 | 1404/11/19 | [7 empty] | 0
38 | 410-DE-EL-DRW-0045 | MV Switchgear Logic Diagram | Electrical | FA | 2026-02-09 | 2026-02-18 |  | 20 | 0.5065% | 0% |  | 1404/11/20 | 1404/11/29 | [7 empty] | 0
39 | 410-DE-EL-REP-0046 | Trip Table | Electrical | FA | 2026-02-19 | 2026-02-28 |  | 21 | 0.5318% | 0% |  | 1404/11/30 | 1404/12/9 | [7 empty] | 0
40 | 410-DE-EL-LST-0047 | Alarm List | Electrical | FA | 2026-02-19 | 2026-02-28 |  | 14 | 0.3545% | 0% |  | 1404/11/30 | 1404/12/9 | [7 empty] | 0
41 | 410-DE-EL-DRW-0048 | Indoor and Outdoor Electrical Plan & Details for Building | Electrical | FA | 2026-01-31 | 2026-02-09 |  | 21 | 0.5318% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
42 | 410-DE-EL-MTO-0049 | MV Switchgear MTO | Electrical | FI | 2026-02-14 | 2026-02-23 |  | 19 | 0.4811% | 0% |  | 1404/11/25 | 1404/12/4 | [7 empty] | 0
43 | 410-DE-EL-LST-0050 | Load List | Electrical | FA | 2026-02-28 | 2026-03-08 |  | 14 | 0.3545% | 0% |  | 1404/12/9 | 1404/12/17 | [7 empty] | 0
44 | 410-DE-EL-DRW-0051 | LVAC Auxiliary Panel Single Line Diagram | Electrical | FA | 2026-01-28 | 2026-02-06 |  | 21 | 0.5318% | 0% |  | 1404/11/8 | 1404/11/17 | [7 empty] | 0
45 | 410-DE-EL-CAL-0052 | UPS Calculation | Electrical | FA | 2026-02-07 | 2026-02-11 |  | 27 | 0.6837% | 0% |  | 1404/11/18 | 1404/11/22 | [7 empty] | 0
46 | 410-DE-EL-MTO-0053 | AUX Equipment MTO (AUX Transformer, Diesel, UPS, Battery) | Electrical | FA | 2026-02-12 | 2026-02-21 |  | 19 | 0.4811% | 0% |  | 1404/11/23 | 1404/12/2 | [7 empty] | 0
47 | 410-DE-EL-CAL-0058 | Indoor and Outdoor Lighting Calculation | Electrical | FA | 2026-01-31 | 2026-02-04 |  | 27 | 0.6837% | 0% |  | 1404/11/11 | 1404/11/15 | [7 empty] | 0
48 | 410-DE-EL-DRW-0059 | Outdoor Lighting Pole Drawing | Electrical | FA | 2026-02-05 | 2026-02-13 |  | 23 | 0.5824% | 0% |  | 1404/11/16 | 1404/11/24 | [7 empty] | 0
49 | 410-DE-EL-DRW-0060 | Outdoor Lighting Layout and Switchboard | Electrical | FA | 2026-02-14 | 2026-02-22 |  | 23 | 0.5824% | 0% |  | 1404/11/25 | 1404/12/3 | [7 empty] | 0
50 | 410-DE-EL-MTO-0061 | Lighting System MTO | Electrical | FI | 2026-02-23 | 2026-03-03 |  | 19 | 0.4811% | 0% |  | 1404/12/4 | 1404/12/12 | [7 empty] | 0
51 | 410-DE-EL-REP-0082 | Special Tools | Electrical | FA | 2026-06-07 | 2026-06-16 | CM | 22 | 0.5571% | 60% |  | 1405/3/17 | 1405/3/26 | NT | 6 | 58 | 2026-05-06 | IFC | 00 |  | 2026-05-12 | CM | 58 | 2026-05-06 | IFC | 00 |  | 2026-05-12 | CM
52 | 410-DE-EL-DRW-0128 | MV Switchgear Schematic Diagram | Electrical | FA | 2026-02-04 | 2026-02-08 |  | 20 | 0.5065% | 0% |  | 1404/11/15 | 1404/11/19 | [7 empty] | 0
53 | 410-DE-EL-DRW-0129 | MV Switchgear Front View Drawing | Electrical | FA | 2026-02-09 | 2026-02-13 |  | 20 | 0.5065% | 0% |  | 1404/11/20 | 1404/11/24 | [7 empty] | 0
54 | 410-BE-EL-DSH-0146 | Solar Panel Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | AP | 5 | 0.1266% | 100% |  | 1404/10/28 | 1404/11/7 |  |  | 55 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AP | 55 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AP
55 | 410-BE-EL-DSH-0147 | Inverter Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | IFC | 5 | 0.1266% | 45% |  | 1404/10/28 | 1404/11/7 | PK | 126 | Email | 2026-01-12 | IFC | 00 |  | 0 |  | Email | 2026-01-12 | IFC | 00
56 | 410-BE-EL-DSH-0148 | MV Station Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | AN | 5 | 0.1266% | 75% |  | 1404/10/28 | 1404/11/7 | NT | 51 | 15 | 2026-03-26 | IFC | 00 | 2 | 2026-03-28 | AN | 15 | 2026-03-26 | IFC | 00 | 2 | 2026-03-28 | AN
57 | 410-BE-EL-DSH-0149 | DC Connection (MC4) Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | AP | 5 | 0.1266% | 100% |  | 1404/10/28 | 1404/11/7 |  |  | 21 | 2026-04-19 | IFC | 00 | - | 2026-05-02 | AP | 21 | 2026-04-19 | IFC | 00 | - | 2026-05-02 | AP
58 | 410-BE-EL-DSH-0150 | DC Cable Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | AP | 5 | 0.1266% | 100% |  | 1404/10/28 | 1404/11/7 |  |  | 23 | 2026-04-19 | IFC | 00 | - | 2026-05-02 | AP | 23 | 2026-04-19 | IFC | 00 | - | 2026-05-02 | AP
59 | 410-BE-EL-DSH-0151 | LV Cable Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 |  | 5 | 0.1266% | 0% |  | 1404/10/28 | 1404/11/7 | [7 empty] | 0
60 | 410-BE-EL-DSH-0152 | MV Cable Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 |  | 5 | 0.1266% | 0% |  | 1404/10/28 | 1404/11/7 | [7 empty] | 0
61 | 410-BE-EL-DSH-0153 | MV Switchgear (CT, PT, Relay) Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 |  | 5 | 0.1266% | 0% |  | 1404/10/28 | 1404/11/7 | [7 empty] | 0
62 | 410-BE-EL-DSH-0154 | Earthing and Lightning Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | CM | 5 | 0.1266% | 60% |  | 1404/10/28 | 1404/11/7 | NT | 80 | Email | 2026-02-02 | IFC | 00 | - | 2026-02-27 | CM | Email | 2026-02-02 | IFC | 00 | - | 2026-02-27 | CM
63 | 410-BE-EL-DSH-0155 | Auxiliary Transformer Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | RJ | 5 | 0.1266% | 0% |  | 1404/10/28 | 1404/11/7 | NT | 13 | 56 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | RJ | 56 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | RJ
64 | 410-BE-EL-DSH-0156 | UPS and Battery Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 |  | 5 | 0.1266% | 0% |  | 1404/10/28 | 1404/11/7 | [7 empty] | 0
65 | 410-BE-EL-DSH-0157 | Diesel Generator Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 |  | 2 | 0.05065% | 0% |  | 1404/10/28 | 1404/11/7 | [7 empty] | 0
66 | 410-DE-EL-MRE-0168 | Material Requisition for Indoor Power and Lighting Distribution Panel | Electrical | FA | 2026-02-23 | 2026-02-27 |  | 45 | 1.14% | 0% |  | 1404/12/4 | 1404/12/8 | [7 empty] | 0
67 | 410-DE-EL-MRE-0169 | Material Requisition for Auxiliary Transformer | Electrical | FA | 2026-02-22 | 2026-03-03 |  | 45 | 1.14% | 0% |  | 1404/12/3 | 1404/12/12 | [7 empty] | 0
68 | 410-DE-EL-MRE-0170 | Material Requisition for PCC | Electrical | FA | 2026-05-13 | 2026-05-22 |  | 45 | 1.14% | 0% |  | 1405/2/23 | 1405/3/1 | [7 empty] | 0
69 | 410-DE-EL-MRE-0171 | Material Requisition for MV Switchgear (CT, PT, Relay) | Electrical | FA | 2026-07-07 | 2026-07-16 |  | 45 | 1.14% | 0% |  | 1405/4/16 | 1405/4/25 | [7 empty] | 0
70 | 410-DE-EL-MRE-0172 | Material Requisition for AC Cable | Electrical | FA | 2026-05-20 | 2026-05-29 |  | 35 | 0.8863% | 0% |  | 1405/2/30 | 1405/3/8 | [7 empty] | 0
71 | 410-DE-EL-MRE-0173 | Material Requisition for DC Cable | Electrical | FA | 2026-06-27 | 2026-07-06 |  | 35 | 0.8863% | 0% |  | 1405/4/6 | 1405/4/15 | [7 empty] | 0
72 | 410-DE-EL-MRE-0174 | Material Requisition for Earthing and Lightning | Electrical | FA | 2026-05-26 | 2026-06-04 |  | 45 | 1.14% | 0% |  | 1405/3/5 | 1405/3/14 | [7 empty] | 0
73 | 410-DE-EL-MRE-0175 | Material Requisition for DC Connection (MC4) | Electrical | FA | 2026-06-24 | 2026-07-03 |  | 35 | 0.8863% | 0% |  | 1405/4/3 | 1405/4/12 | [7 empty] | 0
74 | 410-DE-EL-MRE-0176 | Material Requisition for Lighting System | Electrical | FA | 2026-02-28 | 2026-03-07 |  | 45 | 1.14% | 0% |  | 1404/12/9 | 1404/12/16 | [7 empty] | 0
75 | 410-DE-EL-MRE-0177 | Material Requisition for UPS and Battery | Electrical | FA | 2026-04-28 | 2026-05-07 |  | 45 | 1.14% | 0% |  | 1405/2/8 | 1405/2/17 | [7 empty] | 0
76 | 410-BE-EL-MRE-0186 | Material Requisition for Diesel Generator | Electrical | FA | 2026-06-27 | 2026-07-06 |  | 40 | 1.013% | 0% |  | 1405/4/6 | 1405/4/15 | [7 empty] | 0
Civil | [7 empty] | 1131 | 28.64% | 37.94%
77 | 410-DE-CV-REP-0087 | Topography of Field | Civil | FI | 2026-02-03 | 2026-02-12 | AP | 28 | 0.709% | 100% |  | 1404/11/14 | 1404/11/23 |  |  | 35 | 2026-04-27 | IFC | 00 | - | 2026-05-02 | AP | 35 | 2026-04-27 | IFC | 00 | - | 2026-05-02 | AP
78 | 410-DE-CV-REP-0088 | Geotechnical Test Report | Civil | FI | 2026-02-03 | 2026-02-12 | IFI | 28 | 0.709% | 90% |  | 1404/11/14 | 1404/11/23 | PK | 21 | 33 | 2026-04-27 | IFI | 00 |  | 0 |  | 33 | 2026-04-27 | IFI | 00
79 | 410-DE-CV-REP-0089 | Ramming and Pull-Out Test Report | Civil | FI | 2026-02-03 | 2026-02-12 | IFI | 28 | 0.709% | 90% |  | 1404/11/14 | 1404/11/23 | PK | 21 | 34 | 2026-04-27 | IFI | 00 |  | 0 |  | 34 | 2026-04-27 | IFI | 00
80 | 410-DE-CV-REP-0090 | Hydrology Study Report | Civil | FI | 2026-02-03 | 2026-02-12 | CM | 28 | 0.709% | 60% |  | 1404/11/14 | 1404/11/23 | NT | 16 | 37 | 2026-04-28 | IFC | 00 | - | 2026-05-02 | CM | 37 | 2026-04-28 | IFC | 00 | - | 2026-05-02 | CM
81 | 410-DE-CV-DRW-0091 | Site Fence Detail Drawing | Civil | FA | 2026-02-18 | 2026-02-27 | AFC | 28 | 0.709% | 100% |  | 1404/11/29 | 1404/12/8 |  |  | 49 | 2026-05-04 | AFC | 06 | - | 2026-05-05 | AFC | 3 | 2026-02-19 | IFC | 00 | - | 2026-02-22 | RJ |  |  |  | - | 2026-02-22 | IFA | 1 | - | 2026-03-07 |  |  |  |  | 6 | 2026-02-23 | IFC | 02 | 9 | 2026-03-17 | RJ |  | 18 | 2026-04-08 | IFC | 3 | - | 2026-04-12 | AN |  | 27 | 2026-04-21 | IFA | 4 | - | 2026-04-26 | AN | 30 | 2026-04-27 | IFA | 05 | - | 2026-05-02 | AP | 49 | 2026-05-04 | AFC | 06 | - | 2026-05-05 | AFC
82 | 410-DE-CV-DRW-0092 | Logistic Area | Civil | FA | 2026-01-31 | 2026-02-09 | AN | 28 | 0.709% | 75% |  | 1404/11/11 | 1404/11/20 | NT | 13 | 48 | 2026-05-04 | AFC | 02 | - | 2026-05-05 | AN | 5 | 2026-02-21 | IFC | 00 | 10 | 2026-03-16 | CM |  |  |  | 39 | 2026-04-28 | IFA | 01 | - | 2026-05-02 | AP |  |  |  | 48 | 2026-05-04 | AFC | 02 |  | 2026-05-05 | AN
83 | 410-DE-CV-CAL-0093 | Buildings Foundation & Structure Calculation | Civil | FA | 2026-02-03 | 2026-02-12 | Deleted |  |  | 0% |  | 1404/11/14 | 1404/11/23 | [7 empty] | 0
84 | 410-DE-CV-CAL-0187 | Swichgear Building Foundation & Structure Calculation | Civil | FA |  |  |  | 11 | 0.2786% | 0% | [10 empty] | 0
85 | 410-DE-CV-CAL-0188 | Control Building Foundation & Structure Calculation | Civil | FA |  |  |  | 11 | 0.2786% | 0% | [10 empty] | 0
86 | 410-DE-CV-CAL-0189 | Guard Building Foundation & Structure Calculation | Civil | FA |  |  |  | 11 | 0.2786% | 0% | [10 empty] | 0
87 | 410-DE-CV-DRW-0094 | Buildings Foundation & Structure Drawing | Civil | FA | 2026-02-08 | 2026-02-17 | Deleted |  |  | 0% |  | 1404/11/19 | 1404/11/28 | [7 empty] | 0
88 | 410-DE-CV-DRW-0190 | Swichgear Building Foundation & Structure Drawing | Civil | FA |  |  |  | 9 | 0.2279% | 0% | [10 empty] | 0
89 | 410-DE-CV-DRW-0191 | Control Building Foundation & Structure Drawing | Civil | FA |  |  |  | 9 | 0.2279% | 0% | [10 empty] | 0
90 | 410-DE-CV-DRW-0192 | Guard Building Foundation & Structure Drawing | Civil | FA |  |  |  | 9 | 0.2279% | 0% | [10 empty] | 0
91 | 410-DE-CV-DRW-0098 | Parking Foundation & Structure Detail Drawing | Civil | FA | 2026-02-03 | 2026-02-12 |  | 26 | 0.6584% | 0% |  | 1404/11/14 | 1404/11/23 | [7 empty] | 0
92 | 410-DE-CV-DRW-0099 | Power Plant Entrance Gate Drawing | Civil | FA | 2026-02-22 | 2026-03-03 |  | 26 | 0.6584% | 0% |  | 1404/12/3 | 1404/12/12 | [7 empty] | 0
93 | 410-DE-CV-DRW-0100 | Parking Architectural Drawing | Civil | FA | 2026-02-10 | 2026-02-19 |  | 29 | 0.7344% | 0% |  | 1404/11/21 | 1404/11/30 | [7 empty] | 0
94 | 410-DE-CV-DRW-0101 | Landscaping Layout | Civil | FA | 2026-01-31 | 2026-02-08 |  | 29 | 0.7344% | 0% |  | 1404/11/11 | 1404/11/19 | [7 empty] | 0
95 | 410-DE-CV-DRW-0102 | Buildings Architectural Detail drawing | Civil | FA | 2026-02-12 | 2026-02-21 | Deleted |  |  | 0% |  | 1404/11/23 | 1404/12/2 |  |  | 12 | 2026-03-15 | IFC | 00 | 11 | 2026-03-17 | RJ | 12 | 2026-03-15 | IFC | 00 | 11 | 2026-03-17 | RJ
96 | 410-DE-CV-DRW-0193 | Swichgear Building Architectural Detail drawing | Civil | FA |  |  | AN | 10 | 0.2532% | 75% |  |  |  | NT | 2 | 73 | 2026-05-13 | IFC | 00 |  | 2026-05-16 | AN | 73 | 2026-05-13 | IFC | 00 |  | 2026-05-16 | AN
97 | 410-DE-CV-DRW-0194 | Control Building Architectural Detail drawing | Civil | FA |  |  | CM | 10 | 0.2532% | 60% |  |  |  | NT | 13 | 45 | 2026-05-04 | IFC | 00 |  | 2026-05-05 | CM | 45 | 2026-05-04 | IFC | 00 |  | 2026-05-05 | CM
98 | 410-DE-CV-DRW-0195 | Guard Building Architectural Detail drawing | Civil | FA |  |  | CM | 10 | 0.2532% | 60% |  |  |  | NT | 13 | 46 | 2026-05-04 | IFC | 00 |  | 2026-05-05 | CM | 46 | 2026-05-04 | IFC | 00 |  | 2026-05-05 | CM
99 | 410-DE-CV-MTO-0103 | Fence MTO | Civil | FI | 2026-02-22 | 2026-03-02 | AN | 25 | 0.6331% | 75% |  | 1404/12/3 | 1404/12/11 | NT | 22 | 26 | 2026-04-21 | IFI | 2 | - | 2026-04-26 | AN | 3 | 2026-02-19 | IFI | 00 | 16 | 2026-03-17 | CM |  |  |  | 18 | 2026-04-08 | IFI | 1 | - | 2026-04-12 | AN |  |  |  | 26 | 2026-04-21 | IFI | 2 | - | 2026-04-26 | AN | 2026-04-27
100 | 410-DE-CV-DRW-0104 | Site Grading and Leveling | Civil | FA | 2026-02-13 | 2026-02-22 | IFA | 29 | 0.7344% | 60% |  | 1404/11/24 | 1404/12/3 | PK | 21 | 32 | 2026-04-27 | IFA | 01 | 12 | 2026-03-17 | CM | Email | 2026-02-02 | IFC | 00 | 12 | 2026-03-17 | CM | 2026-04-27 |  |  | 32 | 2026-04-27 | IFA | 01
101 | 410-DE-CV-DRW-0105 | Drainage For Insite of Plant & Implementation Detail Drawing | Civil | FA | 2026-02-13 | 2026-02-21 | IFC | 29 | 0.7344% | 45% |  | 1404/11/24 | 1404/12/2 | PK | 20 | 38 | 2026-04-28 | IFC | 01 | 13 | 2026-03-17 | RJ | Email | 2026-02-02 | IFC | 00 | 13 | 2026-03-17 | RJ |  |  |  | 38 | 2026-04-28 | IFC | 01
102 | 410-DE-CV-DRW-0106 | Flood Managmant For Outsite of Plant & Implementation Detail Drawing | Civil | FA | 2026-02-16 | 2026-02-25 | IFC | 29 | 0.7344% | 45% |  | 1404/11/27 | 1404/12/6 | PK | 20 | 40 | 2026-04-28 | IFC | 01 | 14 | 2026-03-17 | RJ | Email | 2026-02-02 | IFC | 00 | 14 | 2026-03-17 | RJ |  |  |  | 40 | 2026-04-28 | IFC | 01
103 | 410-DE-CV-DRW-0107 | Internal Road Layout & Implementation Detail Drawing | Civil | FA | 2026-01-31 | 2026-02-09 | IFA | 29 | 0.7344% | 60% |  | 1404/11/11 | 1404/11/20 | PK | 20 | 36 | 2026-04-28 | IFA | 01 | 15 | 2026-03-17 | CM | Email | 2026-02-02 | IFC | 00 | 15 | 2026-03-17 | CM |  |  |  | 36 | 2026-04-28 | IFA | 01
104 | 410-DE-CV-DRW-0108 | Access Road Layout & Implementation Detail Drawing | Civil | FA | 2026-01-31 | 2026-02-09 |  | 29 | 0.7344% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
105 | 410-DE-CV-CAL-0109 | MV Station Foundation Calculation | Civil | FA | 2026-01-28 | 2026-02-06 | AN | 36 | 0.9116% | 75% |  | 1404/11/8 | 1404/11/17 | NT | 1 | 67 | 2026-05-11 | IFC | 00 | 410-05-PK-NT-C-0091 | 2026-05-17 | AN | 67 | 2026-05-11 | IFC | 00 | 410-05-PK-NT-C-0091 | 2026-05-17 | AN
106 | 410-DE-CV-DRW-0110 | MV Station Foundation Drawings | Civil | FA | 2026-02-02 | 2026-02-11 | AN | 29 | 0.7344% | 75% |  | 1404/11/13 | 1404/11/22 | NT | 1 | 68 | 2026-05-11 | IFC | 00 | 410-05-PK-NT-C-0092 | 2026-05-17 | AN | 68 | 2026-05-11 | IFC | 00 | 410-05-PK-NT-C-0092 | 2026-05-17 | AN
107 | 410-DE-CV-DRW-0111 | Auxiliary Transformer Foundation Detail Drawings | Civil | FA | 2026-01-28 | 2026-02-06 |  | 29 | 0.7344% | 0% |  | 1404/11/8 | 1404/11/17 | [7 empty] | 0
108 | 410-DE-CV-CAL-0112 | Calculation Report for Structure | Civil | FA | 2026-02-07 | 2026-02-16 | CM | 36 | 0.9116% | 60% |  | 1404/11/18 | 1404/11/27 | NT | 39 | 16 | 2026-04-04 | IFC | 00 | - | 2026-04-09 | CM | 16 | 2026-04-04 | IFC | 00 | - | 2026-04-09 | CM
109 | 410-DE-CV-DRW-0113 | Structure Detail Drawings | Civil | FA | 2026-02-13 | 2026-02-22 | CM | 29 | 0.7344% | 60% |  | 1404/11/24 | 1404/12/3 | NT | 28 | 16 | 2026-04-04 | IFC | 00 | - | 2026-04-20 | CM | 16 | 2026-04-04 | IFC | 00 | - | 2026-04-20 | CM
110 | 410-DE-CV-DRW-0114 | PV Structure Ramming Location Details Drawing (Stacking) | Civil | FA | 2026-02-07 | 2026-02-16 |  | 29 | 0.7344% | 0% |  | 1404/11/18 | 1404/11/27 | [7 empty] | 0
111 | 410-DE-CV-MTO-0115 | Solar Module Structure MTO | Civil | FI | 2026-02-17 | 2026-02-26 | AN | 25 | 0.6331% | 75% |  | 1404/11/28 | 1404/12/7 | NT | 36 | 16 | 2026-04-04 | IFI | 00 | - | 2026-04-12 | AN | 16 | 2026-04-04 | IFI | 00 | - | 2026-04-12 | AN
112 | 410-DE-CV-DRW-0116 | Table UTM Point | Civil | FA | 2026-02-17 | 2026-02-25 |  | 29 | 0.7344% | 0% |  | 1404/11/28 | 1404/12/6 | [7 empty] | 0
113 | 410-DE-CV-MTO-0117 | Structure, Entrance Gate and Foundation of Building MTO | Civil | FI | 2026-02-26 | 2026-03-07 |  | 25 | 0.6331% | 0% |  | 1404/12/7 | 1404/12/16 | [7 empty] | 0
114 | 410-DE-CV-CAL-0130 | System Drainage Calculation | Civil | FA | 2026-02-13 | 2026-02-22 | IFC | 36 | 0.9116% | 45% |  | 1404/11/24 | 1404/12/3 | PK | 21 | 31 | 2026-04-27 | IFC | 00 |  | 0 |  | 31 | 2026-04-27 | IFC | 00
115 | 410-DE-CV-CAL-0131 | Lighting Foundation Calculation | Civil | FA | 2026-01-31 | 2026-02-04 |  | 36 | 0.9116% | 0% |  | 1404/11/11 | 1404/11/15 | [7 empty] | 0
116 | 410-DE-CV-CAL-0132 | Lightning Foundation Calculation | Civil | FA | 2026-01-28 | 2026-02-01 |  | 36 | 0.9116% | 0% |  | 1404/11/8 | 1404/11/12 | [7 empty] | 0
117 | 410-DE-CV-DRW-0133 | Lightning Foundation Drawing | Civil | FA | 2026-02-05 | 2026-02-09 |  | 28 | 0.709% | 0% |  | 1404/11/16 | 1404/11/20 | [7 empty] | 0
118 | 410-DE-CV-CAL-0134 | Lighting and CCTV Pole Calculation | Civil | FA | 2026-01-31 | 2026-02-04 |  | 36 | 0.9116% | 0% |  | 1404/11/11 | 1404/11/15 | [7 empty] | 0
119 | 410-DE-CV-DRW-0135 | Septic Tank Detail Drawing | Civil | FA | 2026-02-10 | 2026-02-14 |  | 28 | 0.709% | 0% |  | 1404/11/21 | 1404/11/25 | [7 empty] | 0
120 | 410-DE-CV-DRW-0136 | Water Tank Foundation Detail Drawing | Civil | FA | 2026-02-09 | 2026-02-13 |  | 28 | 0.709% | 0% |  | 1404/11/20 | 1404/11/24 | [7 empty] | 0
121 | 410-DE-CV-CAL-0137 | Calculation for Fence | Civil | FA | 2026-02-13 | 2026-02-22 | AN | 28 | 0.709% | 75% |  | 1404/11/24 | 1404/12/3 | NT | 22 | 25 | 2026-04-21 | IFA | 3 | - | 2026-04-26 | AN |  | 2026-02-20 | IFC | 00 | [6 empty] | 6 | 2026-02-23 | IFA | 1 | 4 | 2026-03-16 | CM |  |  |  | 18 | 2026-04-08 | IFA | 2 | - | 2026-04-12 | CM |  | 25 | 2026-04-21 | IFA | 3 | - | 2026-04-26 | AN | 2026-04-27
122 | 410-DE-CV-MRE-0167 | Material Requisition for Fence | Civil | FA | 2026-03-03 | 2026-03-03 | CM | 70 | 1.773% | 60% |  | 1404/12/12 | 1404/12/12 | NT | 63 | 6 | 2026-02-23 | IFC | 00 | - | 2026-03-16 | CM | 6 | 2026-02-23 | IFC | 00 | - | 2026-03-16 | CM
Quality | [7 empty] | 580 | 14.69% | 9%
123 | 410-DE-QA-REP-0073 | Solar Panel Installation Manual & Operation & Maintenance | Quality | FI | 2026-06-03 | 2026-06-03 |  | 29 | 0.7344% | 0% |  | 1405/3/13 | 1405/3/13 | [7 empty] | 0
124 | 410-DE-QA-REP-0074 | Inverter Installation Manual & Operation & Maintenance | Quality | FI | 2026-07-16 | 2026-07-16 |  | 29 | 0.7344% | 0% |  | 1405/4/25 | 1405/4/25 | [7 empty] | 0
125 | 410-DE-QA-REP-0075 | MV Station Installation Manual & Operation & Maintenance | Quality | FI | 2026-08-05 | 2026-08-05 | IFI | 29 | 0.7344% | 90% |  | 1405/5/14 | 1405/5/14 | PK | 0 | 74 | 2026-05-18 | IFI | 00 |  | 0 |  | 74 | 2026-05-18 | IFI | 00
126 | 410-DE-QA-REP-0076 | UPS Installation Manual & Operation & Maintenance | Quality | FI | 2026-08-16 | 2026-08-16 |  | 29 | 0.7344% | 0% |  | 1405/5/25 | 1405/5/25 | [7 empty] | 0
127 | 410-DE-QA-REP-0077 | AUX Transformer Installation Manual & Operation & Maintenance | Quality | FI | 2026-08-04 | 2026-08-04 |  | 29 | 0.7344% | 0% |  | 1405/5/13 | 1405/5/13 | [7 empty] | 0
128 | 410-DE-QA-REP-0078 | Diesel Generator Installation Manual & Operation & Maintenance | Quality | FI | 2026-08-04 | 2026-08-04 |  | 29 | 0.7344% | 0% |  | 1405/5/13 | 1405/5/13 | [7 empty] | 0
129 | 410-DE-QA-REP-0079 | Weather Station Installation Manual & Operation & Maintenance | Quality | FI | 2026-08-17 | 2026-08-17 |  | 29 | 0.7344% | 0% |  | 1405/5/26 | 1405/5/26 | [7 empty] | 0
130 | 410-DE-QA-REP-0080 | Solar Structure Installation Manual & Operation & Maintenance | Quality | FI | 2026-05-04 | 2026-05-04 |  | 29 | 0.7344% | 0% |  | 1405/2/14 | 1405/2/14 | [7 empty] | 0
131 | 410-DE-QA-REP-0081 | SCADA and Monitoring System Installation Manual & Operation & Maintenance | Quality | FI | 2026-08-06 | 2026-08-06 |  | 29 | 0.7344% | 0% |  | 1405/5/15 | 1405/5/15 | [7 empty] | 0
132 | 410-DE-QA-REP-0083 | Project O&M General Instructions | Quality | FI | 2026-08-26 | 2026-08-26 |  | 29 | 0.7344% | 0% |  | 1405/6/4 | 1405/6/4 | [7 empty] | 0
133 | 410-DE-QA-REP-0118 | Test Report of Solar Structure | Quality | FI | 2026-06-03 | 2026-06-04 | CM | 29 | 0.7344% | 90% |  | 1405/3/13 | 1405/3/14 | NT | 37 | 16 | 2026-04-04 | IFI | 00 | - | 2026-04-11 | CM | 16 | 2026-04-04 | IFI | 00 | - | 2026-04-11 | CM
134 | 410-DE-QA-REP-0119 | Test Reports for PV Modules | Quality | FI | 2026-06-03 | 2026-06-04 |  | 29 | 0.7344% | 0% |  | 1405/3/13 | 1405/3/14 | [7 empty] | 0
135 | 410-DE-QA-REP-0120 | Test Reports for Inverter | Quality | FI | 2026-07-16 | 2026-07-17 |  | 29 | 0.7344% | 0% |  | 1405/4/25 | 1405/4/26 | [7 empty] | 0
136 | 410-DE-QA-REP-0121 | Test Reports for MV Sation | Quality | FI | 2026-08-10 | 2026-08-11 |  | 29 | 0.7344% | 0% |  | 1405/5/19 | 1405/5/20 | [7 empty] | 0
137 | 410-DE-QA-REP-0122 | Test Reports for AC and DC Cables | Quality | FI | 2026-08-19 | 2026-08-20 | Deleted |  |  | 0% |  | 1405/5/28 | 1405/5/29 | [7 empty] | 0
138 | 410-DE-QA-REP-0196 | Test Reports for AC Cables | Quality | FI |  |  |  | 14.5 | 0.3672% | 0% | [10 empty] | 0
139 | 410-DE-QA-REP-0197 | Test Reports for DC Cables | Quality | FI |  |  |  | 14.5 | 0.3672% | 0% | [10 empty] | 0
140 | 410-DE-QA-REP-0123 | Test Reports for Diesel Generators | Quality | FI | 2026-09-01 | 2026-09-01 |  | 29 | 0.7344% | 0% |  | 1405/6/10 | 1405/6/10 | [7 empty] | 0
141 | 410-DE-QA-REP-0124 | Test Reports for AUX Transformer | Quality | FI | 2026-09-01 | 2026-09-01 |  | 29 | 0.7344% | 0% |  | 1405/6/10 | 1405/6/10 | [7 empty] | 0
142 | 410-DE-QA-REP-0125 | Test Reports for Earthing and Ligthtning | Quality | FI | 2026-08-06 | 2026-08-07 |  | 29 | 0.7344% | 0% |  | 1405/5/15 | 1405/5/16 | [7 empty] | 0
143 | 410-DE-QA-REP-0126 | Test Reports for MV Switchgear (CT, PT, Relay, …) | Quality | FI | 2026-08-17 | 2026-08-18 |  | 29 | 0.7344% | 0% |  | 1405/5/26 | 1405/5/27 | [7 empty] | 0
144 | 410-DE-QA-REP-0127 | Test Reports for UPS and Battery | Quality | FI | 2026-08-19 | 2026-08-20 |  | 29 | 0.7344% | 0% |  | 1405/5/28 | 1405/5/29 | [7 empty] | 0
Telecom | [7 empty] | 307 | 7.774% | 12.31%
145 | 410-BE-TL-SPC-0010 | Monitoring System Technical Specification | Telecom | FA | 2026-01-14 | 2026-01-23 | AN | 8 | 0.2026% | 75% |  | 1404/10/24 | 1404/11/3 | NT | 2 | 71 | 2026-05-13 | IFC | 00 |  | 2026-05-16 | AN | 71 | 2026-05-13 | IFC | 00 |  | 2026-05-16 | AN
146 | 410-BE-TL-SPC-0011 | Data Logger Technical Specification | Telecom | FA | 2026-01-27 | 2026-02-05 |  | 8 | 0.2026% | 0% |  | 1404/11/7 | 1404/11/16 | [7 empty] | 0
147 | 410-BE-TL-SPC-0012 | Weather Station Technical Specification | Telecom | FA | 2026-01-27 | 2026-02-05 | CM | 8 | 0.2026% | 60% |  | 1404/11/7 | 1404/11/16 | NT | 7 | 57 | 2026-05-06 | IFC | 00 |  | 2026-05-11 | CM | 57 | 2026-05-06 | IFC | 00 |  | 2026-05-11 | CM
148 | 410-BE-TL-SPC-0014 | CCTV and NVR Technical Specification | Telecom | FA | 2026-01-27 | 2026-02-05 | CM | 8 | 0.2026% | 60% |  | 1404/11/7 | 1404/11/16 | NT | 5 | 66 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM | 66 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM
149 | 410-DE-TL-DRW-0054 | CCTV System Block Diagram | Telecom | FA | 2026-02-10 | 2026-02-13 |  | 19 | 0.4811% | 0% |  | 1404/11/21 | 1404/11/24 | [7 empty] | 0
150 | 410-DE-TL-DRW-0055 | CCTV System Arrangement & Layout | Telecom | FA | 2026-02-14 | 2026-02-17 |  | 19 | 0.4811% | 0% |  | 1404/11/25 | 1404/11/28 | [7 empty] | 0
151 | 410-DE-TL-DRW-0056 | CCTV Pole Detail Drawing, Switchboard, CAFU Details | Telecom | FA | 2026-02-18 | 2026-02-21 |  | 22 | 0.5571% | 0% |  | 1404/11/29 | 1404/12/2 | [7 empty] | 0
152 | 410-DE-TL-MTO-0057 | CCTV System MTO | Telecom | FI | 2026-02-22 | 2026-03-03 |  | 18 | 0.4558% | 0% |  | 1404/12/3 | 1404/12/12 | [7 empty] | 0
153 | 410-DE-TL-LST-0063 | SCADA System I/O List | Telecom | FA | 2026-02-04 | 2026-02-07 |  | 14 | 0.3545% | 0% |  | 1404/11/15 | 1404/11/18 | [7 empty] | 0
154 | 410-DE-TL-DRW-0064 | Monitoring System Overall Diagram | Telecom | FA | 2026-02-19 | 2026-02-22 |  | 20 | 0.5065% | 0% |  | 1404/11/30 | 1404/12/3 | [7 empty] | 0
155 | 410-DE-TL-MTO-0065 | Telecommunication and Monitoring System MTO | Telecom | FI | 2026-02-23 | 2026-02-26 |  | 19 | 0.4811% | 0% |  | 1404/12/4 | 1404/12/7 | [7 empty] | 0
156 | 410-BE-TL-DSH-0158 | Monitoring System Datasheet | Telecom | FA | 2026-01-18 | 2026-01-27 | CM | 7 | 0.1773% | 60% |  | 1404/10/28 | 1404/11/7 | NT | 2 | 72 | 2026-05-13 | IFC | 00 |  | 2026-05-16 | CM | 72 | 2026-05-13 | IFC | 00 |  | 2026-05-16 | CM
157 | 410-BE-TL-DSH-0159 | Data Logger Datasheet | Telecom | FA | 2026-01-31 | 2026-02-09 |  | 7 | 0.1773% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
158 | 410-BE-TL-DSH-0160 | Weather Station Datasheet | Telecom | FA | 2026-01-31 | 2026-02-09 |  | 3 | 0.07597% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
159 | 410-BE-TL-DSH-0161 | CCTV and NVR Datasheet | Telecom | FA | 2026-01-31 | 2026-02-09 |  | 7 | 0.1773% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
160 | 410-DE-TL-MRE-0178 | Material Requisition forTelecommunication and Monitoring Cable | Telecom | FA | 2026-07-17 | 2026-07-21 |  | 30 | 0.7597% | 0% |  | 1405/4/26 | 1405/4/30 | [7 empty] | 0
161 | 410-BE-TL-MRE-0179 | Material Requisition forFiber Optics | Telecom | FA | 2026-06-08 | 2026-06-12 |  | 30 | 0.7597% | 0% |  | 1405/3/18 | 1405/3/22 | [7 empty] | 0
162 | 410-DE-TL-MRE-0180 | Material Requisition for CCTV and NVR | Telecom | FA | 2026-03-04 | 2026-03-08 |  | 30 | 0.7597% | 0% |  | 1404/12/13 | 1404/12/17 | [7 empty] | 0
163 | 410-BE-TL-MRE-0185 | Material Requisition for Weather Station | Telecom | FA | 2026-05-14 | 2026-05-18 | CM | 30 | 0.7597% | 60% |  | 1405/2/24 | 1405/2/28 | NT | 5 | 64 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM | 64 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM
Mechanical | [7 empty] | 226 | 5.723% | 6.173%
164 | 410-BE-ME-SPC-0017 | HVAC Technical Specification | Mechanical | FA | 2026-01-27 | 2026-02-05 |  | 8 | 0.2026% | 0% |  | 1404/11/7 | 1404/11/16 | [7 empty] | 0
165 | 410-BE-ME-SPC-0018 | Piping Material, Plumbing Fittings, Pumps Technical Specification | Mechanical | FA | 2026-01-27 | 2026-02-05 |  | 8 | 0.2026% | 0% |  | 1404/11/7 | 1404/11/16 | [7 empty] | 0
166 | 410-DE-ME-REP-0062 | Solar Panel Cleaning & Maintenance Procedures | Mechanical | FA | 2026-02-23 | 2026-02-26 | CM | 15 | 0.3798% | 60% |  | 1404/12/4 | 1404/12/7 | NT | 15 |  | 2026-02-02 | IFC | 00 | - | 2026-05-03 | CM |  | 2026-02-02 | IFC | 00 | - | 2026-05-03 | CM
167 | 410-DE-ME-CAL-0066 | HVAC Equipment Calculation | Mechanical | FA | 2026-02-10 | 2026-02-19 |  | 20 | 0.5065% | 0% |  | 1404/11/21 | 1404/11/30 | [7 empty] | 0
168 | 410-DE-ME-DRW-0067 | HVAC Equipment Layout for Building | Mechanical | FA | 2026-02-20 | 2026-02-23 | Deleted |  |  | 0% |  | 1404/12/1 | 1404/12/4 | [7 empty] | 0
169 | 410-DE-ME-DRW-0198 | HVAC Equipment Layout for Swichgear Building | Mechanical | FA |  |  |  | 6.6667 | 0.1688% | 0% | [10 empty] | 0
170 | 410-DE-ME-DRW-0199 | HVAC Equipment Layout for Control Building | Mechanical | FA |  |  |  | 6.6667 | 0.1688% | 0% | [10 empty] | 0
171 | 410-DE-ME-DRW-0200 | HVAC Equipment Layout for Guard Building | Mechanical | FA |  |  |  | 6.6667 | 0.1688% | 0% | [10 empty] | 0
172 | 410-DE-ME-MTO-0068 | HVAC and Piping System MTO | Mechanical | FI | 2026-02-24 | 2026-02-27 |  | 19 | 0.4811% | 0% |  | 1404/12/5 | 1404/12/8 | [7 empty] | 0
173 | 410-DE-ME-DRW-0095 | Mechanical Drawing (Water Supply and Sewage Systems) | Mechanical | FA | 2026-02-10 | 2026-02-13 |  | 20 | 0.5065% | 0% |  | 1404/11/21 | 1404/11/24 | [7 empty] | 0
174 | 410-DE-ME-SPC-0096 | Septic Tank Technical Specification | Mechanical | FA | 2026-01-27 | 2026-02-05 | IFC | 4 | 0.1013% | 45% |  | 1404/11/7 | 1404/11/16 | PK | 0 | 75 | 2026-05-18 | IFC | 00 |  | 0 |  | 75 | 2026-05-18 | IFC | 00
175 | 410-DE-ME-SPC-0097 | Water Tank Technical Specification | Mechanical | FA | 2026-01-27 | 2026-02-05 |  | 4 | 0.1013% | 0% |  | 1404/11/7 | 1404/11/16 | [7 empty] | 0
176 | 410-BE-ME-DSH-0162 | HVAC Datasheet | Mechanical | FA | 2026-01-31 | 2026-02-09 |  | 7 | 0.1773% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
177 | 410-BE-ME-DSH-0163 | Piping Material, Plumbing Fittings, Pumps Datasheet | Mechanical | FA | 2026-01-31 | 2026-02-09 |  | 7 | 0.1773% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
178 | 410-BE-ME-DSH-0164 | Septic Tank Datasheet | Mechanical | FA | 2026-01-31 | 2026-02-09 | IFC | 7 | 0.1773% | 45% |  | 1404/11/11 | 1404/11/20 | PK | 0 | 76 | 2026-05-18 | IFC | 00 |  | 0 |  | 76 | 2026-05-18 | IFC | 00
179 | 410-BE-ME-DSH-0165 | Water Tank Datasheet | Mechanical | FA | 2026-01-31 | 2026-02-09 |  | 7 | 0.1773% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
180 | 410-BE-ME-MRE-0183 | Material Requisition for Septic Tank | Mechanical | FA | 2026-02-15 | 2026-02-17 |  | 40 | 1.013% | 0% |  | 1404/11/26 | 1404/11/28 | [7 empty] | 0
181 | 410-BE-ME-MRE-0184 | Material Requisition for Water | Mechanical | FA | 2026-02-14 | 2026-02-16 |  | 40 | 1.013% | 0% |  | 1404/11/25 | 1404/11/27 | [7 empty] | 0
Safety | [7 empty] | 149 | 3.773% | 14.19%
182 | 410-BE-SF-SPC-0019 | Fire Alarm System Technical Specification | Safety | FA | 2026-01-27 | 2026-02-05 | IFC | 8 | 0.2026% | 45% |  | 1404/11/7 | 1404/11/16 | PK | 6 | 69 | 2026-05-12 | IFC | 00 |  | 0 |  | 69 | 2026-05-12 | IFC | 00
183 | 410-DE-SF-DRW-0069 | Fire Fighting Equipment Arrangement of MV Switchgear Buildings | Safety | FA | 2026-02-16 | 2026-02-23 |  | 19 | 0.4811% | 0% |  | 1404/11/27 | 1404/12/4 | [7 empty] | 0
184 | 410-DE-SF-DRW-0070 | Outdoor Fire Fighting Equipment & Shelter Arrangement | Safety | FA | 2026-02-20 | 2026-02-28 | IFC | 19 | 0.4811% | 45% |  | 1404/12/1 | 1404/12/9 | PK | 0 | 77 | 2026-05-18 | IFC | 00 |  | 0 |  | 77 | 2026-05-18 | IFC | 00
185 | 410-DE-SF-DRW-0071 | Fire Alarm System Layout and Block Diagram | Safety | FA | 2026-02-20 | 2026-02-27 |  | 19 | 0.4811% | 0% |  | 1404/12/1 | 1404/12/8 | [7 empty] | 0
186 | 410-DE-SF-MTO-0072 | Fire and Safety and F & G System MTO | Safety | FI | 2026-02-25 | 2026-03-06 |  | 19 | 0.4811% | 0% |  | 1404/12/6 | 1404/12/15 | [7 empty] | 0
187 | 410-BE-SF-DSH-0166 | Fire Alarm System Datasheet | Safety | FA | 2026-01-31 | 2026-02-09 |  | 5 | 0.1266% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
188 | 410-DE-SF-MRE-0181 | Material Requisition for Fire Alarm System | Safety | FA | 2026-07-13 | 2026-07-22 |  | 30 | 0.7597% | 0% |  | 1405/4/22 | 1405/4/31 | [7 empty] | 0
189 | 410-DE-SF-MRE-0182 | Material Requisition for Fire Fighting Equipment Arrangement | Safety | FA | 2026-06-30 | 2026-07-09 |  | 15 | 0.3798% | 0% |  | 1405/4/9 | 1405/4/18 | [7 empty] | 0
190 | 410-DE-SF-REP-0201 | HSE Plan | Safety | FA |  |  | CM | 15 | 0.3798% | 60% |  |  |  | NT | 7 | 59 | 2026-04-25 | IFC | 00 |  | 2026-05-11 | CM | 59 | 2026-04-25 | IFC | 00 |  | 2026-05-11 | CM
Project Management | [7 empty] | 108 | 2.735% | 62.04%
191 | 410-DE-PM-LST-0084 | Master Document List | Project Management | FA | 2026-01-14 | 2026-01-23 | AP | 14 | 0.3545% | 100% |  | 1404/10/24 | 1404/11/3 |  |  | 44 | 2026-05-04 | IFA | 06 | نامه 0034 | 2026-05-05 | AP | نامه 0006 | 2026-02-07 | IFC | 00 | - | 2026-02-14 | CM | [13 empty] | 8 | 2026-02-25 | IFA | 2 |  | 2026-02-15 | CM |  | 9 | 2026-02-25 | IFA | 3 |  |  |  |  | 13 | 2026-03-15 | IFA | 4 |  |  |  | 19 | 2026-04-11 | IFA | 5 | پیرو جلسه 1405/02/09نامه کارفرما ارسال می شود | 2026-04-29 | AP | 44 | 2026-05-04 | IFA | 06 | نامه 0034 | 2026-05-05 | AP
192 | 410-DE-PM-REP-0085 | Time Schedule | Project Management | FA | 2026-01-24 | 2026-02-02 | AP | 23 | 0.5824% | 100% |  | 1404/11/4 | 1404/11/13 |  |  | 20 | 2026-04-22 | IFA | 2 | 410-05-PK-NT-C-0055 | 2026-04-26 | AP | - | 2026-02-01 | IFC | 00 | جلسه MC |  | CM |  |  |  | 11 | 2026-03-11 | IFA | 1 | نامه کارفرما | 2026-03-31 | CM |  |  |  | 20 | 2026-04-22 | IFA | 2 | 410-05-PK-NT-C-0055 | 2026-04-26 | AP
193 | 410-DE-PM-CAF-0086 | Cash Flow | Project Management | FA | 2026-04-09 | 2026-04-28 | CM | 15 | 0.3798% | 60% |  | 1405/1/20 | 1405/2/8 | NT | 41 | 14 | 2026-03-20 | IFA | 1 | جلسه کارفرما | 2026-04-07 | CM | نامه 0015 | 2026-02-17 | IFC | 00 | جلسه کارفرما | 2026-02-23 | CM |  |  |  | 14 | 2026-03-20 | IFA | 1 | جلسه کارفرما | 2026-04-07 | CM
194 | 410-DE-PM-REP-0138 | Monthly Report 410-M-001 | Project Management | FI | 2026-02-19 | 2026-02-23 | AP | 7 | 0.1773% | 100% |  | 1404/11/30 | 1404/12/4 |  |  | 7 | 2026-02-24 | IFI | 00 | جلسه 1405/02/09 | 2026-04-29 | AP | 7 | 2026-02-24 | IFI | 00 | جلسه 1405/02/09 | 2026-04-29 | AP
195 | 410-DE-PM-REP-0139 | Monthly Report 410-M-002 | Project Management | FI | 2026-03-19 | 2026-03-28 | AP | 7 | 0.1773% | 100% |  | 1404/12/28 | 1405/1/8 |  |  | - | 2026-03-20 | IFI | 00 | جلسه 1405/02/09 | 2026-04-29 | AP | - | 2026-03-20 | IFI | 00 | جلسه 1405/02/09 | 2026-04-29 | AP
196 | 410-DE-PM-REP-0140 | Monthly Report 410-M-003 | Project Management | FI | 2026-04-21 | 2026-04-25 | AP | 7 | 0.1773% | 100% |  | 1405/2/1 | 1405/2/5 |  |  | 28 | 2026-04-23 | IFI | 00 | 140-05-PK-NT-C-0097 | 2026-05-05 | AP | 28 | 2026-04-23 | IFI | 00 | 140-05-PK-NT-C-0097 | 2026-05-05 | AP
197 | 410-DE-PM-REP-0141 | Monthly Report 410-M-004 | Project Management | FI | 2026-05-22 | 2026-05-26 |  | 7 | 0.1773% | 0% |  | 1405/3/1 | 1405/3/5 | [7 empty] | 0
198 | 410-DE-PM-REP-0142 | Monthly Report 410-M-005 | Project Management | FI | 2026-06-22 | 2026-06-26 |  | 7 | 0.1773% | 0% |  | 1405/4/1 | 1405/4/5 | [7 empty] | 0
199 | 410-DE-PM-REP-0143 | Monthly Report 410-M-006 | Project Management | FI | 2026-07-23 | 2026-07-27 |  | 7 | 0.1773% | 0% |  | 1405/5/1 | 1405/5/5 | [7 empty] | 0
200 | 410-DE-PM-REP-0144 | Monthly Report 410-M-007 | Project Management | FI | 2026-08-23 | 2026-08-27 |  | 7 | 0.1773% | 0% |  | 1405/6/1 | 1405/6/5 | [7 empty] | 0
201 | 410-DE-PM-REP-0145 | Monthly Report 410-M-008 | Project Management | FI | 2026-09-07 | 2026-09-11 |  | 7 | 0.1773% | 0% |  | 1405/6/16 | 1405/6/20 | [7 empty] | 0
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
06
Note on AS209: ارسال اولیه 2026/04/15