## کاور
احداث نیروگاه خورشیدی 20مگاواتی زارچ یزد شماره قرارداد: PKSP-P2-C2-0410
صورت وضعیت عملیات مهندسی
شماره صورت وضعیت : |  |  | 410-05-NT-PK-INVOICE(E)-0001
کارکرد تجمعی منتهی به : |  |  | اردیبهشت ماه 1405
احداث نیروگاه خورشیدی 20 مگاواتی زارچ یزد
کارفرما : شرکت تجارت پردازش امین
مدیریت پیمان : شرکت پترو کاویان صنعت پارس
پیمانکار : شرکت پیشگامان انرژی نوراتک
تهیه کننده | بررسی کننده | تائید کننده | ویرایش | تاریخ تهیه | تاریخ ارسال
واحد برنامه ریزی و کنترل پروژه | مدیر پروژه | مدیر پروژه | 00 | 1405/02/31 | 1405/03/30

## خلاصه کاربرگ
| پروژه احداث نیروگاه خورشیدی 20 مگاواتی زارچ یزد |  |  | تاریخ : 1405/03/30
شماره : Invoice (E)-0001
| کاربرگ خلاصه صورت وضعيت مهندسی پیمانکار |  |  | پيوست: دارد
اطلاعات قرارداد:
موضوع قرارداد: طراحی ، تامین ، ساخت و نصب احداث نیروگاه خورشیدی 20 مگا واتی زارچ یزد
نام پیمانکار / مشاور: شركت پیشگامان انرژی نوراتک
شماره قرارداد: PKSP-P2-C2-0410 |  | ارزي | ريالي
تاريخ ابلاغ: 1404/10/21 | مبلغ اوليه قرارداد |  | 28160614893 | کداقتصادي:
مدت (ماه) : 8 ماه | مبلغ 25 درصداول |  |  | شناسه ملی: | 14012972718
تاريخ اتمام اوليه : 1405/06/21 | مبلغ 25 درصددوم |  |  | تاريخ ابلاغ 25 درصداول: | ---
تاريخ اتمام کاربراساس آخرين تمديد: ..... | مبلغ الحاقيه |  |  | تاريخ ابلاغ 25 درصددوم: | ---
| جمع کل | 0 | 28160614893 | تاريخ ابلاغ الحاقيه: | ---
صورت وضعيت:
شماره صورت وضعيت: 1 (یک) - عملیات مهندسی |  | نوع صورت وضعيت: |  | دوره صورت وضعيت :
|  | ¢موقت £ قطعی |  | از تاريخ: | 1404/10/21
|  |  |  | لغايت: | 1405/02/31
پيمانکار: | ارزي | ريالي | درصدپيشرفت فيزيکي واقعي: | 25.27%
مبلغ تجمعي کارکرد بر اساس اين صورت وضعيت(A) |  | 10859017467.8449 | درصدپيشرفت مالي واقعي: | 38.56%
مبلغ تجمعي کارکرد بر اساس صورت وضعيت قبلي(B) |  | 0 | تاريخ، مهر و امضاء مجاز:
مبلغ کارکرد بر اساس صورت وضعيت اين دوره(A-B) |  | 10859017467.8449
مدیریت پیمان: | ارزي | ريالي | درصدپيشرفت فيزيکي واقعي:
مبلغ تجمعي کارکرد بر اساس اين صورت وضعيت(A) |  |  | درصدپيشرفت مالي واقعي:
مبلغ تجمعي کارکرد بر اساس صورت وضعيت قبلي(B) |  |  | تاريخ، مهر / امضاء مجاز:
مبلغ کارکرد بر اساس صورت وضعيت اين دوره(A-B)
کارفرما: | ارزي | ريالي | درصدپيشرفت فيزيکي واقعي:
مبلغ تجمعي کارکرد بر اساس اين صورت وضعيت(A) |  |  | درصدپيشرفت مالي واقعي:
مبلغ تجمعي کارکرد بر اساس صورت وضعيت قبلي(B) |  |  | تاريخ، مهر / امضاء مجاز:
مبلغ کارکرد بر اساس صورت وضعيت اين دوره(A-B)
مالی پروژه: | ارزي | ريالي | تاريخ، مهر / امضاء مجاز:
مبلغ تجمعي کارکرد بر اساس اين صورت وضعيت: (A)
مبلغ تجمعي کارکرد بر اساس صورت وضعيت قبلي(B)
کارکرد دوره با احتساب 10% ماليات بر ارزش افزوده (C=(A-B)*0.1 )
کسورات (D)
مبلغ قابل پرداخت E=(C-D)

## برگ مالی
احداث نیروگاه خورشیدی 20مگاواتی زارچ یزد شماره قرارداد: PKSP-P2-C2-0410
برگ مالی کل به تفکیک مبالغ پیمان برای بخش های مختلف کار
شماره صورت وضعیت : |  | 410-05-NT-PK-INVOICE(E)-0001 | کارکرد منتهی به : | اردیبهشت ماه 1405 |  | تاریخ : | 1405/02/31
ردیف | فعالیت | شرح | مبلغ کل قرارداد |  | مبلغ کارکرد دوره قبل | مبلغ کارکرد این دوره | مبلغ کارکرد تجمعی
1 | طراحی و مهندسی | هزینه های بخش طراحی تفصیلی ، مهندسی و تهیه مدارک فنی (مطابق MDR) | 14080307448 |  | 0 | 3824958621.2312 | 3824958621.2312
2 | تجهیز کارگاه | شامل بخش های اداری ، اسکان ، حمل و نقل ، تغذیه (مطابق PMS) | 14908560827 |  | - | - | -
|  | تجهیز دفتر دستگاه نظارت و کارفرما (مطابق جدول ج) | 20000000000 |  | - | - | -
3 | احداث | هزینه های اجرا و نصب تجهیزات الکتریکی و ابزار (مطابق با جدول الف) | 236501799458 |  | 0 | 576715295.2512 | 576715295.2512
|  | هزینه های اجرای بخش سازه و ساختمان و دقیق از جمله پنل ، اینورتر و MV Station (مطابق با جدول ب) | 222085531578 |  | 0 | 6457343551.3625 | 6457343551.3625
|  | هزینه های بازرسی ، راه اندازی ، بهره برداری آزمایشی و آموزش (مطابق PMS) | 12423800689 |  | - | - | -
مبلغ کل قراردادی (مبلغ ریالی) |  |  | 520000000000
جمع کل ناخالص تجمعی (مبلغ ریالی) |  |  |  |  | 10859017467.8449
جمع کل ناخالص تجمعی تا دوره قبل (مبلغ ریالی) |  |  |  |  | 0
جمع کل ناخالص این دوره (مبلغ ریالی) |  |  |  |  | 10859017467.8449

## خلاصه مالی - الف
احداث نیروگاه خورشیدی 20مگاواتی زارچ یزد شماره قرارداد: PKSP-P2-C2-0410
برگ خلاصه مالی جدول "الف" به تفکیک مبالغ پیمان برای بخش های مختلف کار
شماره صورت وضعیت : |  | 410-05-NT-PK-INVOICE(E)-0001 |  | کارکرد منتهی به : | اردیبهشت ماه 1405 |  | تاریخ : | 1405/02/31
ردیف | شرح |  | توضیحات | بهای قراردادی آیتم | درصد پیشرفت | مبلغ کارکرد دوره قبل | مبلغ کارکرد این دوره | مبلغ کارکرد تجمعی
الف-1 | کلیه کابل های فشار ضعیف موردنیاز AC داخل نیروگاه |  | طراحی و مهندسی | 830569500 | 25.15% | 0 | 208863800.7353 | 208863800.7353
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-2 | کلیه کابل های AC فشار متوسط موردنیاز داخل نیروگاه |  | طراحی و مهندسی | 278589948 | 56.25% | 0 | 156706845.75 | 156706845.75
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-3 | کابل DC (مخصوص فتوولتاییک) |  | طراحی و مهندسی | 347680256 | 26.39% | 0 | 91748956.4444 | 91748956.4444
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-4 | کابل شبکه موردنیاز سیستم انتقال دیتا و اسکادای داخلی نیروگاه |  | طراحی و مهندسی | 18572663 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-5 | کلیه متعلقات مربوط به کابل کشی و سیم کشی شامل و نه محدود به سینی کابل ، بست کمربندی و بست مخصوص کابل ، لوله های خرطومی لوله های پلی اتیلن و نوار خطر زرد رنگ و ... |  | طراحی و مهندسی | 217671613 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-6 | کلیه تجهیزات و ملزومات مربوط به سیستم های زمین نیروگاه (ارت اصلی ، ارت تمیز ابزار دقیق و نول ترانسفورماتور) |  | طراحی و مهندسی | 803824865 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-7 | تابلوهای فشار ضعیف و کلیه متعلقات شامل و نه محدود به بدنه ، کلیدهای قدرت ، ادوات حفاظتی و اعلامی ، مدارات کنترل ، مدارات قدرت و ...) منصوبه در پست سوئیچگیر و تابلوهای فشار ضعیف مصرف داخلی نیروگاه |  | طراحی و مهندسی | 111435979 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-8 | تابلوهای فشار متوسط و کلیه متعلقات (شامل و نه محدود به بدنه ، بریکر و سکسیونرهای قدرت و ارت ، ادوات حفاظتی و اندازه گیری ، مدارات کنترل ، مدارات قدرت و ...) منصوبه در پست های کمپکت و پست سوئیچگیر فشار متوسط 20 کیلوولت شامل و نه محدود به ورودی ها ، تک خروجی ، اندازه گیری مطابق با الزامات وزارت نیرو |  | طراحی و مهندسی | 148581306 | 67.5% | 0 | 100292381.55 | 100292381.55
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-9 | کلیه ملزومات و تجهیزات مربوط به ایجاد ارتباط شبکه انتقال دیتا و بستر مخابراتی با پست بالا دست و دیسپاچینگ منطقه تحت عنوان سیستم های رویت پذیری و انتقال تریپ ، ارتباط با مدیریت شبکه شامل و نه محدود به RTU ، رک ، تابلوهای مربوطه ، سوییچ ، منبع تغذیه ، تلفن مخصوص و کلیه تجهیزات مربوط به آن در سمت نیروگاه مطابق با الزامات دستگاه های ذیربط به جز کابل فیبر نوری مربوطه |  | طراحی و مهندسی | 144866773 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-10 | کلیه ملزومات و تجهیزات مربوط به شبکه انتقال دیتا و ارسال فرامین کنترلی (اسکادا) داخلی نیروگاه (شامل و نه محدود به رک ، سوئیچ ، سرور ، منبع تغذیه صفحه نمایش LED واحدهای اندازه گیری پارامترهای الکتریکی و نرم افزار مانیتورینگ جامع کلیه تجهیزات مبدل و واسط موردنیاز ، کابل فیبر نوری به همراه تجهیزات و مبدل ها و اتصالات مربوطه و ...) |  | طراحی و مهندسی | 57946709 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-11 | کلیه تجهیزات مربوط به UPS های موردنیاز (جهت سیستم RTU ، سوئیچگیر 20 کیلوولت ، سیستم کنترل و مانیتورینگ ، اعلام حریق و CCTV و پشتیبان برق اضطراری مصرف داخلی به صورت مجزا) |  | طراحی و مهندسی | 48288924 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-12 | کلیه تجهیزات مربوط به دوربین های مداربسته CCTV به همراه پایه و فونداسیون های مربوطه شامل و نه محدود به دوربین ، تابلو ، رک ، NVR، صفحه نمایش LED ، اتصالات ، سوییچ ها و مبدل های موردنیاز |  | طراحی و مهندسی | 372196171 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-13 | کلیه تجهیزات مربوط به روشنایی محوطه پیرامونی سایت ، سر در ورودی و ساختمان های نیروگاه به همراه پایه و فونداسیون های مربوطه |  | طراحی و مهندسی | 46060205 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-14 | سیستم اعلام حریق موردنیاز همراه با تمامی ادوات مربوطه (شامل و نه محدود به سنسورها ، کابل مخصوص ، واحد کنترل ، هشدار دهنده ها و ...) |  | طراحی و مهندسی | 7429065 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-15 | سیستم اطفاء حریق موردنیاز همراه با تمامی ادوات مربوطه (شامل و نه محدود به انواع کپسول های آتش نشانی و ...) |  | طراحی و مهندسی | 22287196 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-16 | سیستم حفاظت صاعقه سایت |  | طراحی و مهندسی | 74290653 | 25.71% | 0 | 19103310.7714 | 19103310.7714
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
الف-17 | ترانسفورماتور کمکی و دیزل ژنراتور 10KVA قابل حمل و تمامی متعلقات مربوطه شامل اتصالات و ... |  | طراحی و مهندسی | 92863316 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
حقوق و عوارض گمرکی
نصب و اجرا
تست و راه اندازی
جمع کل کارکرد تجمعی ریالی جدول "الف" | [5 empty] | 0 | 576715295.2512 | 576715295.2512

## خلاصه مالی - ب
احداث نیروگاه خورشیدی 20مگاواتی زارچ یزد شماره قرارداد: PKSP-P2-C2-0410
برگ خلاصه مالی جدول "ب" به تفکیک مبالغ پیمان برای بخش های مختلف کار
شماره صورت وضعیت : |  | 410-05-NT-PK-INVOICE(E)-0001 |  | کارکرد منتهی به : | اردیبهشت ماه 1405 |  | تاریخ : | 1405/02/31
ردیف | شرح |  | توضیحات | بهای قراردادی آیتم | درصد پیشرفت | مبلغ کارکرد دوره قبل | مبلغ کارکرد این دوره | مبلغ کارکرد تجمعی
ب-1 | استراکچر نگهدارنده پنل ها و نصب پنل و MV Station به همراه کوبش پایه ها ، پوشش گالوانیزه و کلیه متعلقات موردنیاز شامل پیچ و مهره و واشر و ... |  | طراحی و مهندسی | 7354774639 | 75% | 0 | 5516080979.25 | 5516080979.25
خرید و حمل و بیمه
نصب و اجرا
ب-2 | استراکچر نگهدارنده اینورترها به همراه پایه ها و نصب اینورتر و پوشش گالوانیزه و کلیه متعلقات موردنیاز شامل پیچ و مهره و واشر و ... |  | طراحی و مهندسی | 84691344 | 75% | 0 | 63518508 | 63518508
خرید و حمل و بیمه
نصب و اجرا
ب-3 | دیوار پیرامونی (از نوع فنس) با ارتفاع حداقل 2/5 به همراه قطعات و اتصالات |  | طراحی و مهندسی | 490318309 | 75% | 0 | 367738731.75 | 367738731.75
خرید و حمل و بیمه
نصب و اجرا
ب-4 | تسطیح و زیرسازی و فراهم کردن بستر جهت دیوارکشی پیرامونی |  | طراحی و مهندسی | 44574392 | 60% | 0 | 26744635.2 | 26744635.2
هزینه اجاره ماشین آلات
نصب و اجرا
ب-5 | فونداسیون مربوط به پایه های روشنایی ، دوربین های مداربسته و صاعقه گیر ، پست های کمپکت و ... |  | طراحی و مهندسی | 148581306 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
نصب و اجرا
ب-6 | مواد و مصالح موردنیاز گیت ورودی نیروگاه همراه با ستون های دوطرف |  | طراحی و مهندسی | 37145326 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
نصب و اجرا
ب-7 | مصالح ، تجهیزات و ملزومات عمرانی و ابنیه یک ساختمان دو طبقه ، هر طبقه با مساحت 70 متر مربع به عنوان اتاق مانیتورینگ (طبقه دوم) ، انبار (طبقه اول) دارای بخش های مربوطه (شامل و نه محدود به گودبرداری ، فونداسیون ، ستون ها و سقف ، سفت کاری) |  | طراحی و مهندسی | 436829039 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
نصب و اجرا
ب-8 | مصالح ، تجهیزات و ملزومات عمرانی و ابنیه یک ساختمان یک طبقه ، با مساحت حدود 120 متر مربع به عنوان پست سوئیچگیر دارای بخش های مربوطه (شامل و نه محدود به گودبرداری ، فونداسیون ، ستون ها و سقف ، سفت کاری) |  | طراحی و مهندسی | 374424891 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
نصب و اجرا
ب-9 | مصالح ، تجهیزات و ملزومات تاسیسات برقی و تلفن و اعلام حریق ، تاسیسات مکانیکی (آبگرمکن ، سیستم سرمایش و گرمایش به صورت داکت اسپیلت و یا اسپیلت مجزا برای هر بخش ، قفل و دستگیره و تجهیزات کامل آشپزخانه شامل و نه محدود به کابینت ، هود ، اجاق گاز ، یخچال و ...) ، آب و فاضلاب (لوله کشی های مربوطه ، شیرآلات و...) بطور کامل جهت ساختمان های اشاره شده در بند 6 |  | طراحی و مهندسی | 89148784 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
نصب و اجرا
ب-10 | کلیه تجهیزات و ملزومات اداری و رفاهی موردنیاز برای بخش های مختلف ساختمان های اشاره شده در بند 5 و 6 |  | طراحی و مهندسی | 44574392 | 65% | 0 | 28973354.8 | 28973354.8
خرید و حمل و بیمه
نصب و اجرا
ب-11 | تانک سپتیک (و نه چاه جذبی) و دو مخزن آب 10 هزار لیتری سه لایه ایستاده با زیرسازی مناسب و یک مخزن آب 500 لیتری ، با نصب پمپ مناسب و لوله کشی به O&M ساختمان |  | طراحی و مهندسی | 22287196 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
نصب و اجرا
ب-12 | اجرای ترانشه و کانال عبور کلیه کابل های انتقال توان و انتقال دیتا داخل نیروگاه با لحاظ تمامی موارد مندرج در آیین نامه و ضوابط مربوط همراه با مصالح موردنیاز |  | طراحی و مهندسی | 222871959 | 0% | 0 | 0 | 0
هزینه اجاره ماشین آلات
نصب و اجرا
ب-13 | تسطیح و تحکیم مناسب زمین سایت جهت نصب تجهیزات اصلی نیروگاه و شیب بندی و زهکشی و هدایت آب های سطحی به محل های مربوطه |  | طراحی و مهندسی | 408598591 | 60% | 0 | 245159154.6 | 245159154.6
هزینه اجاره ماشین آلات
نصب و اجرا
ب-14 | احداث پارکینگ مسقف جهت 6 عدد اتومبیل سواری |  | طراحی و مهندسی | 29716261 | 81.25% | 0 | 24144462.0625 | 24144462.0625
خرید و حمل و بیمه
نصب و اجرا
ب-15 | زیرسازی جاده دسترسی نیروگاه به عرض 6 متر به طول حدود 1/5 کیلومتر به همراه تمامی جاده های داخلی با عرض حداقل 6 متر |  | طراحی و مهندسی | 616612419 | 30% | 0 | 184983725.7 | 184983725.7
هزینه اجاره ماشین آلات
نصب و اجرا
ب-16 | یک عدد کانکس نگهبانی با مساحت 12 مترمربع به همراه فونداسیون و تمامی متعلقات |  | طراحی و مهندسی | 52003455 | 0% | 0 | 0 | 0
خرید و حمل و بیمه
نصب و اجرا
جمع کل کارکرد تجمعی ریالی جدول "ب" | [5 empty] | 0 | 6457343551.3625 | 6457343551.3625

## ریز متره
احداث نیروگاه خورشیدی 20مگاواتی زارچ یزد شماره قرارداد: PKSP-P2-C2-0410
صورت ریز متره
شماره صورت وضعیت : |  | 410-05-NT-PK-INVOICE(E)-0001 | کارکرد منتهی به : | اردیبهشت ماه 1405 |  | تاریخ : |  | 1405/02/31
ردیف | شرح خرید |  | مبلغ قراردادی (ریال) | Document No. | WBS Code | ارزش وزنی MDR | پیشرفت دوره قبل | پیشرفت این دوره | پیشرفت تجمعی
درصد پیشرفت فیزیکی بخش مهندسی | [6 empty] | 0% | 25.27% | 25.27%
الف-1 | کلیه کابل های فشار ضعیف موردنیاز AC داخل نیروگاه |  | 49725419080 |  |  |  | 0% | 0%
| طراحی و مهندسی |  | 830569500 |  |  |  |  | 25.15% | 25.15%
| LV Cable Termination List and MTO |  | 170999602.9412 | 410-DE-EL-LST-0031 | 3.4.8 | 0.3545% |  | 0% | 0%
| LV Cable List, Labeling Code and MTO |  | 232070889.7059 | 410-DE-EL-MTO-0032 | 3.4.9 | 0.4811% |  | 90% | 90%
| Material Requisition for AC Cable |  | 427499007.3529 | 410-DE-EL-MRE-0172 | 3.4.42 | 0.8863% |  | 0% | 0%
الف-2 | کلیه کابل های AC فشار متوسط موردنیاز داخل نیروگاه |  | 20047849081 |  |  |  |  | 0%
| طراحی و مهندسی |  | 278589948 |  |  |  |  | 56.25% | 56.25%
| MV Cable List, Labeling Code and MTO |  | 156706845.75 | 410-DE-EL-MTO-0034 | 3.4.11 | 0.4558% |  | 100% | 100%
| MV Cable Termination List and MTO |  | 121883102.25 | 410-DE-EL-LST-0035 | 3.4.12 | 0.3545% |  | 0% | 0%
الف-3 | کابل DC (مخصوص فتوولتاییک) |  | 24996101408 |  |  |  |  | 0%
| طراحی و مهندسی |  | 347680256 |  |  |  |  | 26.39% | 26.39%
| DC Cable List, Labeling Code and MTO |  | 122331941.9259 | 410-DE-EL-MTO-0029 | 3.4.6 | 0.4811% |  | 75% | 75%
| Material Requisition for DC Cable |  | 225348314.0741 | 410-DE-EL-MRE-0173 | 3.4.43 | 0.8863% |  | 0% | 0%
الف-4 | کابل شبکه موردنیاز سیستم انتقال دیتا و اسکادای داخلی نیروگاه |  | 1335329895 |  |  |  |  | 0%
| طراحی و مهندسی |  | 18572663 |  |  |  |  | 0% | 0%
| Telecommunication and Monitoring System MTO |  | 4466843 | 410-DE-TL-MTO-0065 | 3.7.7 | 0.1604% |  | 0% | 0%
| Material Requisition forTelecommunication and Monitoring Cable |  | 7052910 | 410-DE-TL-MRE-0178 | 3.7.8 | 0.2532% |  | 0% | 0%
| Material Requisition forFiber Optics |  | 7052910 | 410-BE-TL-MRE-0179 | 3.7.9 | 0.2532% |  | 0% | 0%
الف-5 | کلیه متعلقات مربوط به کابل کشی و سیم کشی |  | 15623731230 |  |  |  |  | 0%
| طراحی و مهندسی |  | 217671613 |  |  |  |  | 0% | 0%
| Material Requisition for DC Connection (MC4) |  | 217671613 | 410-DE-EL-MRE-0175 | 3.4.45 | 0.8863% |  | 0% | 0%
الف-6 | کلیه تجهیزات و ملزومات مربوط به سیستم های زمین نیروگاه |  | 53805092503 |  |  |  |  | 0%
| طراحی و مهندسی |  | 803824865 |  |  |  |  | 0% | 0%
| Earthing and Lightning Protection MTO |  | 238635506.7969 | 410-DE-EL-MTO-0042 | 3.4.19 | 0.4811% |  | 0% | 0%
| Material Requisition for Earthing and Lightning |  | 565189358.2031 | 410-DE-EL-MRE-0174 | 3.4.44 | 1.14% |  | 0% | 0%
الف-7 | تابلوهای فشار ضعیف و کلیه متعلقات |  | 8011979372 |  |  |  |  | 0%
| طراحی و مهندسی |  | 111435979 |  |  |  |  | 0% | 0%
| MV Switchgear MTO |  | 33082556.2656 | 410-DE-EL-MTO-0049 | 3.4.26 | 0.4811% |  | 0% | 0%
| Material Requisition for MV Switchgear (CT, PT, Relay) |  | 78353422.7344 | 410-DE-EL-MRE-0171 | 3.4.41 | 1.14% |  | 0% | 0%
الف-8 | تابلوهای فشار متوسط و کلیه متعلقات |  | 10682639164 |  |  |  |  | 0%
| طراحی و مهندسی |  | 148581306 |  |  |  |  | 67.5% | 67.5%
| General Single Line Diagram (GSLD) |  | 74290653 | 410-BE-EL-DRW-0020 | 3.2.5 | 0.5318% |  | 75% | 75%
| Protection Single Line Diagram (PSLD) |  | 74290653 | 410-DE-EL-DRW-0043 | 3.4.20 | 0.5318% |  | 60% | 60%
الف-9 | کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و بستر مخابراتی با پست بالادست و دیسپاچینگ منطقه |  | 10415573185 |  |  |  |  | 0%
| طراحی و مهندسی |  | 144866773 |  |  |  |  | 0% | 0%
| Telecommunication and Monitoring System MTO |  | 34841375.7848 | 410-DE-TL-MTO-0065 | 3.7.7 | 0.1604% |  | 0% | 0%
| Material Requisition forTelecommunication and Monitoring Cable |  | 55012698.6076 | 410-DE-TL-MRE-0178 | 3.7.8 | 0.2532% |  | 0% | 0%
| Material Requisition forFiber Optics |  | 55012698.6076 | 410-BE-TL-MRE-0179 | 3.7.9 | 0.2532% |  | 0% | 0%
الف-10 | کلیه ملزومات و تجهیزات مربوط به شبکه انتقال دیتا و ارسال فرامین کنترلی (اسکادا) داخلی نیروگاه |  | 4164955038 |  |  |  |  | 0%
| طراحی و مهندسی |  | 57946709 |  |  |  |  | 0% | 0%
| Telecommunication and Monitoring System MTO |  | 13936550.2658 | 410-DE-TL-MTO-0065 | 3.7.7 | 0.1604% |  | 0% | 0%
| Material Requisition forTelecommunication and Monitoring Cable |  | 22005079.3671 | 410-DE-TL-MRE-0178 | 3.7.8 | 0.2532% |  | 0% | 0%
| Material Requisition forFiber Optics |  | 22005079.3671 | 410-BE-TL-MRE-0179 | 3.7.9 | 0.2532% |  | 0% | 0%
الف-11 | کلیه تجهیزات مربوط به UPS های موردنیاز |  | 3471857728 |  |  |  |  | 0%
| طراحی و مهندسی |  | 48288924 |  |  |  |  | 0% | 0%
| Material Requisition for UPS and Battery |  | 48288924 | 410-DE-EL-MRE-0177 | 3.4.47 | 1.14% |  | 0% | 0%
الف-12 | کلیه تجهیزات مربوط به دوربین های مداربسته CCTV به همراه پایه و فونداسیون های مربوطه |  | 16732401725 |  |  |  |  | 0%
| طراحی و مهندسی |  | 372196171 |  |  |  |  | 0% | 0%
| CCTV System MTO |  | 139573564.125 | 410-DE-TL-MTO-0057 | 3.7.4 | 0.4558% |  | 0% | 0%
| Material Requisition for CCTV and NVR |  | 232622606.875 | 410-DE-TL-MRE-0180 | 3.7.10 | 0.7597% |  | 0% | 0%
الف-13 | کلیه تجهیزات مربوط به روشنایی محوطه پیرامونی سایت ، سر در ورودی و ساختمان های نیروگاه |  | 3334373156 |  |  |  |  | 0%
| طراحی و مهندسی |  | 46060205 |  |  |  |  | 0% | 0%
| Material Requisition for Lighting System |  | 46060205 | 410-DE-EL-MRE-0176 | 3.4.46 | 1.14% |  | 0% | 0%
الف-14 | سیستم اعلام حریق موردنیاز همراه با تمامی ادوات مربوطه |  | 534131958 |  |  |  |  | 0%
| طراحی و مهندسی |  | 7429065 |  |  |  |  | 0% | 0%
| Material Requisition for Fire Alarm System |  | 7429065 | 410-DE-SF-MRE-0181 | 3.6.5 | 0.7597% |  | 0% | 0%
الف-15 | سیستم اطفاء حریق موردنیاز همراه با تمامی ادوات مربوطه |  | 1602395875 |  |  |  |  | 0%
| طراحی و مهندسی |  | 22287196 |  |  |  |  | 0% | 0%
| Fire and Safety and F & G System MTO |  | 8641973.9592 | 410-DE-SF-MTO-0072 | 3.6.4 | 0.4811% |  | 0% | 0%
| Material Requisition for Fire Fighting Equipment Arrangement |  | 13645222.0408 | 410-DE-SF-MRE-0182 | 3.6.6 | 0.3798% |  | 0% | 0%
الف-16 | سیستم حفاظت صاعقه سایت |  | 5341319582 |  |  |  |  | 0%
| طراحی و مهندسی |  | 74290653 |  |  |  |  | 25.71% | 25.71%
| Lightning Foundation Calculation |  | 42451801.7143 | 410-DE-CV-CAL-0132 | 3.3.31 | 0.9116% |  | 0% | 0%
| Lightning Protection Calculation |  | 31838851.2857 | 410-DE-EL-CAL-0040 | 3.4.17 | 0.6837% |  | 60% | 60%
الف-17 | ترانسفورماتور کمکی و دیزل ژنراتور 10 KVA قابل حمل و تمامی متعلقات |  | 6676649478 |  |  |  |  | 0%
| طراحی و مهندسی |  | 92863316 |  |  |  |  | 0% | 0%
| Material Requisition for Auxiliary Transformer |  | 49162932 | 410-DE-EL-MRE-0169 | 3.4.39 | 1.14% |  | 0% | 0%
| Material Requisition for Diesel Generator |  | 43700384 | 410-BE-EL-MRE-0186 | 3.4.48 | 1.013% |  | 0% | 0%
ب-1 | استراکچر نگهدارنده پنل ها و نصب پنل و MV Station |  | 155455357136 |  |  |  |  | 0%
| طراحی و مهندسی |  | 7354774639 |  |  |  |  | 75% | 75%
| Solar Module Structure MTO |  | 7354774639 | 410-DE-CV-MTO-0115 | 3.3.26 | 0.6331% |  | 75% | 75%
ب-2 | استراکچر نگهدارنده اینورترها به همراه پایه ها و نصب اینورتر |  | 1818927176 |  |  |  |  | 0%
| طراحی و مهندسی |  | 84691344 |  |  |  |  | 75% | 75%
| Solar Module, Connector, Inverter and MV station MTO |  | 84691344 | 410-BE-EL-MTO-0025 | 3.4.1 | 0.4558% |  | 75% | 75%
ب-3 | دیوار پیرامونی از نوع فنس |  | 10530631018 |  |  |  |  | 0%
| طراحی و مهندسی |  | 490318309 |  |  |  |  | 75% | 75%
| Fence MTO |  | 490318309 | 410-DE-CV-MTO-0103 | 3.3.14 | 0.6331% |  | 75% | 75%
ب-4 | تسطیح و زیر سازی و فراهم کردن بستر جهت دیوارکشی پیرامونی(فنس کشی) |  | 957330093 |  |  |  |  | 0%
| طراحی و مهندسی |  | 44574392 |  |  |  |  | 60% | 60%
| Material Requisition for Fence |  | 44574392 | 410-DE-CV-MRE-0167 | 3.3.37 | 1.773% |  | 60% | 60%
ب-5 | فونداسیون مربوطه به پایه های روشنایی ، دوربین های مداربسته و صاعقه گیر ، پست های کمپکت و ... |  | 3191100309 |  |  |  |  | 0%
| طراحی و مهندسی |  | 148581306 |  |  |  |  | 0% | 0%
| Lighting System MTO |  | 44110075.2188 | 410-DE-EL-MTO-0061 | 3.4.34 | 0.4811% |  | 0% | 0%
| Material Requisition for Indoor Power and Lighting Distribution Panel |  | 104471230.7812 | 410-DE-EL-MRE-0168 | 3.4.38 | 1.14% |  | 0% | 0%
ب-6 | مواد و مصالح موردنیاز گیت ورودی نیروگاه همراه با ستون های دوطرف |  | 797775077 |  |  |  |  | 0%
| طراحی و مهندسی |  | 37145326 |  |  |  |  | 0% | 0%
| Structure, Entrance Gate and Foundation of Building MTO |  | 37145326 | 410-DE-CV-MTO-0117 | 3.3.28 | 0.6331% |  | 0% | 0%
ب-7 | مصالح ، تجهیزات و ملزومات عمرانی و ابنیه یک ساختمان دو طبقه |  | 9381834907 |  |  |  |  | 0%
| طراحی و مهندسی |  | 436829039 |  |  |  |  | 0% | 0%
| Swichgear Building Foundation & Structure Calculation |  | 145609679.6667 | 410-DE-CV-CAL-0187 | 3.3.7 | 0.2786% |  | 0% | 0%
| Control Building Foundation & Structure Calculation |  | 145609679.6667 | 410-DE-CV-CAL-0188 | 3.3.7 | 0.2786% |  | 0% | 0%
| Guard Building Foundation & Structure Calculation |  | 145609679.6667 | 410-DE-CV-CAL-0189 | 3.3.7 | 0.2786% |  | 0% | 0%
ب-8 | مصالح ، تجهیزات و ملزومات عمرانی و ابنیه یک ساختمان یک طبقه |  | 8041572778 |  |  |  |  | 0%
| طراحی و مهندسی |  | 374424891 |  |  |  |  | 0% | 0%
| Swichgear Building Foundation & Structure Drawing |  | 46803111.375 | 410-DE-CV-DRW-0190 | 3.3.8 | 0.2279% |  | 0% | 0%
| Control Building Foundation & Structure Drawing |  | 46803111.375 | 410-DE-CV-DRW-0191 | 3.3.8 | 0.2279% |  | 0% | 0%
| Guard Building Foundation & Structure Drawing |  | 46803111.375 | 410-DE-CV-DRW-0192 | 3.3.8 | 0.2279% |  | 0% | 0%
| Material Requisition for PCC |  | 234015556.875 | 410-DE-EL-MRE-0170 | 3.4.40 | 1.14% |  | 0% | 0%
ب-9 | مصالح ،تجهیزات و ملزومات تاسیسات برقی و تلفن و اعلام حریق ، تاسیسات مکانیکی و آب و فاضلاب |  | 1914660186 |  |  |  |  | 0%
| طراحی و مهندسی |  | 89148784 |  |  |  |  | 0% | 0%
| HVAC and Piping System MTO |  | 89148784 | 410-DE-ME-MTO-0068 | 3.5.4 | 0.4811% |  | 0% | 0%
ب-10 | کلیه تجهیزات و ملزومات اداری و رفاهی |  | 957330093 |  |  |  |  | 0%
| طراحی و مهندسی |  | 44574392 |  |  |  |  | 65% | 65%
| Swichgear Building Architectural Detail drawing |  | 14858130.6667 | 410-DE-CV-DRW-0193 | 3.3.13 | 0.2532% |  | 75% | 75%
| Control Building Architectural Detail drawing |  | 14858130.6667 | 410-DE-CV-DRW-0194 | 3.3.13 | 0.2532% |  | 60% | 60%
| Guard Building Architectural Detail drawing |  | 14858130.6667 | 410-DE-CV-DRW-0195 | 3.3.13 | 0.2532% |  | 60% | 60%
ب-11 | تانک سپتیک و دو مخزن آب 10 هزار لیتری سه لایه ایستاده با زیرسازی و یک مخزن 500 لیتری |  | 478665046 |  |  |  |  | 0%
| طراحی و مهندسی |  | 22287196 |  |  |  |  | 0% | 0%
| Material Requisition for Septic Tank |  | 11143598 | 410-BE-ME-MRE-0183 | 3.5.6 | 1.013% |  | 0% | 0%
| Material Requisition for Water |  | 11143598 | 410-BE-ME-MRE-0184 | 3.5.7 | 1.013% |  | 0% | 0%
ب-12 | اجرای ترانشه و کانال عبور کلیه کابل های انتقال توان و انتقال دیتا داخل نیروگاه |  | 4786650463 |  |  |  |  | 0%
| طراحی و مهندسی |  | 222871959 |  |  |  |  | 0% | 0%
| Cable Trench Layout |  | 222871959 | 410-DE-EL-DRW-0037 | 3.4.14 | 0.5571% |  | 0% | 0%
ب-13 | تسطیح و تحکیم مناسب زمین سایت جهت نصب تجهیزات اصلی نیروگاه |  | 8775525848 |  |  |  |  | 0%
| طراحی و مهندسی |  | 408598591 |  |  |  |  | 60% | 60%
| Site Grading and Leveling |  | 408598591 | 410-DE-CV-DRW-0104 | 3.3.15 | 0.7344% |  | 60% | 60%
ب-14 | احداث پارکینگ مسقف |  | 638220062 |  |  |  |  | 0%
| طراحی و مهندسی |  | 29716261 |  |  |  |  | 81.25% | 81.25%
| Topography of Field |  | 7429065.25 | 410-DE-CV-REP-0087 | 3.3.1 | 0.709% |  | 100% | 100%
| Geotechnical Test Report |  | 7429065.25 | 410-DE-CV-REP-0088 | 3.3.2 | 0.709% |  | 90% | 90%
| Hydrology Study Report |  | 7429065.25 | 410-DE-CV-REP-0090 | 3.3.4 | 0.709% |  | 60% | 60%
| Logistic Area |  | 7429065.25 | 410-DE-CV-DRW-0092 | 3.3.6 | 0.709% |  | 75% | 75%
ب-15 | زیر سازی جاده دسترسی نیروگاه |  | 13243066280 |  |  |  |  | 0%
| طراحی و مهندسی |  | 616612419 |  |  |  |  | 30% | 30%
| Internal Road Layout & Implementation Detail Drawing |  | 308306209.5 | 410-DE-CV-DRW-0107 | 3.3.18 | 0.7344% |  | 60% | 60%
| Access Road Layout & Implementation Detail Drawing |  | 308306209.5 | 410-DE-CV-DRW-0108 | 3.3.19 | 0.7344% |  | 0% | 0%
ب-16 | یک عدد کانکس نگهبانی با مساحت 12 مترمربع به همراه فونداسیون و تمامی متعلقات |  | 1116885106 |  |  |  |  | 0%
| طراحی و مهندسی |  | 52003455 |  |  |  |  | 0% | 0%
| Landscaping Layout |  | 52003455 | 410-DE-CV-DRW-0101 | 3.3.12 | 0.7344% |  | 0% | 0%
جدول 3 | طراحی و مهندسی (E) |  | 14080307448 |  |  |  |  | 0%
| طراحی و مهندسی |  | 14080307448 |  |  |  |  | 27.17% | 27.17%
| LVAC Auxiliary Panel Single Line Diagram |  | 120688349.5543 | 410-DE-EL-DRW-0051 | 3.4.28 | 0.5318% |  | 0% | 0%
| LV Cable Datasheet |  | 28735321.3224 | 410-BE-EL-DSH-0151 | 3.2.1.6 | 0.1266% |  | 0% | 0%
| LV Cable Technical Specification |  | 28735321.3224 | 410-BE-EL-SPC-0006 | 3.2.2.6 | 0.1266% |  | 0% | 0%
| LVAC Cable Calculation |  | 155170735.1412 | 410-DE-EL-CAL-0030 | 3.4.7 | 0.6837% |  | 100% | 100%
| MV Cable Datasheet |  | 28735321.3224 | 410-BE-EL-DSH-0152 | 3.2.1.7 | 0.1266% |  | 0% | 0%
| MV Cable Technical Specification |  | 28735321.3224 | 410-BE-EL-SPC-0007 | 3.2.2.7 | 0.1266% |  | 0% | 0%
| MV Cable Calculations |  | 155170735.1412 | 410-DE-EL-CAL-0033 | 3.4.10 | 0.6837% |  | 100% | 100%
| DC Cable Datasheet |  | 28735321.3224 | 410-BE-EL-DSH-0150 | 3.2.1.5 | 0.1266% |  | 100% | 100%
| DC Cable Technical Specification |  | 28735321.3224 | 410-BE-EL-SPC-0005 | 3.2.2.5 | 0.1266% |  | 100% | 100%
| DC Cable Calculation |  | 155170735.1412 | 410-DE-EL-CAL-0028 | 3.4.5 | 0.6837% |  | 75% | 75%
| Electrical Cable Route and Section |  | 126435413.8188 | 410-DE-EL-DRW-0036 | 3.4.13 | 0.5571% |  | 0% | 0%
| SCADA System I/O List |  | 80458899.7029 | 410-DE-TL-LST-0063 | 3.7.5 | 0.3545% |  | 0% | 0%
| Monitoring System Datasheet |  | 40229449.8514 | 410-BE-TL-DSH-0158 | 3.2.1.13 | 0.1773% |  | 60% | 60%
| Monitoring System Technical Specification |  | 45976514.1159 | 410-BE-TL-SPC-0010 | 3.2.2.13 | 0.2026% |  | 75% | 75%
| Monitoring System Overall Diagram |  | 114941285.2898 | 410-DE-TL-DRW-0064 | 3.7.6 | 0.5065% |  | 0% | 0%
| Earthing System Layout |  | 126435413.8188 | 410-DE-EL-DRW-0039 | 3.4.16 | 0.5571% |  | 60% | 60%
| DC Connection (MC4) Datasheet |  | 28735321.3224 | 410-BE-EL-DSH-0149 | 3.2.1.4 | 0.1266% |  | 100% | 100%
| DC Connection (MC4) Technical Specification |  | 28735321.3224 | 410-BE-EL-SPC-0004 | 3.2.2.4 | 0.1266% |  | 100% | 100%
| Earthing and Lightning Datasheet |  | 28735321.3224 | 410-BE-EL-DSH-0154 | 3.2.1.9 | 0.1266% |  | 60% | 60%
| Earthing and Lightning Technical Specification |  | 28735321.3224 | 410-BE-EL-SPC-0009 | 3.2.2.9 | 0.1266% |  | 0% | 0%
| Earthing System Calculation |  | 155170735.1412 | 410-DE-EL-CAL-0038 | 3.4.15 | 0.6837% |  | 60% | 60%
| MV Switchgear Logic Diagram |  | 114941285.2898 | 410-DE-EL-DRW-0045 | 3.4.22 | 0.5065% |  | 0% | 0%
| MV Switchgear Schematic Diagram |  | 114941285.2898 | 410-DE-EL-DRW-0128 | 3.4.36 | 0.5065% |  | 0% | 0%
| MV Switchgear Front View Drawing |  | 114941285.2898 | 410-DE-EL-DRW-0129 | 3.4.37 | 0.5065% |  | 0% | 0%
| MV Switchgear (CT, PT, Relay) Datasheet |  | 28735321.3224 | 410-BE-EL-DSH-0153 | 3.2.1.8 | 0.1266% |  | 0% | 0%
| MV Switchgear (CT, PT, Relay) Technical Specification |  | 28735321.3224 | 410-BE-EL-SPC-0008 | 3.2.2.8 | 0.1266% |  | 75% | 75%
| CT and PT Calculations |  | 155170735.1412 | 410-DE-EL-CAL-0044 | 3.4.21 | 0.6837% |  | 0% | 0%
| Solar Panel Cleaning & Maintenance Procedures |  | 86205963.9673 | 410-DE-ME-REP-0062 | 3.5.1 | 0.3798% |  | 60% | 60%
| Lighting Foundation Calculation |  | 206894313.5216 | 410-DE-CV-CAL-0131 | 3.3.30 | 0.9116% |  | 0% | 0%
| Indoor and Outdoor Lighting Calculation |  | 155170735.1412 | 410-DE-EL-CAL-0058 | 3.4.31 | 0.6837% |  | 0% | 0%
| UPS and Battery Datasheet |  | 28735321.3224 | 410-BE-EL-DSH-0156 | 3.2.1.11 | 0.1266% |  | 0% | 0%
| UPS and Battery Technical Specification |  | 28735321.3224 | 410-BE-EL-SPC-0015 | 3.2.2.11 | 0.1266% |  | 0% | 0%
| UPS Calculation |  | 155170735.1412 | 410-DE-EL-CAL-0052 | 3.4.29 | 0.6837% |  | 0% | 0%
| CCTV and NVR Datasheet |  | 40229449.8514 | 410-BE-TL-DSH-0161 | 3.2.1.16 | 0.1773% |  | 0% | 0%
| CCTV and NVR Technical Specification |  | 45976514.1159 | 410-BE-TL-SPC-0014 | 3.2.2.16 | 0.2026% |  | 60% | 60%
| CCTV System Block Diagram |  | 109194221.0253 | 410-DE-TL-DRW-0054 | 3.7.1 | 0.4811% |  | 0% | 0%
| CCTV System Arrangement & Layout |  | 109194221.0253 | 410-DE-TL-DRW-0055 | 3.7.2 | 0.4811% |  | 0% | 0%
| CCTV Pole Detail Drawing, Switchboard, CAFU Details |  | 126435413.8188 | 410-DE-TL-DRW-0056 | 3.7.3 | 0.5571% |  | 0% | 0%
| Lighting and CCTV Pole Calculation |  | 206894313.5216 | 410-DE-CV-CAL-0134 | 3.3.33 | 0.9116% |  | 0% | 0%
| MV Station Datasheet |  | 28735321.3224 | 410-BE-EL-DSH-0148 | 3.2.1.3 | 0.1266% |  | 75% | 75%
| MV Station Technical Specification |  | 28735321.3224 | 410-BE-EL-SPC-0003 | 3.2.2.3 | 0.1266% |  | 100% | 100%
| MV Station Foundation Calculation |  | 206894313.5216 | 410-DE-CV-CAL-0109 | 3.3.20 | 0.9116% |  | 75% | 75%
| Outdoor Lighting Layout and Switchboard |  | 132182478.0833 | 410-DE-EL-DRW-0060 | 3.4.33 | 0.5824% |  | 0% | 0%
| Fire Alarm System Layout and Block Diagram |  | 109194221.0253 | 410-DE-SF-DRW-0071 | 3.6.3 | 0.4811% |  | 0% | 0%
| Fire Alarm System Datasheet |  | 28735321.3224 | 410-BE-SF-DSH-0166 | 3.2.1.21 | 0.1266% |  | 0% | 0%
| Fire Alarm System Technical Specification |  | 45976514.1159 | 410-BE-SF-SPC-0019 | 3.2.2.21 | 0.2026% |  | 45% | 45%
| Fire Fighting Equipment Arrangement of MV Switchgear Buildings |  | 109194221.0253 | 410-DE-SF-DRW-0069 | 3.6.1 | 0.4811% |  | 0% | 0%
| Outdoor Fire Fighting Equipment & Shelter Arrangement |  | 109194221.0253 | 410-DE-SF-DRW-0070 | 3.6.2 | 0.4811% |  | 45% | 45%
| Lightning Foundation Drawing |  | 160917799.4057 | 410-DE-CV-DRW-0133 | 3.3.32 | 0.709% |  | 0% | 0%
| Lightning Protection Layout |  | 120688349.5543 | 410-DE-EL-DRW-0041 | 3.4.18 | 0.5318% |  | 60% | 60%
| AUX Equipment MTO (AUX Transformer, Diesel, UPS, Battery) |  | 109194221.0253 | 410-DE-EL-MTO-0053 | 3.4.30 | 0.4811% |  | 0% | 0%
| Diesel Generator Datasheet |  | 11494128.529 | 410-BE-EL-DSH-0157 | 3.2.1.12 | 0.05065% |  | 0% | 0%
| Diesel Generator Technical Specification |  | 28735321.3224 | 410-BE-EL-SPC-0016 | 3.2.2.12 | 0.1266% |  | 0% | 0%
| Auxiliary Transformer Datasheet |  | 28735321.3224 | 410-BE-EL-DSH-0155 | 3.2.1.10 | 0.1266% |  | 0% | 0%
| Auxiliary Transformer Technical Specification |  | 28735321.3224 | 410-BE-EL-SPC-0013 | 3.2.2.10 | 0.1266% |  | 0% | 0%
| Load List |  | 80458899.7029 | 410-DE-EL-LST-0050 | 3.4.27 | 0.3545% |  | 0% | 0%
| PV Structure Ramming Location Details Drawing (Stacking) |  | 166664863.6702 | 410-DE-CV-DRW-0114 | 3.3.25 | 0.7344% |  | 0% | 0%
| Table UTM Point |  | 166664863.6702 | 410-DE-CV-DRW-0116 | 3.3.27 | 0.7344% |  | 0% | 0%
| Inverter Datasheet |  | 28735321.3224 | 410-BE-EL-DSH-0147 | 3.2.1.2 | 0.1266% |  | 45% | 45%
| Inverter Technical Specification |  | 28735321.3224 | 410-BE-EL-SPC-0002 | 3.2.2.2 | 0.1266% |  | 100% | 100%
| Strings Connection Diagram & Inverter Arrangement (DC Side) |  | 120688349.5543 | 410-DE-EL-DRW-0026 | 3.4.3 | 0.5318% |  | 75% | 75%
| Solar Panel Datasheet |  | 28735321.3224 | 410-BE-EL-DSH-0146 | 3.2.1.1 | 0.1266% |  | 100% | 100%
| Solar Panel Technical Specification |  | 28735321.3224 | 410-BE-EL-SPC-0001 | 3.2.2.1 | 0.1266% |  | 100% | 100%
| PV System Calculation Study (String Size, Optimum Tilt and Pitch) |  | 155170735.1412 | 410-DE-EL-CAL-0022 | 3.4.2 | 0.6837% |  | 0% | 0%
| Module & Table Arrangement (DC Side) |  | 120688349.5543 | 410-DE-EL-DRW-0027 | 3.4.4 | 0.5318% |  | 75% | 75%
| Calculation Report for Structure |  | 206894313.5216 | 410-DE-CV-CAL-0112 | 3.3.23 | 0.9116% |  | 60% | 60%
| Structure Detail Drawings |  | 166664863.6702 | 410-DE-CV-DRW-0113 | 3.3.24 | 0.7344% |  | 60% | 60%
| Outdoor Lighting Pole Drawing |  | 132182478.0833 | 410-DE-EL-DRW-0059 | 3.4.32 | 0.5824% |  | 0% | 0%
| MV Station Foundation Drawings |  | 166664863.6702 | 410-DE-CV-DRW-0110 | 3.3.21 | 0.7344% |  | 75% | 75%
| Auxiliary Transformer Foundation Detail Drawings |  | 166664863.6702 | 410-DE-CV-DRW-0111 | 3.3.22 | 0.7344% |  | 0% | 0%
| Calculation for Fence |  | 160917799.4057 | 410-DE-CV-CAL-0137 | 3.3.36 | 0.709% |  | 75% | 75%
| Power Plant Entrance Gate Drawing |  | 149423670.8767 | 410-DE-CV-DRW-0099 | 3.3.10 | 0.6584% |  | 0% | 0%
| HVAC Datasheet |  | 40229449.8514 | 410-BE-ME-DSH-0162 | 3.2.1.17 | 0.1773% |  | 0% | 0%
| HVAC Technical Specification |  | 45976514.1159 | 410-BE-ME-SPC-0017 | 3.2.2.17 | 0.2026% |  | 0% | 0%
| HVAC Equipment Calculation |  | 114941285.2898 | 410-DE-ME-CAL-0066 | 3.5.2 | 0.5065% |  | 0% | 0%
| HVAC Equipment Layout for Swichgear Building |  | 38313761.7633 | 410-DE-ME-DRW-0198 | 3.5.3 | 0.1688% |  | 0% | 0%
| HVAC Equipment Layout for Control Building |  | 38313761.7633 | 410-DE-ME-DRW-0199 | 3.5.3 | 0.1688% |  | 0% | 0%
| HVAC Equipment Layout for Guard Building |  | 38313761.7633 | 410-DE-ME-DRW-0200 | 3.5.3 | 0.1688% |  | 0% | 0%
| Septic Tank Detail Drawing |  | 160917799.4057 | 410-DE-CV-DRW-0135 | 3.3.34 | 0.709% |  | 0% | 0%
| Water Tank Foundation Detail Drawing |  | 160917799.4057 | 410-DE-CV-DRW-0136 | 3.3.35 | 0.709% |  | 0% | 0%
| Mechanical Drawing (Water Supply and Sewage Systems) |  | 114941285.2898 | 410-DE-ME-DRW-0095 | 3.5.5 | 0.5065% |  | 0% | 0%
| Parking Foundation & Structure Detail Drawing |  | 149423670.8767 | 410-DE-CV-DRW-0098 | 3.3.9 | 0.6584% |  | 0% | 0%
| Parking Architectural Drawing |  | 166664863.6702 | 410-DE-CV-DRW-0100 | 3.3.11 | 0.7344% |  | 0% | 0%
| Flood Managmant For Outsite of Plant & Implementation Detail Drawing |  | 166664863.6702 | 410-DE-CV-DRW-0106 | 3.3.17 | 0.7344% |  | 45% | 45%
| PVSYST Report |  | 103447156.7608 | 410-BE-EL-REP-0023 | 3.2.3 | 0.4558% |  | 75% | 75%
| General Layout |  | 120688349.5543 | 410-BE-EL-DRW-0021 | 3.2.4 | 0.5318% |  | 100% | 100%
| Site Fence Detail Drawing |  | 160917799.4057 | 410-DE-CV-DRW-0091 | 3.3.5 | 0.709% |  | 100% | 100%
| Plant Detailed Report |  | 120688349.5543 | 410-BE-EL-REP-0024 | 3.2.6 | 0.5318% |  | 100% | 100%
| Ramming and Pull-Out Test Report |  | 160917799.4057 | 410-DE-CV-REP-0089 | 3.3.3 | 0.709% |  | 90% | 90%
| Drainage For Insite of Plant & Implementation Detail Drawing |  | 166664863.6702 | 410-DE-CV-DRW-0105 | 3.3.16 | 0.7344% |  | 45% | 45%
| System Drainage Calculation |  | 206894313.5216 | 410-DE-CV-CAL-0130 | 3.3.29 | 0.9116% |  | 45% | 45%
| Trip Table |  | 120688349.5543 | 410-DE-EL-REP-0046 | 3.4.23 | 0.5318% |  | 0% | 0%
| Alarm List |  | 80458899.7029 | 410-DE-EL-LST-0047 | 3.4.24 | 0.3545% |  | 0% | 0%
| Indoor and Outdoor Electrical Plan & Details for Building |  | 120688349.5543 | 410-DE-EL-DRW-0048 | 3.4.25 | 0.5318% |  | 0% | 0%
| Piping Material, Plumbing Fittings, Pumps Datasheet |  | 40229449.8514 | 410-BE-ME-DSH-0163 | 3.2.1.18 | 0.1773% |  | 0% | 0%
| Septic Tank Datasheet |  | 40229449.8514 | 410-BE-ME-DSH-0164 | 3.2.1.19 | 0.1773% |  | 45% | 45%
| Water TankDatasheet |  | 40229449.8514 | 410-BE-ME-DSH-0165 | 3.2.1.20 | 0.1773% |  | 0% | 0%
| Piping Material, Plumbing Fittings, Pumps Technical Specification |  | 45976514.1159 | 410-BE-ME-SPC-0018 | 3.2.2.18 | 0.2026% |  | 0% | 0%
| Septic Tank Technical Specification |  | 22988257.058 | 410-DE-ME-SPC-0096 | 3.2.2.19 | 0.1013% |  | 45% | 45%
| Water Tank Technical Specification |  | 22988257.058 | 410-DE-ME-SPC-0097 | 3.2.2.20 | 0.1013% |  | 0% | 0%
| Special Tools |  | 126435413.8188 | 410-DE-EL-REP-0082 | 3.4.35 | 0.5571% |  | 60% | 60%
| Data Logger Technical Specification |  | 45976514.1159 | 410-BE-TL-SPC-0011 | 3.2.2.14 | 0.2026% |  | 0% | 0%
| Weather Station Technical Specification |  | 45976514.1159 | 410-BE-TL-SPC-0012 | 3.2.2.15 | 0.2026% |  | 60% | 60%
| Data Logger Datasheet |  | 40229449.8514 | 410-BE-TL-DSH-0159 | 3.2.1.14 | 0.1773% |  | 0% | 0%
| Weather Station Datasheet |  | 17241192.7935 | 410-BE-TL-DSH-0160 | 3.2.1.15 | 0.07597% |  | 0% | 0%
| Material Requisition for Weather Station |  | 172411927.9347 | 410-BE-TL-MRE-0185 | 3.7.11 | 0.7597% |  | 60% | 60%
| Master Document List |  | 80458899.7029 | 410-DE-PM-LST-0084 | 3.1.1 | 0.3545% |  | 100% | 100%
| Time Schedule |  | 132182478.0833 | 410-DE-PM-REP-0085 | 3.1.2 | 0.5824% |  | 100% | 100%
| Cash Flow |  | 86205963.9673 | 410-DE-PM-CAF-0086 | 3.1.3 | 0.3798% |  | 60% | 60%
| Monthly Report 410-M-001 |  | 40229449.8514 | 410-DE-PM-REP-0138 | 3.1.4 | 0.1773% |  | 100% | 100%
| Monthly Report 410-M-002 |  | 40229449.8514 | 410-DE-PM-REP-0139 | 3.1.5 | 0.1773% |  | 100% | 100%
| Monthly Report 410-M-003 |  | 40229449.8514 | 410-DE-PM-REP-0140 | 3.1.6 | 0.1773% |  | 100% | 100%
| Monthly Report 410-M-004 |  | 40229449.8514 | 410-DE-PM-REP-0141 | 3.1.7 | 0.1773% |  | 0% | 0%
| Monthly Report 410-M-005 |  | 40229449.8514 | 410-DE-PM-REP-0142 | 3.1.8 | 0.1773% |  | 0% | 0%
| Monthly Report 410-M-006 |  | 40229449.8514 | 410-DE-PM-REP-0143 | 3.1.9 | 0.1773% |  | 0% | 0%
| Monthly Report 410-M-007 |  | 40229449.8514 | 410-DE-PM-REP-0144 | 3.1.10 | 0.1773% |  | 0% | 0%
| Monthly Report 410-M-008 |  | 40229449.8514 | 410-DE-PM-REP-0145 | 3.1.11 | 0.1773% |  | 0% | 0%
| Solar Panel Installation Manual & Operation & Maintenance |  | 166664863.6702 | 410-DE-QA-REP-0073 | 3.8.1 | 0.7344% |  | 0% | 0%
| UPS Installation Manual & Operation & Maintenance |  | 166664863.6702 | 410-DE-QA-REP-0076 | 3.8.4 | 0.7344% |  | 0% | 0%
| AUX Transformer Installation Manual & Operation & Maintenance |  | 166664863.6702 | 410-DE-QA-REP-0077 | 3.8.5 | 0.7344% |  | 0% | 0%
| Diesel Generator Installation Manual & Operation & Maintenance |  | 166664863.6702 | 410-DE-QA-REP-0078 | 3.8.6 | 0.7344% |  | 0% | 0%
| Weather Station Installation Manual & Operation & Maintenance |  | 166664863.6702 | 410-DE-QA-REP-0079 | 3.8.7 | 0.7344% |  | 0% | 0%
| Solar Structure Installation Manual & Operation & Maintenance |  | 166664863.6702 | 410-DE-QA-REP-0080 | 3.8.8 | 0.7344% |  | 0% | 0%
| SCADA and Monitoring System Installation Manual & Operation & Maintenance |  | 166664863.6702 | 410-DE-QA-REP-0081 | 3.8.9 | 0.7344% |  | 0% | 0%
| Test Report of Solar Structure |  | 166664863.6702 | 410-DE-QA-REP-0118 | 3.8.11 | 0.7344% |  | 90% | 90%
| Test Reports for AC Cables |  | 83332431.8351 | 410-DE-QA-REP-0196 | 3.8.15 | 0.3672% |  | 0% | 0%
| Test Reports for DC Cables |  | 83332431.8351 | 410-DE-QA-REP-0197 | 3.8.15 | 0.3672% |  | 0% | 0%
| HSE Plan |  | 86205963.9673 | 410-DE-SF-REP-0201 | 3.6.6 | 0.3798% |  | 60% | 60%
| Inverter Installation Manual & Operation & Maintenance |  | 166664863.6702 | 410-DE-QA-REP-0074 | 3.8.2 | 0.7344% |  | 0% | 0%
| MV Station Installation Manual & Operation & Maintenance |  | 166664863.6702 | 410-DE-QA-REP-0075 | 3.8.3 | 0.7344% |  | 90% | 90%
| Project O&M General Instructions |  | 166664863.6702 | 410-DE-QA-REP-0083 | 3.8.10 | 0.7344% |  | 0% | 0%
| Test Reports for PV Modules |  | 166664863.6702 | 410-DE-QA-REP-0119 | 3.8.12 | 0.7344% |  | 0% | 0%
| Test Reports for Inverter |  | 166664863.6702 | 410-DE-QA-REP-0120 | 3.8.13 | 0.7344% |  | 0% | 0%
| Test Reports for MV Station |  | 166664863.6702 | 410-DE-QA-REP-0121 | 3.8.14 | 0.7344% |  | 0% | 0%
| Test Reports for Diesel Generators |  | 166664863.6702 | 410-DE-QA-REP-0123 | 3.8.16 | 0.7344% |  | 0% | 0%
| Test Reports for AUX Transformer |  | 166664863.6702 | 410-DE-QA-REP-0124 | 3.8.17 | 0.7344% |  | 0% | 0%
| Test Reports for Earthing and Ligthtning |  | 166664863.6702 | 410-DE-QA-REP-0125 | 3.8.18 | 0.7344% |  | 0% | 0%
| Test Reports for MV Switchgear (CT, PT, Relay, …) |  | 166664863.6702 | 410-DE-QA-REP-0126 | 3.8.19 | 0.7344% |  | 0% | 0%
| Test Reports for UPS and Battery |  | 166664863.6702 | 410-DE-QA-REP-0127 | 3.8.20 | 0.7344% |  | 0% | 0%

## MDR0 (hidden)
Master Document List
Row | Document No. | Document Name | Discipline | %MDR
| Engineering |  |  | 25.27%
Electrical |  |  |  | 26.01%
1 | 410-BE-EL-SPC-0001 | Solar Panel Technical Specification | Electrical | 100%
2 | 410-BE-EL-SPC-0002 | Inverter Technical Specification | Electrical | 100%
3 | 410-BE-EL-SPC-0003 | MV Station Technical Specification | Electrical | 100%
4 | 410-BE-EL-SPC-0004 | DC Connection (MC4) Technical Specification | Electrical | 100%
5 | 410-BE-EL-SPC-0005 | DC Cable Technical Specification | Electrical | 100%
6 | 410-BE-EL-SPC-0006 | LV Cable Technical Specification | Electrical | 0%
7 | 410-BE-EL-SPC-0007 | MV Cable Technical Specification | Electrical | 0%
8 | 410-BE-EL-SPC-0008 | MV Switchgear (CT, PT, Relay) Technical Specification | Electrical | 75%
9 | 410-BE-EL-SPC-0009 | Earthing and Lightning Technical Specification | Electrical | 0%
10 | 410-BE-EL-SPC-0013 | Auxiliary Transformer Technical Specification | Electrical | 0%
11 | 410-BE-EL-SPC-0015 | UPS and Battery Technical Specification | Electrical | 0%
12 | 410-BE-EL-SPC-0016 | Diesel Generator Technical Specification | Electrical | 0%
13 | 410-BE-EL-DRW-0020 | General Single Line Diagram (GSLD) | Electrical | 75%
14 | 410-BE-EL-DRW-0021 | General Layout | Electrical | 100%
15 | 410-DE-EL-CAL-0022 | PV System Calculation Study (String Size, Optimum Tilt and Pitch) | Electrical | 0%
16 | 410-BE-EL-REP-0023 | PVSYST Report | Electrical | 75%
17 | 410-BE-EL-REP-0024 | Plant Detailed Report | Electrical | 100%
18 | 410-BE-EL-MTO-0025 | Solar Module, Connector, Inverter and MV station MTO | Electrical | 75%
19 | 410-DE-EL-DRW-0026 | Strings Connection Diagram & Inverter Arrangement (DC Side) | Electrical | 75%
20 | 410-DE-EL-DRW-0027 | Module & Table Arrangement (DC Side) | Electrical | 75%
21 | 410-DE-EL-CAL-0028 | DC Cable Calculation | Electrical | 75%
22 | 410-DE-EL-MTO-0029 | DC Cable List, Labeling Code and MTO | Electrical | 75%
23 | 410-DE-EL-CAL-0030 | LVAC Cable Calculation | Electrical | 100%
24 | 410-DE-EL-LST-0031 | LV Cable Termination List and MTO | Electrical | 0%
25 | 410-DE-EL-MTO-0032 | LV Cable List, Labeling Code and MTO | Electrical | 90%
26 | 410-DE-EL-CAL-0033 | MV Cable Calculations | Electrical | 100%
27 | 410-DE-EL-MTO-0034 | MV Cable List, Labeling Code and MTO | Electrical | 100%
28 | 410-DE-EL-LST-0035 | MV Cable Termination List and MTO | Electrical | 0%
29 | 410-DE-EL-DRW-0036 | Electrical Cable Route and Section | Electrical | 0%
30 | 410-DE-EL-DRW-0037 | Cable Trench Layout | Electrical | 0%
31 | 410-DE-EL-CAL-0038 | Earthing System Calculation | Electrical | 60%
32 | 410-DE-EL-DRW-0039 | Earthing System Layout | Electrical | 60%
33 | 410-DE-EL-CAL-0040 | Lightning Protection Calculation | Electrical | 60%
34 | 410-DE-EL-DRW-0041 | Lightning Protection Layout | Electrical | 60%
35 | 410-DE-EL-MTO-0042 | Earthing and Lightning Protection MTO | Electrical | 0%
36 | 410-DE-EL-DRW-0043 | Protection Single Line Diagram (PSLD) | Electrical | 60%
37 | 410-DE-EL-CAL-0044 | CT and PT Calculations | Electrical | 0%
38 | 410-DE-EL-DRW-0045 | MV Switchgear Logic Diagram | Electrical | 0%
39 | 410-DE-EL-REP-0046 | Trip Table | Electrical | 0%
40 | 410-DE-EL-LST-0047 | Alarm List | Electrical | 0%
41 | 410-DE-EL-DRW-0048 | Indoor and Outdoor Electrical Plan & Details for Building | Electrical | 0%
42 | 410-DE-EL-MTO-0049 | MV Switchgear MTO | Electrical | 0%
43 | 410-DE-EL-LST-0050 | Load List | Electrical | 0%
44 | 410-DE-EL-DRW-0051 | LVAC Auxiliary Panel Single Line Diagram | Electrical | 0%
45 | 410-DE-EL-CAL-0052 | UPS Calculation | Electrical | 0%
46 | 410-DE-EL-MTO-0053 | AUX Equipment MTO (AUX Transformer, Diesel, UPS, Battery) | Electrical | 0%
47 | 410-DE-EL-CAL-0058 | Indoor and Outdoor Lighting Calculation | Electrical | 0%
48 | 410-DE-EL-DRW-0059 | Outdoor Lighting Pole Drawing | Electrical | 0%
49 | 410-DE-EL-DRW-0060 | Outdoor Lighting Layout and Switchboard | Electrical | 0%
50 | 410-DE-EL-MTO-0061 | Lighting System MTO | Electrical | 0%
51 | 410-DE-EL-REP-0082 | Special Tools | Electrical | 60%
52 | 410-DE-EL-DRW-0128 | MV Switchgear Schematic Diagram | Electrical | 0%
53 | 410-DE-EL-DRW-0129 | MV Switchgear Front View Drawing | Electrical | 0%
54 | 410-BE-EL-DSH-0146 | Solar Panel Datasheet | Electrical | 100%
55 | 410-BE-EL-DSH-0147 | Inverter Datasheet | Electrical | 45%
56 | 410-BE-EL-DSH-0148 | MV Station Datasheet | Electrical | 75%
57 | 410-BE-EL-DSH-0149 | DC Connection (MC4) Datasheet | Electrical | 100%
58 | 410-BE-EL-DSH-0150 | DC Cable Datasheet | Electrical | 100%
59 | 410-BE-EL-DSH-0151 | LV Cable Datasheet | Electrical | 0%
60 | 410-BE-EL-DSH-0152 | MV Cable Datasheet | Electrical | 0%
61 | 410-BE-EL-DSH-0153 | MV Switchgear (CT, PT, Relay) Datasheet | Electrical | 0%
62 | 410-BE-EL-DSH-0154 | Earthing and Lightning Datasheet | Electrical | 60%
63 | 410-BE-EL-DSH-0155 | Auxiliary Transformer Datasheet | Electrical | 0%
64 | 410-BE-EL-DSH-0156 | UPS and Battery Datasheet | Electrical | 0%
65 | 410-BE-EL-DSH-0157 | Diesel Generator Datasheet | Electrical | 0%
66 | 410-DE-EL-MRE-0168 | Material Requisition for Indoor Power and Lighting Distribution Panel | Electrical | 0%
67 | 410-DE-EL-MRE-0169 | Material Requisition for Auxiliary Transformer | Electrical | 0%
68 | 410-DE-EL-MRE-0170 | Material Requisition for PCC | Electrical | 0%
69 | 410-DE-EL-MRE-0171 | Material Requisition for MV Switchgear (CT, PT, Relay) | Electrical | 0%
70 | 410-DE-EL-MRE-0172 | Material Requisition for AC Cable | Electrical | 0%
71 | 410-DE-EL-MRE-0173 | Material Requisition for DC Cable | Electrical | 0%
72 | 410-DE-EL-MRE-0174 | Material Requisition for Earthing and Lightning | Electrical | 0%
73 | 410-DE-EL-MRE-0175 | Material Requisition for DC Connection (MC4) | Electrical | 0%
74 | 410-DE-EL-MRE-0176 | Material Requisition for Lighting System | Electrical | 0%
75 | 410-DE-EL-MRE-0177 | Material Requisition for UPS and Battery | Electrical | 0%
76 | 410-BE-EL-MRE-0186 | Material Requisition for Diesel Generator | Electrical | 0%
Civil |  |  |  | 37.94%
77 | 410-DE-CV-REP-0087 | Topography of Field | Civil | 100%
78 | 410-DE-CV-REP-0088 | Geotechnical Test Report | Civil | 90%
79 | 410-DE-CV-REP-0089 | Ramming and Pull-Out Test Report | Civil | 90%
80 | 410-DE-CV-REP-0090 | Hydrology Study Report | Civil | 60%
81 | 410-DE-CV-DRW-0091 | Site Fence Detail Drawing | Civil | 100%
82 | 410-DE-CV-DRW-0092 | Logistic Area | Civil | 75%
83 | 410-DE-CV-CAL-0093 | Buildings Foundation & Structure Calculation | Civil | 0%
84 | 410-DE-CV-CAL-0187 | Swichgear Building Foundation & Structure Calculation | Civil | 0%
85 | 410-DE-CV-CAL-0188 | Control Building Foundation & Structure Calculation | Civil | 0%
86 | 410-DE-CV-CAL-0189 | Guard Building Foundation & Structure Calculation | Civil | 0%
87 | 410-DE-CV-DRW-0094 | Buildings Foundation & Structure Drawing | Civil | 0%
88 | 410-DE-CV-DRW-0190 | Swichgear Building Foundation & Structure Drawing | Civil | 0%
89 | 410-DE-CV-DRW-0191 | Control Building Foundation & Structure Drawing | Civil | 0%
90 | 410-DE-CV-DRW-0192 | Guard Building Foundation & Structure Drawing | Civil | 0%
91 | 410-DE-CV-DRW-0098 | Parking Foundation & Structure Detail Drawing | Civil | 0%
92 | 410-DE-CV-DRW-0099 | Power Plant Entrance Gate Drawing | Civil | 0%
93 | 410-DE-CV-DRW-0100 | Parking Architectural Drawing | Civil | 0%
94 | 410-DE-CV-DRW-0101 | Landscaping Layout | Civil | 0%
95 | 410-DE-CV-DRW-0102 | Buildings Architectural Detail drawing | Civil | 65%
96 | 410-DE-CV-DRW-0193 | Swichgear Building Architectural Detail drawing | Civil | 75%
97 | 410-DE-CV-DRW-0194 | Control Building Architectural Detail drawing | Civil | 60%
98 | 410-DE-CV-DRW-0195 | Guard Building Architectural Detail drawing | Civil | 60%
99 | 410-DE-CV-MTO-0103 | Fence MTO | Civil | 75%
100 | 410-DE-CV-DRW-0104 | Site Grading and Leveling | Civil | 60%
101 | 410-DE-CV-DRW-0105 | Drainage For Insite of Plant & Implementation Detail Drawing | Civil | 45%
102 | 410-DE-CV-DRW-0106 | Flood Managmant For Outsite of Plant & Implementation Detail Drawing | Civil | 45%
103 | 410-DE-CV-DRW-0107 | Internal Road Layout & Implementation Detail Drawing | Civil | 60%
104 | 410-DE-CV-DRW-0108 | Access Road Layout & Implementation Detail Drawing | Civil | 0%
105 | 410-DE-CV-CAL-0109 | MV Station Foundation Calculation | Civil | 75%
106 | 410-DE-CV-DRW-0110 | MV Station Foundation Drawings | Civil | 75%
107 | 410-DE-CV-DRW-0111 | Auxiliary Transformer Foundation Detail Drawings | Civil | 0%
108 | 410-DE-CV-CAL-0112 | Calculation Report for Structure | Civil | 60%
109 | 410-DE-CV-DRW-0113 | Structure Detail Drawings | Civil | 60%
110 | 410-DE-CV-DRW-0114 | PV Structure Ramming Location Details Drawing (Stacking) | Civil | 0%
111 | 410-DE-CV-MTO-0115 | Solar Module Structure MTO | Civil | 75%
112 | 410-DE-CV-DRW-0116 | Table UTM Point | Civil | 0%
113 | 410-DE-CV-MTO-0117 | Structure, Entrance Gate and Foundation of Building MTO | Civil | 0%
114 | 410-DE-CV-CAL-0130 | System Drainage Calculation | Civil | 45%
115 | 410-DE-CV-CAL-0131 | Lighting Foundation Calculation | Civil | 0%
116 | 410-DE-CV-CAL-0132 | Lightning Foundation Calculation | Civil | 0%
117 | 410-DE-CV-DRW-0133 | Lightning Foundation Drawing | Civil | 0%
118 | 410-DE-CV-CAL-0134 | Lighting and CCTV Pole Calculation | Civil | 0%
119 | 410-DE-CV-DRW-0135 | Septic Tank Detail Drawing | Civil | 0%
120 | 410-DE-CV-DRW-0136 | Water Tank Foundation Detail Drawing | Civil | 0%
121 | 410-DE-CV-CAL-0137 | Calculation for Fence | Civil | 75%
122 | 410-DE-CV-MRE-0167 | Material Requisition for Fence | Civil | 60%
Quality |  |  |  | 9%
123 | 410-DE-QA-REP-0073 | Solar Panel Installation Manual & Operation & Maintenance | Quality | 0%
124 | 410-DE-QA-REP-0074 | Inverter Installation Manual & Operation & Maintenance | Quality | 0%
125 | 410-DE-QA-REP-0075 | MV Station Installation Manual & Operation & Maintenance | Quality | 90%
126 | 410-DE-QA-REP-0076 | UPS Installation Manual & Operation & Maintenance | Quality | 0%
127 | 410-DE-QA-REP-0077 | AUX Transformer Installation Manual & Operation & Maintenance | Quality | 0%
128 | 410-DE-QA-REP-0078 | Diesel Generator Installation Manual & Operation & Maintenance | Quality | 0%
129 | 410-DE-QA-REP-0079 | Weather Station Installation Manual & Operation & Maintenance | Quality | 0%
130 | 410-DE-QA-REP-0080 | Solar Structure Installation Manual & Operation & Maintenance | Quality | 0%
131 | 410-DE-QA-REP-0081 | SCADA and Monitoring System Installation Manual & Operation & Maintenance | Quality | 0%
132 | 410-DE-QA-REP-0083 | Project O&M General Instructions | Quality | 0%
133 | 410-DE-QA-REP-0118 | Test Report of Solar Structure | Quality | 90%
134 | 410-DE-QA-REP-0119 | Test Reports for PV Modules | Quality | 0%
135 | 410-DE-QA-REP-0120 | Test Reports for Inverter | Quality | 0%
136 | 410-DE-QA-REP-0121 | Test Reports for MV Sation | Quality | 0%
137 | 410-DE-QA-REP-0122 | Test Reports for AC and DC Cables | Quality | 0%
138 | 410-DE-QA-REP-0196 | Test Reports for AC Cables | Quality | 0%
139 | 410-DE-QA-REP-0197 | Test Reports for DC Cables | Quality | 0%
140 | 410-DE-QA-REP-0123 | Test Reports for Diesel Generators | Quality | 0%
141 | 410-DE-QA-REP-0124 | Test Reports for AUX Transformer | Quality | 0%
142 | 410-DE-QA-REP-0125 | Test Reports for Earthing and Ligthtning | Quality | 0%
143 | 410-DE-QA-REP-0126 | Test Reports for MV Switchgear (CT, PT, Relay, …) | Quality | 0%
144 | 410-DE-QA-REP-0127 | Test Reports for UPS and Battery | Quality | 0%
Telecom |  |  |  | 12.31%
145 | 410-BE-TL-SPC-0010 | Monitoring System Technical Specification | Telecom | 75%
146 | 410-BE-TL-SPC-0011 | Data Logger Technical Specification | Telecom | 0%
147 | 410-BE-TL-SPC-0012 | Weather Station Technical Specification | Telecom | 60%
148 | 410-BE-TL-SPC-0014 | CCTV and NVR Technical Specification | Telecom | 60%
149 | 410-DE-TL-DRW-0054 | CCTV System Block Diagram | Telecom | 0%
150 | 410-DE-TL-DRW-0055 | CCTV System Arrangement & Layout | Telecom | 0%
151 | 410-DE-TL-DRW-0056 | CCTV Pole Detail Drawing, Switchboard, CAFU Details | Telecom | 0%
152 | 410-DE-TL-MTO-0057 | CCTV System MTO | Telecom | 0%
153 | 410-DE-TL-LST-0063 | SCADA System I/O List | Telecom | 0%
154 | 410-DE-TL-DRW-0064 | Monitoring System Overall Diagram | Telecom | 0%
155 | 410-DE-TL-MTO-0065 | Telecommunication and Monitoring System MTO | Telecom | 0%
156 | 410-BE-TL-DSH-0158 | Monitoring System Datasheet | Telecom | 60%
157 | 410-BE-TL-DSH-0159 | Data Logger Datasheet | Telecom | 0%
158 | 410-BE-TL-DSH-0160 | Weather Station Datasheet | Telecom | 0%
159 | 410-BE-TL-DSH-0161 | CCTV and NVR Datasheet | Telecom | 0%
160 | 410-DE-TL-MRE-0178 | Material Requisition forTelecommunication and Monitoring Cable | Telecom | 0%
161 | 410-BE-TL-MRE-0179 | Material Requisition forFiber Optics | Telecom | 0%
162 | 410-DE-TL-MRE-0180 | Material Requisition for CCTV and NVR | Telecom | 0%
163 | 410-BE-TL-MRE-0185 | Material Requisition for Weather Station | Telecom | 60%
Mechanical |  |  |  | 6.173%
164 | 410-BE-ME-SPC-0017 | HVAC Technical Specification | Mechanical | 0%
165 | 410-BE-ME-SPC-0018 | Piping Material, Plumbing Fittings, Pumps Technical Specification | Mechanical | 0%
166 | 410-DE-ME-REP-0062 | Solar Panel Cleaning & Maintenance Procedures | Mechanical | 60%
167 | 410-DE-ME-CAL-0066 | HVAC Equipment Calculation | Mechanical | 0%
168 | 410-DE-ME-DRW-0067 | HVAC Equipment Layout for Building | Mechanical | 0%
169 | 410-DE-ME-DRW-0198 | HVAC Equipment Layout for Swichgear Building | Mechanical | 0%
170 | 410-DE-ME-DRW-0199 | HVAC Equipment Layout for Control Building | Mechanical | 0%
171 | 410-DE-ME-DRW-0200 | HVAC Equipment Layout for Guard Building | Mechanical | 0%
172 | 410-DE-ME-MTO-0068 | HVAC and Piping System MTO | Mechanical | 0%
173 | 410-DE-ME-DRW-0095 | Mechanical Drawing (Water Supply and Sewage Systems) | Mechanical | 0%
174 | 410-DE-ME-SPC-0096 | Septic Tank Technical Specification | Mechanical | 45%
175 | 410-DE-ME-SPC-0097 | Water Tank Technical Specification | Mechanical | 0%
176 | 410-BE-ME-DSH-0162 | HVAC Datasheet | Mechanical | 0%
177 | 410-BE-ME-DSH-0163 | Piping Material, Plumbing Fittings, Pumps Datasheet | Mechanical | 0%
178 | 410-BE-ME-DSH-0164 | Septic Tank Datasheet | Mechanical | 45%
179 | 410-BE-ME-DSH-0165 | Water Tank Datasheet | Mechanical | 0%
180 | 410-BE-ME-MRE-0183 | Material Requisition for Septic Tank | Mechanical | 0%
181 | 410-BE-ME-MRE-0184 | Material Requisition for Water | Mechanical | 0%
Safety |  |  |  | 14.19%
182 | 410-BE-SF-SPC-0019 | Fire Alarm System Technical Specification | Safety | 45%
183 | 410-DE-SF-DRW-0069 | Fire Fighting Equipment Arrangement of MV Switchgear Buildings | Safety | 0%
184 | 410-DE-SF-DRW-0070 | Outdoor Fire Fighting Equipment & Shelter Arrangement | Safety | 45%
185 | 410-DE-SF-DRW-0071 | Fire Alarm System Layout and Block Diagram | Safety | 0%
186 | 410-DE-SF-MTO-0072 | Fire and Safety and F & G System MTO | Safety | 0%
187 | 410-BE-SF-DSH-0166 | Fire Alarm System Datasheet | Safety | 0%
188 | 410-DE-SF-MRE-0181 | Material Requisition for Fire Alarm System | Safety | 0%
189 | 410-DE-SF-MRE-0182 | Material Requisition for Fire Fighting Equipment Arrangement | Safety | 0%
190 | 410-DE-SF-REP-0201 | HSE Plan | Safety | 60%
Project Management |  |  |  | 62.04%
191 | 410-DE-PM-LST-0084 | Master Document List | Project Management | 100%
192 | 410-DE-PM-REP-0085 | Time Schedule | Project Management | 100%
193 | 410-DE-PM-CAF-0086 | Cash Flow | Project Management | 60%
194 | 410-DE-PM-REP-0138 | Monthly Report 410-M-001 | Project Management | 100%
195 | 410-DE-PM-REP-0139 | Monthly Report 410-M-002 | Project Management | 100%
196 | 410-DE-PM-REP-0140 | Monthly Report 410-M-003 | Project Management | 100%
197 | 410-DE-PM-REP-0141 | Monthly Report 410-M-004 | Project Management | 0%
198 | 410-DE-PM-REP-0142 | Monthly Report 410-M-005 | Project Management | 0%
199 | 410-DE-PM-REP-0143 | Monthly Report 410-M-006 | Project Management | 0%
200 | 410-DE-PM-REP-0144 | Monthly Report 410-M-007 | Project Management | 0%
201 | 410-DE-PM-REP-0145 | Monthly Report 410-M-008 | Project Management | 0%

## MDR(Formulas)
|  | پروژه احداث نیروگاه خورشیدی 20 مگاواتی زارچ یزد شماره قرارداد: PKPS-P2-C2-0410 | [77 empty] | 2026-06-22 |  | RJ
[80 empty] | RJ | IFC | CM
[80 empty] | CM | IFA | AN
DOCUMENT NO. : 410-DE-PM-LST-0084 |  | Document Name : Master Document List | [18 empty] | Discipline | Rev. | [57 empty] | AN | IFI | AP
[21 empty] | PM | 06 | [57 empty] | AP | AFC | IFC
[21 empty] | Page 1 of 1 | [58 empty] | AFC |  | IFA
|  | #REF! | [79 empty] | IFI
No | Document Number | Description | Discipline | Class | Plan Date |  | Status | Man-Hour | W.V | %Complete | تاریخ برنامه ای اولین ارسال | شروع طبق برنامه | پایان طبق برنامه | Hold By | Delay | Last Status | [6 empty] | REV 00 | [9 empty] | REV 01 | [9 empty] | REV 02 | [7 empty] | REV 03 | [7 empty] | REV 04 | [6 empty] | REV 05 | [6 empty] | REV 06
[5 empty] | Start | Finish
Engineering | [7 empty] | 3949 | 100% | 25.27% | [5 empty] | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Reply Date | Conclusion | Answer Date | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Reply Date | Conclusion | Answer Date | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Reply sheet | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Reply sheet | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results | Input Trans No. | Date of Receive | status | Rev | Comment sheet No. | Comment sheet Date | Review Results
Electrical | [7 empty] | 1448 | 36.67% | 26.01%
1 | 410-BE-EL-SPC-0001 | Solar Panel Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 | AP | 5 | 0.1266% | 100% |  | 1404/10/24 | 1404/11/3 |  |  | 50 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AP | 50 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AP
2 | 410-BE-EL-SPC-0002 | Inverter Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 | AP | 5 | 0.1266% | 100% |  | 1404/10/24 | 1404/11/3 |  |  | 51 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | CM | 51 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | CM | 2026-05-11 | AP | 2026-05-12
3 | 410-BE-EL-SPC-0003 | MV Station Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 | AP | 5 | 0.1266% | 100% |  | 1404/10/24 | 1404/11/3 |  |  | 52 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | CM | 52 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | CM | 2026-05-11 | AP | 2026-05-12
4 | 410-BE-EL-SPC-0004 | DC Connection (MC4) Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 | AP | 5 | 0.1266% | 100% |  | 1404/10/24 | 1404/11/3 |  |  | 22 | 2026-04-19 | IFA | 01 | - | 2026-05-02 | CM | 2 | 2026-02-02 | IFC | 00 | - | 2026-02-16 | CM | 2026-04-19 |  |  | 22 | 2026-04-19 | IFA | 01 | - | 2026-05-02 | CM | 2026-05-13 | AP | 2026-05-16
5 | 410-BE-EL-SPC-0005 | DC Cable Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 | AP | 5 | 0.1266% | 100% |  | 1404/10/24 | 1404/11/3 |  |  | 24 | 2026-04-19 | IFA | 01 | - | 2026-05-02 | AP | 2 | 2026-02-02 | IFC | 00 | - | 2026-02-15 | CM | 2026-04-13 |  |  | 24 | 2026-04-19 | IFA | 01 | - | 2026-05-02 | AP
6 | 410-BE-EL-SPC-0006 | LV Cable Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 |  | 5 | 0.1266% | 0% |  | 1404/10/24 | 1404/11/3 | [7 empty] | 0
7 | 410-BE-EL-SPC-0007 | MV Cable Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 |  | 5 | 0.1266% | 0% |  | 1404/10/24 | 1404/11/3 | [7 empty] | 0
8 | 410-BE-EL-SPC-0008 | MV Switchgear (CT, PT, Relay) Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 | AN | 5 | 0.1266% | 75% |  | 1404/10/24 | 1404/11/3 | NT | 48 | 53 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AN | 53 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AN | 2026-05-11
9 | 410-BE-EL-SPC-0009 | Earthing and Lightning Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 |  | 5 | 0.1266% | 0% |  | 1404/10/24 | 1404/11/3 | [7 empty] | 0
10 | 410-BE-EL-SPC-0013 | Auxiliary Transformer Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 |  | 5 | 0.1266% | 0% |  | 1404/10/24 | 1404/11/3 | [7 empty] | 0
11 | 410-BE-EL-SPC-0015 | UPS and Battery Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 |  | 5 | 0.1266% | 0% |  | 1404/10/24 | 1404/11/3 | [7 empty] | 0
12 | 410-BE-EL-SPC-0016 | Diesel Generator Technical Specification | Electrical | FA | 2026-01-14 | 2026-01-23 |  | 5 | 0.1266% | 0% |  | 1404/10/24 | 1404/11/3 | [7 empty] | 0
13 | 410-BE-EL-DRW-0020 | General Single Line Diagram (GSLD) | Electrical | FA | 2026-01-25 | 2026-02-03 | AN | 21 | 0.5318% | 75% |  | 1404/11/5 | 1404/11/14 | NT | 124 | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AN |  | 2026-02-02 | IFC | 00 | - | 2026-02-12 | CM |  |  |  | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AN | 2026-04-19
14 | 410-BE-EL-DRW-0021 | General Layout | Electrical | FA | 2026-01-22 | 2026-01-30 | AFC | 21 | 0.5318% | 100% |  | 1404/11/2 | 1404/11/10 |  |  | 47 | 2026-05-04 | AFC | 04 | - | 2026-04-26 | AP |  | 2026-01-27 | IFC | 00 | - | 2026-02-10 | CM |  |  |  | 1 | 2026-02-16 | IFA | 1 | - | 2026-02-18 | CM |  |  |  | 17 | 2026-04-06 | IFA | 2 | - | 2026-04-20 | AN |  | 29 | 2026-04-25 | IFA | 03 | - | 2026-04-26 | AP |  | 47 | 2026-05-04 | AFC | 04
15 | 410-DE-EL-CAL-0022 | PV System Calculation Study (String Size, Optimum Tilt and Pitch) | Electrical | FA | 2026-02-01 | 2026-02-10 |  | 27 | 0.6837% | 0% |  | 1404/11/12 | 1404/11/21 | [7 empty] | 0
16 | 410-BE-EL-REP-0023 | PVSYST Report | Electrical | FA | 2026-01-22 | 2026-01-31 | AN | 18 | 0.4558% | 75% |  | 1404/11/2 | 1404/11/11 | NT | 124 | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AN |  | 2026-01-31 | IFC | 00 | - | 2026-02-10 | CM | 2026-02-14 |  |  | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AN | 2026-04-18
17 | 410-BE-EL-REP-0024 | Plant Detailed Report | Electrical | FA | 2026-01-26 | 2026-02-04 | AP | 21 | 0.5318% | 100% |  | 1404/11/6 | 1404/11/15 |  |  | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AP | 1 | 2026-01-31 | IFC | 00 | - | 2026-02-10 | CM |  |  |  | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AP
18 | 410-BE-EL-MTO-0025 | Solar Module, Connector, Inverter and MV station MTO | Electrical | FI | 2026-02-05 | 2026-02-14 | AN | 18 | 0.4558% | 75% |  | 1404/11/16 | 1404/11/25 | NT | 103 | 10 | 2026-03-07 | IFC | 00 |  | 2026-03-11 | AN | 10 | 2026-03-07 | IFC | 00 |  | 2026-03-11 | AN
19 | 410-DE-EL-DRW-0026 | Strings Connection Diagram & Inverter Arrangement (DC Side) | Electrical | FA | 2026-02-04 | 2026-02-13 | AN | 21 | 0.5318% | 75% |  | 1404/11/15 | 1404/11/24 | NT | 103 | 10 | 2026-03-07 | IFC | 00 |  | 2026-03-11 | AN | 10 | 2026-03-07 | IFC | 00 |  | 2026-03-11 | AN
20 | 410-DE-EL-DRW-0027 | Module & Table Arrangement (DC Side) | Electrical | FA | 2026-01-31 | 2026-02-09 | AN | 21 | 0.5318% | 75% |  | 1404/11/11 | 1404/11/20 | NT | 103 | 10 | 2026-03-07 | IFC | 00 | 7 | 2026-03-11 | AN | 10 | 2026-03-07 | IFC | 00 | 7 | 2026-03-11 | AN
21 | 410-DE-EL-CAL-0028 | DC Cable Calculation | Electrical | FA | 2026-02-14 | 2026-02-23 | AN | 27 | 0.6837% | 75% |  | 1404/11/25 | 1404/12/4 | NT | 103 | 10 | 2026-03-07 | IFC | 00 | 5 | 2026-03-11 | AN | 10 | 2026-03-07 | IFC | 00 | 5 | 2026-03-11 | AN
22 | 410-DE-EL-MTO-0029 | DC Cable List, Labeling Code and MTO | Electrical | FI | 2026-02-18 | 2026-02-26 | AN | 19 | 0.4811% | 75% |  | 1404/11/29 | 1404/12/7 | NT | 103 | 10 | 2026-03-07 | IFC | 00 | 8 | 2026-03-11 | AN | 10 | 2026-03-07 | IFC | 00 | 8 | 2026-03-11 | AN
23 | 410-DE-EL-CAL-0030 | LVAC Cable Calculation | Electrical | FA | 2026-02-10 | 2026-02-14 | AP | 27 | 0.6837% | 100% |  | 1404/11/21 | 1404/11/25 |  |  | 70 | 2026-05-12 | IFA | 02 | - | 2026-05-13 | AP | 17 | 2026-04-06 | IFC | 00 | - | 2026-04-20 | RJ |  |  |  | 41 | 2026-04-29 | IFC | 01 | - | 2026-05-03 | CM | 2026-05-12 |  |  | 70 | 2026-05-12 | IFA | 02 |  | 2026-05-13 | AP
24 | 410-DE-EL-LST-0031 | LV Cable Termination List and MTO | Electrical | FI | 2026-02-15 | 2026-02-23 |  | 14 | 0.3545% | 0% |  | 1404/11/26 | 1404/12/4 | [7 empty] | 0
25 | 410-DE-EL-MTO-0032 | LV Cable List, Labeling Code and MTO | Electrical | FI | 2026-02-24 | 2026-02-27 | IFI | 19 | 0.4811% | 90% |  | 1404/12/5 | 1404/12/8 | PK | 35 | 78 | 2026-05-18 | IFI | 02 | - | 2026-05-03 | CM | 17 | 2026-04-06 | IFI | 00 | - | 2026-04-20 | CM |  |  |  | 42 | 2026-04-29 | IFI | 01 | - | 2026-05-03 | CM |  |  |  | 78 | 2026-05-18 | IFI | 02
26 | 410-DE-EL-CAL-0033 | MV Cable Calculations | Electrical | FA | 2026-02-10 | 2026-02-14 | AP | 27 | 0.6837% | 100% |  | 1404/11/21 | 1404/11/25 |  |  | 65 | 2026-05-11 | IFA | 02 | - | 2026-05-11 | AP | 17 | 2026-04-06 | IFC | 00 | - | 2026-04-20 | RJ |  |  |  | 43 | 2026-05-02 | IFC | 01 | - | 2026-05-03 | AN | 2026-05-11 |  |  | 65 | 2026-05-11 | IFA | 02 |  | 2026-05-11 | AP
27 | 410-DE-EL-MTO-0034 | MV Cable List, Labeling Code and MTO | Electrical | FI | 2026-02-15 | 2026-02-23 | AP | 18 | 0.4558% | 100% |  | 1404/11/26 | 1404/12/4 |  |  | 17 | 2026-04-06 | IFI | 00 | - | 2026-04-20 | CM | 17 | 2026-04-06 | IFI | 00 | - | 2026-04-20 | CM | 2026-05-02 | AP | 2026-05-03
28 | 410-DE-EL-LST-0035 | MV Cable Termination List and MTO | Electrical | FI | 2026-02-24 | 2026-03-04 |  | 14 | 0.3545% | 0% |  | 1404/12/5 | 1404/12/13 | [7 empty] | 0
29 | 410-DE-EL-DRW-0036 | Electrical Cable Route and Section | Electrical | FA | 2026-01-31 | 2026-02-09 |  | 22 | 0.5571% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
30 | 410-DE-EL-DRW-0037 | Cable Trench Layout | Electrical | FA | 2026-01-31 | 2026-02-09 |  | 22 | 0.5571% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
31 | 410-DE-EL-CAL-0038 | Earthing System Calculation | Electrical | FA | 2026-02-10 | 2026-02-14 | CM | 27 | 0.6837% | 60% |  | 1404/11/21 | 1404/11/25 | NT | 40 | 60 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM | 60 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM
32 | 410-DE-EL-DRW-0039 | Earthing System Layout | Electrical | FA | 2026-02-15 | 2026-02-24 | CM | 22 | 0.5571% | 60% |  | 1404/11/26 | 1404/12/5 | NT | 40 | 61 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM | 61 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM
33 | 410-DE-EL-CAL-0040 | Lightning Protection Calculation | Electrical | FA | 2026-01-31 | 2026-02-04 | CM | 27 | 0.6837% | 60% |  | 1404/11/11 | 1404/11/15 | NT | 41 | 54 | 2026-05-04 | IFC | 00 |  | 2026-05-12 | CM | 54 | 2026-05-04 | IFC | 00 |  | 2026-05-12 | CM
34 | 410-DE-EL-DRW-0041 | Lightning Protection Layout | Electrical | FA | 2026-02-05 | 2026-02-14 | CM | 21 | 0.5318% | 60% |  | 1404/11/16 | 1404/11/25 | NT | 40 | 62 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM | 62 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM
35 | 410-DE-EL-MTO-0042 | Earthing and Lightning Protection MTO | Electrical | FI | 2026-02-15 | 2026-02-24 |  | 19 | 0.4811% | 0% |  | 1404/11/26 | 1404/12/5 | [7 empty] | 0
36 | 410-DE-EL-DRW-0043 | Protection Single Line Diagram (PSLD) | Electrical | FA | 2026-02-04 | 2026-02-13 | CM | 21 | 0.5318% | 60% |  | 1404/11/15 | 1404/11/24 | NT | 40 | 63 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM | 63 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM
37 | 410-DE-EL-CAL-0044 | CT and PT Calculations | Electrical | FA | 2026-02-04 | 2026-02-08 |  | 27 | 0.6837% | 0% |  | 1404/11/15 | 1404/11/19 | [7 empty] | 0
38 | 410-DE-EL-DRW-0045 | MV Switchgear Logic Diagram | Electrical | FA | 2026-02-09 | 2026-02-18 |  | 20 | 0.5065% | 0% |  | 1404/11/20 | 1404/11/29 | [7 empty] | 0
39 | 410-DE-EL-REP-0046 | Trip Table | Electrical | FA | 2026-02-19 | 2026-02-28 |  | 21 | 0.5318% | 0% |  | 1404/11/30 | 1404/12/9 | [7 empty] | 0
40 | 410-DE-EL-LST-0047 | Alarm List | Electrical | FA | 2026-02-19 | 2026-02-28 |  | 14 | 0.3545% | 0% |  | 1404/11/30 | 1404/12/9 | [7 empty] | 0
41 | 410-DE-EL-DRW-0048 | Indoor and Outdoor Electrical Plan & Details for Building | Electrical | FA | 2026-01-31 | 2026-02-09 |  | 21 | 0.5318% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
42 | 410-DE-EL-MTO-0049 | MV Switchgear MTO | Electrical | FI | 2026-02-14 | 2026-02-23 |  | 19 | 0.4811% | 0% |  | 1404/11/25 | 1404/12/4 | [7 empty] | 0
43 | 410-DE-EL-LST-0050 | Load List | Electrical | FA | 2026-02-28 | 2026-03-08 |  | 14 | 0.3545% | 0% |  | 1404/12/9 | 1404/12/17 | [7 empty] | 0
44 | 410-DE-EL-DRW-0051 | LVAC Auxiliary Panel Single Line Diagram | Electrical | FA | 2026-01-28 | 2026-02-06 |  | 21 | 0.5318% | 0% |  | 1404/11/8 | 1404/11/17 | [7 empty] | 0
45 | 410-DE-EL-CAL-0052 | UPS Calculation | Electrical | FA | 2026-02-07 | 2026-02-11 |  | 27 | 0.6837% | 0% |  | 1404/11/18 | 1404/11/22 | [7 empty] | 0
46 | 410-DE-EL-MTO-0053 | AUX Equipment MTO (AUX Transformer, Diesel, UPS, Battery) | Electrical | FA | 2026-02-12 | 2026-02-21 |  | 19 | 0.4811% | 0% |  | 1404/11/23 | 1404/12/2 | [7 empty] | 0
47 | 410-DE-EL-CAL-0058 | Indoor and Outdoor Lighting Calculation | Electrical | FA | 2026-01-31 | 2026-02-04 |  | 27 | 0.6837% | 0% |  | 1404/11/11 | 1404/11/15 | [7 empty] | 0
48 | 410-DE-EL-DRW-0059 | Outdoor Lighting Pole Drawing | Electrical | FA | 2026-02-05 | 2026-02-13 |  | 23 | 0.5824% | 0% |  | 1404/11/16 | 1404/11/24 | [7 empty] | 0
49 | 410-DE-EL-DRW-0060 | Outdoor Lighting Layout and Switchboard | Electrical | FA | 2026-02-14 | 2026-02-22 |  | 23 | 0.5824% | 0% |  | 1404/11/25 | 1404/12/3 | [7 empty] | 0
50 | 410-DE-EL-MTO-0061 | Lighting System MTO | Electrical | FI | 2026-02-23 | 2026-03-03 |  | 19 | 0.4811% | 0% |  | 1404/12/4 | 1404/12/12 | [7 empty] | 0
51 | 410-DE-EL-REP-0082 | Special Tools | Electrical | FA | 2026-06-07 | 2026-06-16 | CM | 22 | 0.5571% | 60% |  | 1405/3/17 | 1405/3/26 | NT | 41 | 58 | 2026-05-06 | IFC | 00 |  | 2026-05-12 | CM | 58 | 2026-05-06 | IFC | 00 |  | 2026-05-12 | CM
52 | 410-DE-EL-DRW-0128 | MV Switchgear Schematic Diagram | Electrical | FA | 2026-02-04 | 2026-02-08 |  | 20 | 0.5065% | 0% |  | 1404/11/15 | 1404/11/19 | [7 empty] | 0
53 | 410-DE-EL-DRW-0129 | MV Switchgear Front View Drawing | Electrical | FA | 2026-02-09 | 2026-02-13 |  | 20 | 0.5065% | 0% |  | 1404/11/20 | 1404/11/24 | [7 empty] | 0
54 | 410-BE-EL-DSH-0146 | Solar Panel Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | AP | 5 | 0.1266% | 100% |  | 1404/10/28 | 1404/11/7 |  |  | 55 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AP | 55 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AP
55 | 410-BE-EL-DSH-0147 | Inverter Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | IFC | 5 | 0.1266% | 45% |  | 1404/10/28 | 1404/11/7 | PK | 161 | Email | 2026-01-12 | IFC | 00 |  | 0 |  | Email | 2026-01-12 | IFC | 00
56 | 410-BE-EL-DSH-0148 | MV Station Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | AN | 5 | 0.1266% | 75% |  | 1404/10/28 | 1404/11/7 | NT | 86 | 15 | 2026-03-26 | IFC | 00 | 2 | 2026-03-28 | AN | 15 | 2026-03-26 | IFC | 00 | 2 | 2026-03-28 | AN
57 | 410-BE-EL-DSH-0149 | DC Connection (MC4) Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | AP | 5 | 0.1266% | 100% |  | 1404/10/28 | 1404/11/7 |  |  | 21 | 2026-04-19 | IFC | 00 | - | 2026-05-02 | AP | 21 | 2026-04-19 | IFC | 00 | - | 2026-05-02 | AP
58 | 410-BE-EL-DSH-0150 | DC Cable Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | AP | 5 | 0.1266% | 100% |  | 1404/10/28 | 1404/11/7 |  |  | 23 | 2026-04-19 | IFC | 00 | - | 2026-05-02 | AP | 23 | 2026-04-19 | IFC | 00 | - | 2026-05-02 | AP
59 | 410-BE-EL-DSH-0151 | LV Cable Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 |  | 5 | 0.1266% | 0% |  | 1404/10/28 | 1404/11/7 | [7 empty] | 0
60 | 410-BE-EL-DSH-0152 | MV Cable Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 |  | 5 | 0.1266% | 0% |  | 1404/10/28 | 1404/11/7 | [7 empty] | 0
61 | 410-BE-EL-DSH-0153 | MV Switchgear (CT, PT, Relay) Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 |  | 5 | 0.1266% | 0% |  | 1404/10/28 | 1404/11/7 | [7 empty] | 0
62 | 410-BE-EL-DSH-0154 | Earthing and Lightning Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | CM | 5 | 0.1266% | 60% |  | 1404/10/28 | 1404/11/7 | NT | 115 | Email | 2026-02-02 | IFC | 00 | - | 2026-02-27 | CM | Email | 2026-02-02 | IFC | 00 | - | 2026-02-27 | CM
63 | 410-BE-EL-DSH-0155 | Auxiliary Transformer Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 | RJ | 5 | 0.1266% | 0% |  | 1404/10/28 | 1404/11/7 | NT | 48 | 56 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | RJ | 56 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | RJ
64 | 410-BE-EL-DSH-0156 | UPS and Battery Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 |  | 5 | 0.1266% | 0% |  | 1404/10/28 | 1404/11/7 | [7 empty] | 0
65 | 410-BE-EL-DSH-0157 | Diesel Generator Datasheet | Electrical | FA | 2026-01-18 | 2026-01-27 |  | 2 | 0.05065% | 0% |  | 1404/10/28 | 1404/11/7 | [7 empty] | 0
66 | 410-DE-EL-MRE-0168 | Material Requisition for Indoor Power and Lighting Distribution Panel | Electrical | FA | 2026-02-23 | 2026-02-27 |  | 45 | 1.14% | 0% |  | 1404/12/4 | 1404/12/8 | [7 empty] | 0
67 | 410-DE-EL-MRE-0169 | Material Requisition for Auxiliary Transformer | Electrical | FA | 2026-02-22 | 2026-03-03 |  | 45 | 1.14% | 0% |  | 1404/12/3 | 1404/12/12 | [7 empty] | 0
68 | 410-DE-EL-MRE-0170 | Material Requisition for PCC | Electrical | FA | 2026-05-13 | 2026-05-22 |  | 45 | 1.14% | 0% |  | 1405/2/23 | 1405/3/1 | [7 empty] | 0
69 | 410-DE-EL-MRE-0171 | Material Requisition for MV Switchgear (CT, PT, Relay) | Electrical | FA | 2026-07-07 | 2026-07-16 |  | 45 | 1.14% | 0% |  | 1405/4/16 | 1405/4/25 | [7 empty] | 0
70 | 410-DE-EL-MRE-0172 | Material Requisition for AC Cable | Electrical | FA | 2026-05-20 | 2026-05-29 |  | 35 | 0.8863% | 0% |  | 1405/2/30 | 1405/3/8 | [7 empty] | 0
71 | 410-DE-EL-MRE-0173 | Material Requisition for DC Cable | Electrical | FA | 2026-06-27 | 2026-07-06 |  | 35 | 0.8863% | 0% |  | 1405/4/6 | 1405/4/15 | [7 empty] | 0
72 | 410-DE-EL-MRE-0174 | Material Requisition for Earthing and Lightning | Electrical | FA | 2026-05-26 | 2026-06-04 |  | 45 | 1.14% | 0% |  | 1405/3/5 | 1405/3/14 | [7 empty] | 0
73 | 410-DE-EL-MRE-0175 | Material Requisition for DC Connection (MC4) | Electrical | FA | 2026-06-24 | 2026-07-03 |  | 35 | 0.8863% | 0% |  | 1405/4/3 | 1405/4/12 | [7 empty] | 0
74 | 410-DE-EL-MRE-0176 | Material Requisition for Lighting System | Electrical | FA | 2026-02-28 | 2026-03-07 |  | 45 | 1.14% | 0% |  | 1404/12/9 | 1404/12/16 | [7 empty] | 0
75 | 410-DE-EL-MRE-0177 | Material Requisition for UPS and Battery | Electrical | FA | 2026-04-28 | 2026-05-07 |  | 45 | 1.14% | 0% |  | 1405/2/8 | 1405/2/17 | [7 empty] | 0
76 | 410-BE-EL-MRE-0186 | Material Requisition for Diesel Generator | Electrical | FA | 2026-06-27 | 2026-07-06 |  | 40 | 1.013% | 0% |  | 1405/4/6 | 1405/4/15 | [7 empty] | 0
Civil | [7 empty] | 1131 | 28.64% | 37.94%
77 | 410-DE-CV-REP-0087 | Topography of Field | Civil | FI | 2026-02-03 | 2026-02-12 | AP | 28 | 0.709% | 100% |  | 1404/11/14 | 1404/11/23 |  |  | 35 | 2026-04-27 | IFC | 00 | - | 2026-05-02 | AP | 35 | 2026-04-27 | IFC | 00 | - | 2026-05-02 | AP
78 | 410-DE-CV-REP-0088 | Geotechnical Test Report | Civil | FI | 2026-02-03 | 2026-02-12 | IFI | 28 | 0.709% | 90% |  | 1404/11/14 | 1404/11/23 | PK | 56 | 33 | 2026-04-27 | IFI | 00 |  | 0 |  | 33 | 2026-04-27 | IFI | 00
79 | 410-DE-CV-REP-0089 | Ramming and Pull-Out Test Report | Civil | FI | 2026-02-03 | 2026-02-12 | IFI | 28 | 0.709% | 90% |  | 1404/11/14 | 1404/11/23 | PK | 56 | 34 | 2026-04-27 | IFI | 00 |  | 0 |  | 34 | 2026-04-27 | IFI | 00
80 | 410-DE-CV-REP-0090 | Hydrology Study Report | Civil | FI | 2026-02-03 | 2026-02-12 | CM | 28 | 0.709% | 60% |  | 1404/11/14 | 1404/11/23 | NT | 51 | 37 | 2026-04-28 | IFC | 00 | - | 2026-05-02 | CM | 37 | 2026-04-28 | IFC | 00 | - | 2026-05-02 | CM
81 | 410-DE-CV-DRW-0091 | Site Fence Detail Drawing | Civil | FA | 2026-02-18 | 2026-02-27 | AFC | 28 | 0.709% | 100% |  | 1404/11/29 | 1404/12/8 |  |  | 49 | 2026-05-04 | AFC | 06 | - | 2026-05-05 | AFC | 3 | 2026-02-19 | IFC | 00 | - | 2026-02-22 | RJ |  |  |  | - | 2026-02-22 | IFA | 1 | - | 2026-03-07 |  |  |  |  | 6 | 2026-02-23 | IFC | 02 | 9 | 2026-03-17 | RJ |  | 18 | 2026-04-08 | IFC | 3 | - | 2026-04-12 | AN |  | 27 | 2026-04-21 | IFA | 4 | - | 2026-04-26 | AN | 30 | 2026-04-27 | IFA | 05 | - | 2026-05-02 | AP | 49 | 2026-05-04 | AFC | 06 | - | 2026-05-05 | AFC
82 | 410-DE-CV-DRW-0092 | Logistic Area | Civil | FA | 2026-01-31 | 2026-02-09 | AN | 28 | 0.709% | 75% |  | 1404/11/11 | 1404/11/20 | NT | 48 | 48 | 2026-05-04 | AFC | 02 | - | 2026-05-05 | AN | 5 | 2026-02-21 | IFC | 00 | 10 | 2026-03-16 | CM |  |  |  | 39 | 2026-04-28 | IFA | 01 | - | 2026-05-02 | AP |  |  |  | 48 | 2026-05-04 | AFC | 02 |  | 2026-05-05 | AN
83 | 410-DE-CV-CAL-0093 | Buildings Foundation & Structure Calculation | Civil | FA | 2026-02-03 | 2026-02-12 | Deleted |  |  | 0% |  | 1404/11/14 | 1404/11/23 | [7 empty] | 0
84 | 410-DE-CV-CAL-0187 | Swichgear Building Foundation & Structure Calculation | Civil | FA |  |  |  | 11 | 0.2786% | 0% | [10 empty] | 0
85 | 410-DE-CV-CAL-0188 | Control Building Foundation & Structure Calculation | Civil | FA |  |  |  | 11 | 0.2786% | 0% | [10 empty] | 0
86 | 410-DE-CV-CAL-0189 | Guard Building Foundation & Structure Calculation | Civil | FA |  |  |  | 11 | 0.2786% | 0% | [10 empty] | 0
87 | 410-DE-CV-DRW-0094 | Buildings Foundation & Structure Drawing | Civil | FA | 2026-02-08 | 2026-02-17 | Deleted |  |  | 0% |  | 1404/11/19 | 1404/11/28 | [7 empty] | 0
88 | 410-DE-CV-DRW-0190 | Swichgear Building Foundation & Structure Drawing | Civil | FA |  |  |  | 9 | 0.2279% | 0% | [10 empty] | 0
89 | 410-DE-CV-DRW-0191 | Control Building Foundation & Structure Drawing | Civil | FA |  |  |  | 9 | 0.2279% | 0% | [10 empty] | 0
90 | 410-DE-CV-DRW-0192 | Guard Building Foundation & Structure Drawing | Civil | FA |  |  |  | 9 | 0.2279% | 0% | [10 empty] | 0
91 | 410-DE-CV-DRW-0098 | Parking Foundation & Structure Detail Drawing | Civil | FA | 2026-02-03 | 2026-02-12 |  | 26 | 0.6584% | 0% |  | 1404/11/14 | 1404/11/23 | [7 empty] | 0
92 | 410-DE-CV-DRW-0099 | Power Plant Entrance Gate Drawing | Civil | FA | 2026-02-22 | 2026-03-03 |  | 26 | 0.6584% | 0% |  | 1404/12/3 | 1404/12/12 | [7 empty] | 0
93 | 410-DE-CV-DRW-0100 | Parking Architectural Drawing | Civil | FA | 2026-02-10 | 2026-02-19 |  | 29 | 0.7344% | 0% |  | 1404/11/21 | 1404/11/30 | [7 empty] | 0
94 | 410-DE-CV-DRW-0101 | Landscaping Layout | Civil | FA | 2026-01-31 | 2026-02-08 |  | 29 | 0.7344% | 0% |  | 1404/11/11 | 1404/11/19 | [7 empty] | 0
95 | 410-DE-CV-DRW-0102 | Buildings Architectural Detail drawing | Civil | FA | 2026-02-12 | 2026-02-21 | Deleted |  |  | 0% |  | 1404/11/23 | 1404/12/2 |  |  | 12 | 2026-03-15 | IFC | 00 | 11 | 2026-03-17 | RJ | 12 | 2026-03-15 | IFC | 00 | 11 | 2026-03-17 | RJ
96 | 410-DE-CV-DRW-0193 | Swichgear Building Architectural Detail drawing | Civil | FA |  |  | AN | 10 | 0.2532% | 75% |  |  |  | NT | 37 | 73 | 2026-05-13 | IFC | 00 |  | 2026-05-16 | AN | 73 | 2026-05-13 | IFC | 00 |  | 2026-05-16 | AN
97 | 410-DE-CV-DRW-0194 | Control Building Architectural Detail drawing | Civil | FA |  |  | CM | 10 | 0.2532% | 60% |  |  |  | NT | 48 | 45 | 2026-05-04 | IFC | 00 |  | 2026-05-05 | CM | 45 | 2026-05-04 | IFC | 00 |  | 2026-05-05 | CM
98 | 410-DE-CV-DRW-0195 | Guard Building Architectural Detail drawing | Civil | FA |  |  | CM | 10 | 0.2532% | 60% |  |  |  | NT | 48 | 46 | 2026-05-04 | IFC | 00 |  | 2026-05-05 | CM | 46 | 2026-05-04 | IFC | 00 |  | 2026-05-05 | CM
99 | 410-DE-CV-MTO-0103 | Fence MTO | Civil | FI | 2026-02-22 | 2026-03-02 | AN | 25 | 0.6331% | 75% |  | 1404/12/3 | 1404/12/11 | NT | 57 | 26 | 2026-04-21 | IFI | 2 | - | 2026-04-26 | AN | 3 | 2026-02-19 | IFI | 00 | 16 | 2026-03-17 | CM |  |  |  | 18 | 2026-04-08 | IFI | 1 | - | 2026-04-12 | AN |  |  |  | 26 | 2026-04-21 | IFI | 2 | - | 2026-04-26 | AN | 2026-04-27
100 | 410-DE-CV-DRW-0104 | Site Grading and Leveling | Civil | FA | 2026-02-13 | 2026-02-22 | IFA | 29 | 0.7344% | 60% |  | 1404/11/24 | 1404/12/3 | PK | 56 | 32 | 2026-04-27 | IFA | 01 | 12 | 2026-03-17 | CM | Email | 2026-02-02 | IFC | 00 | 12 | 2026-03-17 | CM | 2026-04-27 |  |  | 32 | 2026-04-27 | IFA | 01
101 | 410-DE-CV-DRW-0105 | Drainage For Insite of Plant & Implementation Detail Drawing | Civil | FA | 2026-02-13 | 2026-02-21 | IFC | 29 | 0.7344% | 45% |  | 1404/11/24 | 1404/12/2 | PK | 55 | 38 | 2026-04-28 | IFC | 01 | 13 | 2026-03-17 | RJ | Email | 2026-02-02 | IFC | 00 | 13 | 2026-03-17 | RJ |  |  |  | 38 | 2026-04-28 | IFC | 01
102 | 410-DE-CV-DRW-0106 | Flood Managmant For Outsite of Plant & Implementation Detail Drawing | Civil | FA | 2026-02-16 | 2026-02-25 | IFC | 29 | 0.7344% | 45% |  | 1404/11/27 | 1404/12/6 | PK | 55 | 40 | 2026-04-28 | IFC | 01 | 14 | 2026-03-17 | RJ | Email | 2026-02-02 | IFC | 00 | 14 | 2026-03-17 | RJ |  |  |  | 40 | 2026-04-28 | IFC | 01
103 | 410-DE-CV-DRW-0107 | Internal Road Layout & Implementation Detail Drawing | Civil | FA | 2026-01-31 | 2026-02-09 | IFA | 29 | 0.7344% | 60% |  | 1404/11/11 | 1404/11/20 | PK | 55 | 36 | 2026-04-28 | IFA | 01 | 15 | 2026-03-17 | CM | Email | 2026-02-02 | IFC | 00 | 15 | 2026-03-17 | CM |  |  |  | 36 | 2026-04-28 | IFA | 01
104 | 410-DE-CV-DRW-0108 | Access Road Layout & Implementation Detail Drawing | Civil | FA | 2026-01-31 | 2026-02-09 |  | 29 | 0.7344% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
105 | 410-DE-CV-CAL-0109 | MV Station Foundation Calculation | Civil | FA | 2026-01-28 | 2026-02-06 | AN | 36 | 0.9116% | 75% |  | 1404/11/8 | 1404/11/17 | NT | 36 | 67 | 2026-05-11 | IFC | 00 | 410-05-PK-NT-C-0091 | 2026-05-17 | AN | 67 | 2026-05-11 | IFC | 00 | 410-05-PK-NT-C-0091 | 2026-05-17 | AN
106 | 410-DE-CV-DRW-0110 | MV Station Foundation Drawings | Civil | FA | 2026-02-02 | 2026-02-11 | AN | 29 | 0.7344% | 75% |  | 1404/11/13 | 1404/11/22 | NT | 36 | 68 | 2026-05-11 | IFC | 00 | 410-05-PK-NT-C-0092 | 2026-05-17 | AN | 68 | 2026-05-11 | IFC | 00 | 410-05-PK-NT-C-0092 | 2026-05-17 | AN
107 | 410-DE-CV-DRW-0111 | Auxiliary Transformer Foundation Detail Drawings | Civil | FA | 2026-01-28 | 2026-02-06 |  | 29 | 0.7344% | 0% |  | 1404/11/8 | 1404/11/17 | [7 empty] | 0
108 | 410-DE-CV-CAL-0112 | Calculation Report for Structure | Civil | FA | 2026-02-07 | 2026-02-16 | CM | 36 | 0.9116% | 60% |  | 1404/11/18 | 1404/11/27 | NT | 74 | 16 | 2026-04-04 | IFC | 00 | - | 2026-04-09 | CM | 16 | 2026-04-04 | IFC | 00 | - | 2026-04-09 | CM
109 | 410-DE-CV-DRW-0113 | Structure Detail Drawings | Civil | FA | 2026-02-13 | 2026-02-22 | CM | 29 | 0.7344% | 60% |  | 1404/11/24 | 1404/12/3 | NT | 63 | 16 | 2026-04-04 | IFC | 00 | - | 2026-04-20 | CM | 16 | 2026-04-04 | IFC | 00 | - | 2026-04-20 | CM
110 | 410-DE-CV-DRW-0114 | PV Structure Ramming Location Details Drawing (Stacking) | Civil | FA | 2026-02-07 | 2026-02-16 |  | 29 | 0.7344% | 0% |  | 1404/11/18 | 1404/11/27 | [7 empty] | 0
111 | 410-DE-CV-MTO-0115 | Solar Module Structure MTO | Civil | FI | 2026-02-17 | 2026-02-26 | AN | 25 | 0.6331% | 75% |  | 1404/11/28 | 1404/12/7 | NT | 71 | 16 | 2026-04-04 | IFI | 00 | - | 2026-04-12 | AN | 16 | 2026-04-04 | IFI | 00 | - | 2026-04-12 | AN
112 | 410-DE-CV-DRW-0116 | Table UTM Point | Civil | FA | 2026-02-17 | 2026-02-25 |  | 29 | 0.7344% | 0% |  | 1404/11/28 | 1404/12/6 | [7 empty] | 0
113 | 410-DE-CV-MTO-0117 | Structure, Entrance Gate and Foundation of Building MTO | Civil | FI | 2026-02-26 | 2026-03-07 |  | 25 | 0.6331% | 0% |  | 1404/12/7 | 1404/12/16 | [7 empty] | 0
114 | 410-DE-CV-CAL-0130 | System Drainage Calculation | Civil | FA | 2026-02-13 | 2026-02-22 | IFC | 36 | 0.9116% | 45% |  | 1404/11/24 | 1404/12/3 | PK | 56 | 31 | 2026-04-27 | IFC | 00 |  | 0 |  | 31 | 2026-04-27 | IFC | 00
115 | 410-DE-CV-CAL-0131 | Lighting Foundation Calculation | Civil | FA | 2026-01-31 | 2026-02-04 |  | 36 | 0.9116% | 0% |  | 1404/11/11 | 1404/11/15 | [7 empty] | 0
116 | 410-DE-CV-CAL-0132 | Lightning Foundation Calculation | Civil | FA | 2026-01-28 | 2026-02-01 |  | 36 | 0.9116% | 0% |  | 1404/11/8 | 1404/11/12 | [7 empty] | 0
117 | 410-DE-CV-DRW-0133 | Lightning Foundation Drawing | Civil | FA | 2026-02-05 | 2026-02-09 |  | 28 | 0.709% | 0% |  | 1404/11/16 | 1404/11/20 | [7 empty] | 0
118 | 410-DE-CV-CAL-0134 | Lighting and CCTV Pole Calculation | Civil | FA | 2026-01-31 | 2026-02-04 |  | 36 | 0.9116% | 0% |  | 1404/11/11 | 1404/11/15 | [7 empty] | 0
119 | 410-DE-CV-DRW-0135 | Septic Tank Detail Drawing | Civil | FA | 2026-02-10 | 2026-02-14 |  | 28 | 0.709% | 0% |  | 1404/11/21 | 1404/11/25 | [7 empty] | 0
120 | 410-DE-CV-DRW-0136 | Water Tank Foundation Detail Drawing | Civil | FA | 2026-02-09 | 2026-02-13 |  | 28 | 0.709% | 0% |  | 1404/11/20 | 1404/11/24 | [7 empty] | 0
121 | 410-DE-CV-CAL-0137 | Calculation for Fence | Civil | FA | 2026-02-13 | 2026-02-22 | AN | 28 | 0.709% | 75% |  | 1404/11/24 | 1404/12/3 | NT | 57 | 25 | 2026-04-21 | IFA | 3 | - | 2026-04-26 | AN |  | 2026-02-20 | IFC | 00 | [6 empty] | 6 | 2026-02-23 | IFA | 1 | 4 | 2026-03-16 | CM |  |  |  | 18 | 2026-04-08 | IFA | 2 | - | 2026-04-12 | CM |  | 25 | 2026-04-21 | IFA | 3 | - | 2026-04-26 | AN | 2026-04-27
122 | 410-DE-CV-MRE-0167 | Material Requisition for Fence | Civil | FA | 2026-03-03 | 2026-03-03 | CM | 70 | 1.773% | 60% |  | 1404/12/12 | 1404/12/12 | NT | 98 | 6 | 2026-02-23 | IFC | 00 | - | 2026-03-16 | CM | 6 | 2026-02-23 | IFC | 00 | - | 2026-03-16 | CM
Quality | [7 empty] | 580 | 14.69% | 9%
123 | 410-DE-QA-REP-0073 | Solar Panel Installation Manual & Operation & Maintenance | Quality | FI | 2026-06-03 | 2026-06-03 |  | 29 | 0.7344% | 0% |  | 1405/3/13 | 1405/3/13 | [7 empty] | 0
124 | 410-DE-QA-REP-0074 | Inverter Installation Manual & Operation & Maintenance | Quality | FI | 2026-07-16 | 2026-07-16 |  | 29 | 0.7344% | 0% |  | 1405/4/25 | 1405/4/25 | [7 empty] | 0
125 | 410-DE-QA-REP-0075 | MV Station Installation Manual & Operation & Maintenance | Quality | FI | 2026-08-05 | 2026-08-05 | IFI | 29 | 0.7344% | 90% |  | 1405/5/14 | 1405/5/14 | PK | 35 | 74 | 2026-05-18 | IFI | 00 |  | 0 |  | 74 | 2026-05-18 | IFI | 00
126 | 410-DE-QA-REP-0076 | UPS Installation Manual & Operation & Maintenance | Quality | FI | 2026-08-16 | 2026-08-16 |  | 29 | 0.7344% | 0% |  | 1405/5/25 | 1405/5/25 | [7 empty] | 0
127 | 410-DE-QA-REP-0077 | AUX Transformer Installation Manual & Operation & Maintenance | Quality | FI | 2026-08-04 | 2026-08-04 |  | 29 | 0.7344% | 0% |  | 1405/5/13 | 1405/5/13 | [7 empty] | 0
128 | 410-DE-QA-REP-0078 | Diesel Generator Installation Manual & Operation & Maintenance | Quality | FI | 2026-08-04 | 2026-08-04 |  | 29 | 0.7344% | 0% |  | 1405/5/13 | 1405/5/13 | [7 empty] | 0
129 | 410-DE-QA-REP-0079 | Weather Station Installation Manual & Operation & Maintenance | Quality | FI | 2026-08-17 | 2026-08-17 |  | 29 | 0.7344% | 0% |  | 1405/5/26 | 1405/5/26 | [7 empty] | 0
130 | 410-DE-QA-REP-0080 | Solar Structure Installation Manual & Operation & Maintenance | Quality | FI | 2026-05-04 | 2026-05-04 |  | 29 | 0.7344% | 0% |  | 1405/2/14 | 1405/2/14 | [7 empty] | 0
131 | 410-DE-QA-REP-0081 | SCADA and Monitoring System Installation Manual & Operation & Maintenance | Quality | FI | 2026-08-06 | 2026-08-06 |  | 29 | 0.7344% | 0% |  | 1405/5/15 | 1405/5/15 | [7 empty] | 0
132 | 410-DE-QA-REP-0083 | Project O&M General Instructions | Quality | FI | 2026-08-26 | 2026-08-26 |  | 29 | 0.7344% | 0% |  | 1405/6/4 | 1405/6/4 | [7 empty] | 0
133 | 410-DE-QA-REP-0118 | Test Report of Solar Structure | Quality | FI | 2026-06-03 | 2026-06-04 | CM | 29 | 0.7344% | 90% |  | 1405/3/13 | 1405/3/14 | NT | 72 | 16 | 2026-04-04 | IFI | 00 | - | 2026-04-11 | CM | 16 | 2026-04-04 | IFI | 00 | - | 2026-04-11 | CM
134 | 410-DE-QA-REP-0119 | Test Reports for PV Modules | Quality | FI | 2026-06-03 | 2026-06-04 |  | 29 | 0.7344% | 0% |  | 1405/3/13 | 1405/3/14 | [7 empty] | 0
135 | 410-DE-QA-REP-0120 | Test Reports for Inverter | Quality | FI | 2026-07-16 | 2026-07-17 |  | 29 | 0.7344% | 0% |  | 1405/4/25 | 1405/4/26 | [7 empty] | 0
136 | 410-DE-QA-REP-0121 | Test Reports for MV Sation | Quality | FI | 2026-08-10 | 2026-08-11 |  | 29 | 0.7344% | 0% |  | 1405/5/19 | 1405/5/20 | [7 empty] | 0
137 | 410-DE-QA-REP-0122 | Test Reports for AC and DC Cables | Quality | FI | 2026-08-19 | 2026-08-20 | Deleted |  |  | 0% |  | 1405/5/28 | 1405/5/29 | [7 empty] | 0
138 | 410-DE-QA-REP-0196 | Test Reports for AC Cables | Quality | FI |  |  |  | 14.5 | 0.3672% | 0% | [10 empty] | 0
139 | 410-DE-QA-REP-0197 | Test Reports for DC Cables | Quality | FI |  |  |  | 14.5 | 0.3672% | 0% | [10 empty] | 0
140 | 410-DE-QA-REP-0123 | Test Reports for Diesel Generators | Quality | FI | 2026-09-01 | 2026-09-01 |  | 29 | 0.7344% | 0% |  | 1405/6/10 | 1405/6/10 | [7 empty] | 0
141 | 410-DE-QA-REP-0124 | Test Reports for AUX Transformer | Quality | FI | 2026-09-01 | 2026-09-01 |  | 29 | 0.7344% | 0% |  | 1405/6/10 | 1405/6/10 | [7 empty] | 0
142 | 410-DE-QA-REP-0125 | Test Reports for Earthing and Ligthtning | Quality | FI | 2026-08-06 | 2026-08-07 |  | 29 | 0.7344% | 0% |  | 1405/5/15 | 1405/5/16 | [7 empty] | 0
143 | 410-DE-QA-REP-0126 | Test Reports for MV Switchgear (CT, PT, Relay, …) | Quality | FI | 2026-08-17 | 2026-08-18 |  | 29 | 0.7344% | 0% |  | 1405/5/26 | 1405/5/27 | [7 empty] | 0
144 | 410-DE-QA-REP-0127 | Test Reports for UPS and Battery | Quality | FI | 2026-08-19 | 2026-08-20 |  | 29 | 0.7344% | 0% |  | 1405/5/28 | 1405/5/29 | [7 empty] | 0
Telecom | [7 empty] | 307 | 7.774% | 12.31%
145 | 410-BE-TL-SPC-0010 | Monitoring System Technical Specification | Telecom | FA | 2026-01-14 | 2026-01-23 | AN | 8 | 0.2026% | 75% |  | 1404/10/24 | 1404/11/3 | NT | 37 | 71 | 2026-05-13 | IFC | 00 |  | 2026-05-16 | AN | 71 | 2026-05-13 | IFC | 00 |  | 2026-05-16 | AN
146 | 410-BE-TL-SPC-0011 | Data Logger Technical Specification | Telecom | FA | 2026-01-27 | 2026-02-05 |  | 8 | 0.2026% | 0% |  | 1404/11/7 | 1404/11/16 | [7 empty] | 0
147 | 410-BE-TL-SPC-0012 | Weather Station Technical Specification | Telecom | FA | 2026-01-27 | 2026-02-05 | CM | 8 | 0.2026% | 60% |  | 1404/11/7 | 1404/11/16 | NT | 42 | 57 | 2026-05-06 | IFC | 00 |  | 2026-05-11 | CM | 57 | 2026-05-06 | IFC | 00 |  | 2026-05-11 | CM
148 | 410-BE-TL-SPC-0014 | CCTV and NVR Technical Specification | Telecom | FA | 2026-01-27 | 2026-02-05 | CM | 8 | 0.2026% | 60% |  | 1404/11/7 | 1404/11/16 | NT | 40 | 66 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM | 66 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM
149 | 410-DE-TL-DRW-0054 | CCTV System Block Diagram | Telecom | FA | 2026-02-10 | 2026-02-13 |  | 19 | 0.4811% | 0% |  | 1404/11/21 | 1404/11/24 | [7 empty] | 0
150 | 410-DE-TL-DRW-0055 | CCTV System Arrangement & Layout | Telecom | FA | 2026-02-14 | 2026-02-17 |  | 19 | 0.4811% | 0% |  | 1404/11/25 | 1404/11/28 | [7 empty] | 0
151 | 410-DE-TL-DRW-0056 | CCTV Pole Detail Drawing, Switchboard, CAFU Details | Telecom | FA | 2026-02-18 | 2026-02-21 |  | 22 | 0.5571% | 0% |  | 1404/11/29 | 1404/12/2 | [7 empty] | 0
152 | 410-DE-TL-MTO-0057 | CCTV System MTO | Telecom | FI | 2026-02-22 | 2026-03-03 |  | 18 | 0.4558% | 0% |  | 1404/12/3 | 1404/12/12 | [7 empty] | 0
153 | 410-DE-TL-LST-0063 | SCADA System I/O List | Telecom | FA | 2026-02-04 | 2026-02-07 |  | 14 | 0.3545% | 0% |  | 1404/11/15 | 1404/11/18 | [7 empty] | 0
154 | 410-DE-TL-DRW-0064 | Monitoring System Overall Diagram | Telecom | FA | 2026-02-19 | 2026-02-22 |  | 20 | 0.5065% | 0% |  | 1404/11/30 | 1404/12/3 | [7 empty] | 0
155 | 410-DE-TL-MTO-0065 | Telecommunication and Monitoring System MTO | Telecom | FI | 2026-02-23 | 2026-02-26 |  | 19 | 0.4811% | 0% |  | 1404/12/4 | 1404/12/7 | [7 empty] | 0
156 | 410-BE-TL-DSH-0158 | Monitoring System Datasheet | Telecom | FA | 2026-01-18 | 2026-01-27 | CM | 7 | 0.1773% | 60% |  | 1404/10/28 | 1404/11/7 | NT | 37 | 72 | 2026-05-13 | IFC | 00 |  | 2026-05-16 | CM | 72 | 2026-05-13 | IFC | 00 |  | 2026-05-16 | CM
157 | 410-BE-TL-DSH-0159 | Data Logger Datasheet | Telecom | FA | 2026-01-31 | 2026-02-09 |  | 7 | 0.1773% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
158 | 410-BE-TL-DSH-0160 | Weather Station Datasheet | Telecom | FA | 2026-01-31 | 2026-02-09 |  | 3 | 0.07597% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
159 | 410-BE-TL-DSH-0161 | CCTV and NVR Datasheet | Telecom | FA | 2026-01-31 | 2026-02-09 |  | 7 | 0.1773% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
160 | 410-DE-TL-MRE-0178 | Material Requisition forTelecommunication and Monitoring Cable | Telecom | FA | 2026-07-17 | 2026-07-21 |  | 30 | 0.7597% | 0% |  | 1405/4/26 | 1405/4/30 | [7 empty] | 0
161 | 410-BE-TL-MRE-0179 | Material Requisition forFiber Optics | Telecom | FA | 2026-06-08 | 2026-06-12 |  | 30 | 0.7597% | 0% |  | 1405/3/18 | 1405/3/22 | [7 empty] | 0
162 | 410-DE-TL-MRE-0180 | Material Requisition for CCTV and NVR | Telecom | FA | 2026-03-04 | 2026-03-08 |  | 30 | 0.7597% | 0% |  | 1404/12/13 | 1404/12/17 | [7 empty] | 0
163 | 410-BE-TL-MRE-0185 | Material Requisition for Weather Station | Telecom | FA | 2026-05-14 | 2026-05-18 | CM | 30 | 0.7597% | 60% |  | 1405/2/24 | 1405/2/28 | NT | 40 | 64 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM | 64 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM
Mechanical | [7 empty] | 226 | 5.723% | 6.173%
164 | 410-BE-ME-SPC-0017 | HVAC Technical Specification | Mechanical | FA | 2026-01-27 | 2026-02-05 |  | 8 | 0.2026% | 0% |  | 1404/11/7 | 1404/11/16 | [7 empty] | 0
165 | 410-BE-ME-SPC-0018 | Piping Material, Plumbing Fittings, Pumps Technical Specification | Mechanical | FA | 2026-01-27 | 2026-02-05 |  | 8 | 0.2026% | 0% |  | 1404/11/7 | 1404/11/16 | [7 empty] | 0
166 | 410-DE-ME-REP-0062 | Solar Panel Cleaning & Maintenance Procedures | Mechanical | FA | 2026-02-23 | 2026-02-26 | CM | 15 | 0.3798% | 60% |  | 1404/12/4 | 1404/12/7 | NT | 50 |  | 2026-02-02 | IFC | 00 | - | 2026-05-03 | CM |  | 2026-02-02 | IFC | 00 | - | 2026-05-03 | CM
167 | 410-DE-ME-CAL-0066 | HVAC Equipment Calculation | Mechanical | FA | 2026-02-10 | 2026-02-19 |  | 20 | 0.5065% | 0% |  | 1404/11/21 | 1404/11/30 | [7 empty] | 0
168 | 410-DE-ME-DRW-0067 | HVAC Equipment Layout for Building | Mechanical | FA | 2026-02-20 | 2026-02-23 | Deleted |  |  | 0% |  | 1404/12/1 | 1404/12/4 | [7 empty] | 0
169 | 410-DE-ME-DRW-0198 | HVAC Equipment Layout for Swichgear Building | Mechanical | FA |  |  |  | 6.6667 | 0.1688% | 0% | [10 empty] | 0
170 | 410-DE-ME-DRW-0199 | HVAC Equipment Layout for Control Building | Mechanical | FA |  |  |  | 6.6667 | 0.1688% | 0% | [10 empty] | 0
171 | 410-DE-ME-DRW-0200 | HVAC Equipment Layout for Guard Building | Mechanical | FA |  |  |  | 6.6667 | 0.1688% | 0% | [10 empty] | 0
172 | 410-DE-ME-MTO-0068 | HVAC and Piping System MTO | Mechanical | FI | 2026-02-24 | 2026-02-27 |  | 19 | 0.4811% | 0% |  | 1404/12/5 | 1404/12/8 | [7 empty] | 0
173 | 410-DE-ME-DRW-0095 | Mechanical Drawing (Water Supply and Sewage Systems) | Mechanical | FA | 2026-02-10 | 2026-02-13 |  | 20 | 0.5065% | 0% |  | 1404/11/21 | 1404/11/24 | [7 empty] | 0
174 | 410-DE-ME-SPC-0096 | Septic Tank Technical Specification | Mechanical | FA | 2026-01-27 | 2026-02-05 | IFC | 4 | 0.1013% | 45% |  | 1404/11/7 | 1404/11/16 | PK | 35 | 75 | 2026-05-18 | IFC | 00 |  | 0 |  | 75 | 2026-05-18 | IFC | 00
175 | 410-DE-ME-SPC-0097 | Water Tank Technical Specification | Mechanical | FA | 2026-01-27 | 2026-02-05 |  | 4 | 0.1013% | 0% |  | 1404/11/7 | 1404/11/16 | [7 empty] | 0
176 | 410-BE-ME-DSH-0162 | HVAC Datasheet | Mechanical | FA | 2026-01-31 | 2026-02-09 |  | 7 | 0.1773% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
177 | 410-BE-ME-DSH-0163 | Piping Material, Plumbing Fittings, Pumps Datasheet | Mechanical | FA | 2026-01-31 | 2026-02-09 |  | 7 | 0.1773% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
178 | 410-BE-ME-DSH-0164 | Septic Tank Datasheet | Mechanical | FA | 2026-01-31 | 2026-02-09 | IFC | 7 | 0.1773% | 45% |  | 1404/11/11 | 1404/11/20 | PK | 35 | 76 | 2026-05-18 | IFC | 00 |  | 0 |  | 76 | 2026-05-18 | IFC | 00
179 | 410-BE-ME-DSH-0165 | Water Tank Datasheet | Mechanical | FA | 2026-01-31 | 2026-02-09 |  | 7 | 0.1773% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
180 | 410-BE-ME-MRE-0183 | Material Requisition for Septic Tank | Mechanical | FA | 2026-02-15 | 2026-02-17 |  | 40 | 1.013% | 0% |  | 1404/11/26 | 1404/11/28 | [7 empty] | 0
181 | 410-BE-ME-MRE-0184 | Material Requisition for Water | Mechanical | FA | 2026-02-14 | 2026-02-16 |  | 40 | 1.013% | 0% |  | 1404/11/25 | 1404/11/27 | [7 empty] | 0
Safety | [7 empty] | 149 | 3.773% | 14.19%
182 | 410-BE-SF-SPC-0019 | Fire Alarm System Technical Specification | Safety | FA | 2026-01-27 | 2026-02-05 | IFC | 8 | 0.2026% | 45% |  | 1404/11/7 | 1404/11/16 | PK | 41 | 69 | 2026-05-12 | IFC | 00 |  | 0 |  | 69 | 2026-05-12 | IFC | 00
183 | 410-DE-SF-DRW-0069 | Fire Fighting Equipment Arrangement of MV Switchgear Buildings | Safety | FA | 2026-02-16 | 2026-02-23 |  | 19 | 0.4811% | 0% |  | 1404/11/27 | 1404/12/4 | [7 empty] | 0
184 | 410-DE-SF-DRW-0070 | Outdoor Fire Fighting Equipment & Shelter Arrangement | Safety | FA | 2026-02-20 | 2026-02-28 | IFC | 19 | 0.4811% | 45% |  | 1404/12/1 | 1404/12/9 | PK | 35 | 77 | 2026-05-18 | IFC | 00 |  | 0 |  | 77 | 2026-05-18 | IFC | 00
185 | 410-DE-SF-DRW-0071 | Fire Alarm System Layout and Block Diagram | Safety | FA | 2026-02-20 | 2026-02-27 |  | 19 | 0.4811% | 0% |  | 1404/12/1 | 1404/12/8 | [7 empty] | 0
186 | 410-DE-SF-MTO-0072 | Fire and Safety and F & G System MTO | Safety | FI | 2026-02-25 | 2026-03-06 |  | 19 | 0.4811% | 0% |  | 1404/12/6 | 1404/12/15 | [7 empty] | 0
187 | 410-BE-SF-DSH-0166 | Fire Alarm System Datasheet | Safety | FA | 2026-01-31 | 2026-02-09 |  | 5 | 0.1266% | 0% |  | 1404/11/11 | 1404/11/20 | [7 empty] | 0
188 | 410-DE-SF-MRE-0181 | Material Requisition for Fire Alarm System | Safety | FA | 2026-07-13 | 2026-07-22 |  | 30 | 0.7597% | 0% |  | 1405/4/22 | 1405/4/31 | [7 empty] | 0
189 | 410-DE-SF-MRE-0182 | Material Requisition for Fire Fighting Equipment Arrangement | Safety | FA | 2026-06-30 | 2026-07-09 |  | 15 | 0.3798% | 0% |  | 1405/4/9 | 1405/4/18 | [7 empty] | 0
190 | 410-DE-SF-REP-0201 | HSE Plan | Safety | FA |  |  | CM | 15 | 0.3798% | 60% |  |  |  | NT | 42 | 59 | 2026-04-25 | IFC | 00 |  | 2026-05-11 | CM | 59 | 2026-04-25 | IFC | 00 |  | 2026-05-11 | CM
Project Management | [7 empty] | 108 | 2.735% | 62.04%
191 | 410-DE-PM-LST-0084 | Master Document List | Project Management | FA | 2026-01-14 | 2026-01-23 | AP | 14 | 0.3545% | 100% |  | 1404/10/24 | 1404/11/3 |  |  | 44 | 2026-05-04 | IFA | 06 | نامه 0034 | 2026-05-05 | AP | نامه 0006 | 2026-02-07 | IFC | 00 | - | 2026-02-14 | CM | [13 empty] | 8 | 2026-02-25 | IFA | 2 |  | 2026-02-15 | CM |  | 9 | 2026-02-25 | IFA | 3 |  |  |  |  | 13 | 2026-03-15 | IFA | 4 |  |  |  | 19 | 2026-04-11 | IFA | 5 | پیرو جلسه 1405/02/09نامه کارفرما ارسال می شود | 2026-04-29 | AP | 44 | 2026-05-04 | IFA | 06 | نامه 0034 | 2026-05-05 | AP
192 | 410-DE-PM-REP-0085 | Time Schedule | Project Management | FA | 2026-01-24 | 2026-02-02 | AP | 23 | 0.5824% | 100% |  | 1404/11/4 | 1404/11/13 |  |  | 20 | 2026-04-22 | IFA | 2 | 410-05-PK-NT-C-0055 | 2026-04-26 | AP | - | 2026-02-01 | IFC | 00 | جلسه MC |  | CM |  |  |  | 11 | 2026-03-11 | IFA | 1 | نامه کارفرما | 2026-03-31 | CM |  |  |  | 20 | 2026-04-22 | IFA | 2 | 410-05-PK-NT-C-0055 | 2026-04-26 | AP
193 | 410-DE-PM-CAF-0086 | Cash Flow | Project Management | FA | 2026-04-09 | 2026-04-28 | CM | 15 | 0.3798% | 60% |  | 1405/1/20 | 1405/2/8 | NT | 76 | 14 | 2026-03-20 | IFA | 1 | جلسه کارفرما | 2026-04-07 | CM | نامه 0015 | 2026-02-17 | IFC | 00 | جلسه کارفرما | 2026-02-23 | CM |  |  |  | 14 | 2026-03-20 | IFA | 1 | جلسه کارفرما | 2026-04-07 | CM
194 | 410-DE-PM-REP-0138 | Monthly Report 410-M-001 | Project Management | FI | 2026-02-19 | 2026-02-23 | AP | 7 | 0.1773% | 100% |  | 1404/11/30 | 1404/12/4 |  |  | 7 | 2026-02-24 | IFI | 00 | جلسه 1405/02/09 | 2026-04-29 | AP | 7 | 2026-02-24 | IFI | 00 | جلسه 1405/02/09 | 2026-04-29 | AP
195 | 410-DE-PM-REP-0139 | Monthly Report 410-M-002 | Project Management | FI | 2026-03-19 | 2026-03-28 | AP | 7 | 0.1773% | 100% |  | 1404/12/28 | 1405/1/8 |  |  | - | 2026-03-20 | IFI | 00 | جلسه 1405/02/09 | 2026-04-29 | AP | - | 2026-03-20 | IFI | 00 | جلسه 1405/02/09 | 2026-04-29 | AP
196 | 410-DE-PM-REP-0140 | Monthly Report 410-M-003 | Project Management | FI | 2026-04-21 | 2026-04-25 | AP | 7 | 0.1773% | 100% |  | 1405/2/1 | 1405/2/5 |  |  | 28 | 2026-04-23 | IFI | 00 | 140-05-PK-NT-C-0097 | 2026-05-05 | AP | 28 | 2026-04-23 | IFI | 00 | 140-05-PK-NT-C-0097 | 2026-05-05 | AP
197 | 410-DE-PM-REP-0141 | Monthly Report 410-M-004 | Project Management | FI | 2026-05-22 | 2026-05-26 |  | 7 | 0.1773% | 0% |  | 1405/3/1 | 1405/3/5 | [7 empty] | 0
198 | 410-DE-PM-REP-0142 | Monthly Report 410-M-005 | Project Management | FI | 2026-06-22 | 2026-06-26 |  | 7 | 0.1773% | 0% |  | 1405/4/1 | 1405/4/5 | [7 empty] | 0
199 | 410-DE-PM-REP-0143 | Monthly Report 410-M-006 | Project Management | FI | 2026-07-23 | 2026-07-27 |  | 7 | 0.1773% | 0% |  | 1405/5/1 | 1405/5/5 | [7 empty] | 0
200 | 410-DE-PM-REP-0144 | Monthly Report 410-M-007 | Project Management | FI | 2026-08-23 | 2026-08-27 |  | 7 | 0.1773% | 0% |  | 1405/6/1 | 1405/6/5 | [7 empty] | 0
201 | 410-DE-PM-REP-0145 | Monthly Report 410-M-008 | Project Management | FI | 2026-09-07 | 2026-09-11 |  | 7 | 0.1773% | 0% |  | 1405/6/16 | 1405/6/20 | [7 empty] | 0
Note on AS209: ارسال اولیه 2026/04/15