## PMS
| پروژه احداث نیروگاه خورشیدی 20 مگاواتی زارچ یزد شماره قرارداد: PKPS-P2-C2-0410 | [17 empty] | 2026-06-27 |  | RJ
| Progress Measurement System (PMS) | [17 empty] | AN | IFI | AP
| WBS | Task Name | Document No. | Duration | Start | Finish | W.F total | Volume |  |  | Cumulative : |  | 1405/04/02 | This Period |  | Last Period : | 1405/03/26
[8 empty] | Total | Unit | Done | Plan% | Actual% | Var.% | Plan% | Actual% | Plan% | Actual% | Var.%
2 | 0 | پروژه احداث نیروگاه خورشیدی 20 مگا واتی زارچ یزد |  | 240 روز | 1404/10/21 | 1405/6/21 | 10000 |  |  |  | 44.29% | 23.32% | -20.97% | 1.96% | 3.08% | 42.33% | 20.24% | -22.09%
3 | 1 | شروع |  | 0 روز | 1404/10/21 | 1404/10/21 | 0 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
4 | 2 | مایلستون های کلیدی |  | 223 روز | 1404/10/23 | 1405/6/7 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5 | 2.1 | دریافت سایر اطلاعات مقدماتی از کارفرما (آزمایش شیمیایی خاک، تست کشش پایه ها و…) |  | 0 روز | 1404/10/23 | 1404/10/23 | 0 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
6 | 2.2 | واریز اولین پیش پرداخت بخش مهندسی |  | 0 روز | 1404/11/13 | 1404/11/13 | 0 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
7 | 2.3 | دریافت مطالعات ژئوتکنیک |  | 0 روز | 1404/10/23 | 1404/10/23 | 0 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
8 | 2.4 | تحویل زمین |  | 0 روز | 1404/11/6 | 1404/11/6 | 0 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
9 | 2.5 | تاییدیه تجهیزات (پنل، اینورتر و MV Station( |  | 0 روز | 1404/11/4 | 1404/11/4 | 0 |  |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
10 | 2.6 | اتمام طراحی و اخذ تاییدیه |  | 0 روز | 1405/1/31 | 1405/1/31 | 0 |  |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
11 | 2.7 | اتمام استعلام قیمتی و سفارش گذاری خرید خارجی |  | 0 روز | 1404/12/8 | 1404/12/8 | 0 |  |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
12 | 2.8 | اتمام تامین و تحویل خرید خارجی در سایت پروژه |  | 0 روز | 1405/4/30 | 1405/4/30 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13 | 2.9 | اتمام تجهیز کارگاه |  | 0 روز | 1405/1/28 | 1405/1/28 | 0 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
14 | 2.1 | اتمام نصب سازه |  | 0 روز | 1405/4/28 | 1405/4/28 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
15 | 2.11 | اتمام نصب پنل |  | 0 روز | 1405/5/30 | 1405/5/30 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
16 | 2.12 | اتمام ساختمان مانیتورینگ |  | 0 روز | 1405/6/7 | 1405/6/7 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
17 | 2.13 | اتمام نصب MV Staion |  | 0 روز | 1405/5/22 | 1405/5/22 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
18 | 2.14 | اتمام نصب اینورتر |  | 0 روز | 1405/5/7 | 1405/5/7 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
19 | 2.15 | تست پست بالادست |  | 0 روز | 1405/6/6 | 1405/6/6 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
20 | 3 | مهندسی |  | 236 روز | 1404/10/24 | 1405/6/20 | 200 |  |  |  | 85.33% | 61.1% | -24.23% | 2.26% | 2.73% | 83.07% | 58.37% | -24.7%
| 3.1 | Electrical |  |  |  |  | 73.335 |  |  |  | 100% | 72.33% | -27.67% | 6.796% | 2.424% | 93.2% | 69.9% | -23.3%
| 3.2.2.1 | Solar Panel Technical Specification | 410-BE-EL-SPC-0001 |  |  |  | 0.25323 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.2.2 | Inverter Technical Specification | 410-BE-EL-SPC-0002 |  |  |  | 0.25323 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.2.3 | MV Station Technical Specification | 410-BE-EL-SPC-0003 |  |  |  | 0.25323 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.2.4 | DC Connection (MC4) Technical Specification | 410-BE-EL-SPC-0004 |  |  |  | 0.25323 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.2.5 | DC Cable Technical Specification | 410-BE-EL-SPC-0005 |  |  |  | 0.25323 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.2.6 | LV Cable Technical Specification | 410-BE-EL-SPC-0006 |  |  |  | 0.25323 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.2.2.7 | MV Cable Technical Specification | 410-BE-EL-SPC-0007 |  |  |  | 0.25323 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.2.2.8 | MV Switchgear (CT, PT, Relay) Technical Specification | 410-BE-EL-SPC-0008 |  |  |  | 0.25323 | 100 | % | 75 | 100% | 75% | -25% | 0% | 0% | 100% | 75% | -25%
| 3.2.2.9 | Earthing and Lightning Technical Specification | 410-BE-EL-SPC-0009 |  |  |  | 0.25323 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.2.2.10 | Auxiliary Transformer Technical Specification | 410-BE-EL-SPC-0013 |  |  |  | 0.25323 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.2.2.11 | UPS and Battery Technical Specification | 410-BE-EL-SPC-0015 |  |  |  | 0.25323 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.2.2.12 | Diesel Generator Technical Specification | 410-BE-EL-SPC-0016 |  |  |  | 0.25323 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.2.5 | General Single Line Diagram (GSLD) | 410-BE-EL-DRW-0020 |  |  |  | 1.0636 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.4 | General Layout | 410-BE-EL-DRW-0021 |  |  |  | 1.0636 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.2 | PV System Calculation Study (String Size, Optimum Tilt and Pitch) | 410-DE-EL-CAL-0022 |  |  |  | 1.3674 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.2.3 | PVSYST Report | 410-BE-EL-REP-0023 |  |  |  | 0.91162 | 100 | % | 75 | 100% | 75% | -25% | 0% | 0% | 100% | 75% | -25%
| 3.2.6 | Plant Detailed Report | 410-BE-EL-REP-0024 |  |  |  | 1.0636 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.1 | Solar Module, Connector, Inverter and MV station MTO | 410-BE-EL-MTO-0025 |  |  |  | 0.91162 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.3 | Strings Connection Diagram & Inverter Arrangement (DC Side) | 410-DE-EL-DRW-0026 |  |  |  | 1.0636 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.4 | Module & Table Arrangement (DC Side) | 410-DE-EL-DRW-0027 |  |  |  | 1.0636 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.5 | DC Cable Calculation | 410-DE-EL-CAL-0028 |  |  |  | 1.3674 | 100 | % | 75 | 100% | 75% | -25% | 0% | 0% | 100% | 75% | -25%
| 3.4.6 | DC Cable List, Labeling Code and MTO | 410-DE-EL-MTO-0029 |  |  |  | 0.96227 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.4.7 | LVAC Cable Calculation | 410-DE-EL-CAL-0030 |  |  |  | 1.3674 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.8 | LV Cable Termination List and MTO | 410-DE-EL-LST-0031 |  |  |  | 0.70904 | 100 | % | 90 | 100% | 90% | -10% | 0% | 90% | 100% | 0% | -100%
| 3.4.9 | LV Cable List, Labeling Code and MTO | 410-DE-EL-MTO-0032 |  |  |  | 0.96227 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.10 | MV Cable Calculations | 410-DE-EL-CAL-0033 |  |  |  | 1.3674 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.11 | MV Cable List, Labeling Code and MTO | 410-DE-EL-MTO-0034 |  |  |  | 0.91162 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.12 | MV Cable Termination List and MTO | 410-DE-EL-LST-0035 |  |  |  | 0.70904 | 100 | % | 90 | 100% | 90% | -10% | 0% | 90% | 100% | 0% | -100%
| 3.4.13 | Electrical Cable Route and Section | 410-DE-EL-DRW-0036 |  |  |  | 1.1142 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.4.14 | Cable Trench Layout | 410-DE-EL-DRW-0037 |  |  |  | 1.1142 | 100 | % | 45 | 100% | 45% | -55% | 0% | 45% | 100% | 0% | -100%
| 3.4.15 | Earthing System Calculation | 410-DE-EL-CAL-0038 |  |  |  | 1.3674 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.4.16 | Earthing System Layout | 410-DE-EL-DRW-0039 |  |  |  | 1.1142 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.4.17 | Lightning Protection Calculation | 410-DE-EL-CAL-0040 |  |  |  | 1.3674 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.18 | Lightning Protection Layout | 410-DE-EL-DRW-0041 |  |  |  | 1.0636 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.4.19 | Earthing and Lightning Protection MTO | 410-DE-EL-MTO-0042 |  |  |  | 0.96227 | 100 | % | 90 | 100% | 90% | -10% | 0% | 0% | 100% | 90% | -10%
| 3.4.20 | Protection Single Line Diagram (PSLD) | 410-DE-EL-DRW-0043 |  |  |  | 1.0636 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.4.21 | CT and PT Calculations | 410-DE-EL-CAL-0044 |  |  |  | 1.3674 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.22 | MV Switchgear Logic Diagram | 410-DE-EL-DRW-0045 |  |  |  | 1.0129 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.4.23 | Trip Table | 410-DE-EL-REP-0046 |  |  |  | 1.0636 | 100 | % | 75 | 100% | 75% | -25% | 0% | 0% | 100% | 75% | -25%
| 3.4.24 | Alarm List | 410-DE-EL-LST-0047 |  |  |  | 0.70904 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.25 | Indoor and Outdoor Electrical Plan & Details for Building | 410-DE-EL-DRW-0048 |  |  |  | 1.0636 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.26 | MV Switchgear MTO | 410-DE-EL-MTO-0049 |  |  |  | 0.96227 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.27 | Load List | 410-DE-EL-LST-0050 |  |  |  | 0.70904 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.28 | LVAC Auxiliary Panel Single Line Diagram | 410-DE-EL-DRW-0051 |  |  |  | 1.0636 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.29 | UPS Calculation | 410-DE-EL-CAL-0052 |  |  |  | 1.3674 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.30 | AUX Equipment MTO (AUX Transformer, Diesel, UPS, Battery) | 410-DE-EL-MTO-0053 |  |  |  | 0.96227 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.31 | Indoor and Outdoor Lighting Calculation | 410-DE-EL-CAL-0058 |  |  |  | 1.3674 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.32 | Outdoor Lighting Pole Drawing | 410-DE-EL-DRW-0059 |  |  |  | 1.1649 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.33 | Outdoor Lighting Layout and Switchboard | 410-DE-EL-DRW-0060 |  |  |  | 1.1649 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.34 | Lighting System MTO | 410-DE-EL-MTO-0061 |  |  |  | 0.96227 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.35 | Special Tools | 410-DE-EL-REP-0082 |  |  |  | 1.1142 | 100 | % | 100 | 100% | 100% | 0% | 70% | 0% | 30% | 100% | 70%
| 3.4.36 | MV Switchgear Schematic Diagram | 410-DE-EL-DRW-0128 |  |  |  | 1.0129 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.37 | MV Switchgear Front View Drawing | 410-DE-EL-DRW-0129 |  |  |  | 1.0129 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.2.1.1 | Solar Panel Datasheet | 410-BE-EL-DSH-0146 |  |  |  | 0.25323 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.2 | Inverter Datasheet | 410-BE-EL-DSH-0147 |  |  |  | 0.25323 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.2.1.3 | MV Station Datasheet | 410-BE-EL-DSH-0148 |  |  |  | 0.25323 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.4 | DC Connection (MC4) Datasheet | 410-BE-EL-DSH-0149 |  |  |  | 0.25323 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.5 | DC Cable Datasheet | 410-BE-EL-DSH-0150 |  |  |  | 0.25323 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.6 | LV Cable Datasheet | 410-BE-EL-DSH-0151 |  |  |  | 0.25323 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.7 | MV Cable Datasheet | 410-BE-EL-DSH-0152 |  |  |  | 0.25323 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.8 | MV Switchgear (CT, PT, Relay) Datasheet | 410-BE-EL-DSH-0153 |  |  |  | 0.25323 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.2.1.9 | Earthing and Lightning Datasheet | 410-BE-EL-DSH-0154 |  |  |  | 0.25323 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.2.1.10 | Auxiliary Transformer Datasheet | 410-BE-EL-DSH-0155 |  |  |  | 0.25323 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.2.1.11 | UPS and Battery Datasheet | 410-BE-EL-DSH-0156 |  |  |  | 0.25323 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.2.1.12 | Diesel Generator Datasheet | 410-BE-EL-DSH-0157 |  |  |  | 0.10129 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.38 | Material Requisition for Indoor Power and Lighting Distribution Panel | 410-DE-EL-MRE-0168 |  |  |  | 2.2791 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.39 | Material Requisition for Auxiliary Transformer | 410-DE-EL-MRE-0169 |  |  |  | 2.2791 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.40 | Material Requisition for PCC | 410-DE-EL-MRE-0170 |  |  |  | 0 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.4.41 | Material Requisition for MV Switchgear (CT, PT, Relay) | 410-DE-EL-MRE-0171 |  |  |  | 4.5581 | 100 | % | 100 | 100% | 100% | 0% | 40% | 0% | 60% | 100% | 40%
| 3.4.42 | Material Requisition for AC Cable | 410-DE-EL-MRE-0172 |  |  |  | 1.7726 | 100 | % | 100 | 100% | 100% | 0% | 10% | 0% | 90% | 100% | 10%
| 3.4.43 | Material Requisition for DC Cable | 410-DE-EL-MRE-0173 |  |  |  | 1.7726 | 100 | % | 100 | 100% | 100% | 0% | 30% | 0% | 70% | 100% | 30%
| 3.4.44 | Material Requisition for Earthing and Lightning | 410-DE-EL-MRE-0174 |  |  |  | 2.2791 | 100 | % | 100 | 100% | 100% | 0% | 40% | 0% | 60% | 100% | 40%
| 3.4.45 | Material Requisition for DC Connection (MC4) | 410-DE-EL-MRE-0175 |  |  |  | 1.7726 | 100 | % | 100 | 100% | 100% | 0% | 20% | 0% | 80% | 100% | 20%
| 3.4.46 | Material Requisition for Lighting System | 410-DE-EL-MRE-0176 |  |  |  | 2.2791 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.47 | Material Requisition for UPS and Battery | 410-DE-EL-MRE-0177 |  |  |  | 2.2791 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.4.48 | Material Requisition for Diesel Generator | 410-BE-EL-MRE-0186 |  |  |  | 2.0258 | 100 | % | 100 | 100% | 100% | 0% | 20% | 0% | 80% | 100% | 20%
| 3.2 | Civil |  |  |  |  | 57.2803 |  |  |  | 100% | 55.52% | -44.48% | -50.66% | 2.281% | 150.7% | 53.24% | -97.43%
| 3.3.1 | Topography of Field | 410-DE-CV-REP-0087 |  |  |  | 1.4181 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3.2 | Geotechnical Test Report | 410-DE-CV-REP-0088 |  |  |  | 1.4181 | 100 | % | 90 | 100% | 90% | -10% | 0% | 0% | 100% | 90% | -10%
| 3.3.3 | Ramming and Pull-Out Test Report | 410-DE-CV-REP-0089 |  |  |  | 1.4181 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.4 | Hydrology Study Report | 410-DE-CV-REP-0090 |  |  |  | 1.4181 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3.5 | Site Fence Detail Drawing | 410-DE-CV-DRW-0091 |  |  |  | 1.4181 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3.6 | Logistic Area | 410-DE-CV-DRW-0092 |  |  |  | 1.4181 | 100 | % | 75 | 100% | 75% | -25% | 0% | 0% | 100% | 75% | -25%
| 3.3.7 | Buildings Foundation & Structure Calculation | 410-DE-CV-CAL-0093 |  |  |  | 0 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| New | Swichgear Building Foundation & Structure Calculation | 410-DE-CV-CAL-0187 |  |  |  | 0.5571 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| New | Control Building Foundation & Structure Calculation | 410-DE-CV-CAL-0188 |  |  |  | 0.5571 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| New | Guard Building Foundation & Structure Calculation | 410-DE-CV-CAL-0189 |  |  |  | 0.5571 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.8 | Buildings Foundation & Structure Drawing | 410-DE-CV-DRW-0094 |  |  |  | 0 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| New | Swichgear Building Foundation & Structure Drawing | 410-DE-CV-DRW-0190 |  |  |  | 0.45581 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| New | Control Building Foundation & Structure Drawing | 410-DE-CV-DRW-0191 |  |  |  | 0.45581 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| New | Guard Building Foundation & Structure Drawing | 410-DE-CV-DRW-0192 |  |  |  | 0.45581 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.9 | Parking Foundation & Structure Detail Drawing | 410-DE-CV-DRW-0098 |  |  |  | 1.3168 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.10 | Power Plant Entrance Gate Drawing | 410-DE-CV-DRW-0099 |  |  |  | 1.3168 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.11 | Parking Architectural Drawing | 410-DE-CV-DRW-0100 |  |  |  | 1.4687 | 100 | % | 60 | 100% | 60% | -40% | 0% | 60% | 100% | 0% | -100%
| 3.3.12 | Landscaping Layout | 410-DE-CV-DRW-0101 |  |  |  | 1.4687 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.3.13 | Buildings Architectural Detail drawing | 410-DE-CV-DRW-0102 |  |  |  | 0 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| New | Swichgear Building Architectural Detail drawing | 410-DE-CV-DRW-0193 |  |  |  | 0.50646 | 100 | % | 75 | 100% | 75% | -25% | 0% | 0% | 100% | 75% | -25%
| New | Control Building Architectural Detail drawing | 410-DE-CV-DRW-0194 |  |  |  | 0.50646 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| New | Guard Building Architectural Detail drawing | 410-DE-CV-DRW-0195 |  |  |  | 0.50646 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3.14 | Fence MTO | 410-DE-CV-MTO-0103 |  |  |  | 1.2661 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3.15 | Site Grading and Leveling | 410-DE-CV-DRW-0104 |  |  |  | 1.4687 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3.16 | Drainage For Insite of Plant & Implementation Detail Drawing | 410-DE-CV-DRW-0105 |  |  |  | 1.4687 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3.17 | Flood Managmant For Outsite of Plant & Implementation Detail Drawing | 410-DE-CV-DRW-0106 |  |  |  | 1.4687 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3.18 | Internal Road Layout & Implementation Detail Drawing | 410-DE-CV-DRW-0107 |  |  |  | 1.4687 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3.19 | Access Road Layout & Implementation Detail Drawing | 410-DE-CV-DRW-0108 |  |  |  | 1.4687 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3.20 | MV Station Foundation Calculation | 410-DE-CV-CAL-0109 |  |  |  | 1.8232 | 100 | % | 75 | 100% | 75% | -25% | 0% | 0% | 100% | 75% | -25%
| 3.3.21 | MV Station Foundation Drawings | 410-DE-CV-DRW-0110 |  |  |  | 1.4687 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.3.22 | Auxiliary Transformer Foundation Detail Drawings | 410-DE-CV-DRW-0111 |  |  |  | 1.4687 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.23 | Calculation Report for Structure | 410-DE-CV-CAL-0112 |  |  |  | 1.8232 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.3.24 | Structure Detail Drawings | 410-DE-CV-DRW-0113 |  |  |  | 1.4687 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.3.25 | PV Structure Ramming Location Details Drawing (Stacking) | 410-DE-CV-DRW-0114 |  |  |  | 1.4687 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.26 | Solar Module Structure MTO | 410-DE-CV-MTO-0115 |  |  |  | 1.2661 | 100 | % | 75 | 100% | 75% | -25% | 0% | 0% | 100% | 75% | -25%
| 3.3.27 | Table UTM Point | 410-DE-CV-DRW-0116 |  |  |  | 1.4687 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.28 | Structure, Entrance Gate and Foundation of Building MTO | 410-DE-CV-MTO-0117 |  |  |  | 1.2661 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.29 | System Drainage Calculation | 410-DE-CV-CAL-0130 |  |  |  | 1.8232 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3.30 | Lighting Foundation Calculation | 410-DE-CV-CAL-0131 |  |  |  | 1.8232 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.31 | Lightning Foundation Calculation | 410-DE-CV-CAL-0132 |  |  |  | 1.8232 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.32 | Lightning Foundation Drawing | 410-DE-CV-DRW-0133 |  |  |  | 1.4181 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.33 | Lighting and CCTV Pole Calculation | 410-DE-CV-CAL-0134 |  |  |  | 1.8232 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.3.34 | Septic Tank Detail Drawing | 410-DE-CV-DRW-0135 |  |  |  | 1.4181 | 100 | % | 60 | 100% | 60% | -40% | 0% | 15% | 100% | 45% | -55%
| 3.3.35 | Water Tank Foundation Detail Drawing | 410-DE-CV-DRW-0136 |  |  |  | 1.4181 | 100 | % | 60 | 100% | 60% | -40% | 0% | 15% | 100% | 45% | -55%
| 3.3.36 | Calculation for Fence | 410-DE-CV-CAL-0137 |  |  |  | 1.4181 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3.37 | Material Requisition for Fence | 410-DE-CV-MRE-0167 |  |  |  | 3.5452 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.3 | Quality |  |  |  |  | 29.3745 |  |  |  | 20% | 26.25% | 6.25% | 0% | 4.5% | 20% | 21.75% | 1.75%
| 3.8.1 | Solar Panel Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0073 |  |  |  | 1.4687 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.8.2 | Inverter Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0074 |  |  |  | 1.4687 | 100 | % | 100 | 0% | 100% | 100% | 0% | 0% | 0% | 100% | 100%
| 3.8.3 | MV Station Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0075 |  |  |  | 1.4687 | 100 | % | 100 | 0% | 100% | 100% | 0% | 0% | 0% | 100% | 100%
| 3.8.4 | UPS Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0076 |  |  |  | 1.4687 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.8.5 | AUX Transformer Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0077 |  |  |  | 1.4687 | 100 | % | 90 | 0% | 90% | 90% | 0% | 90% | 0% | 0% | 0%
| 3.8.6 | Diesel Generator Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0078 |  |  |  | 1.4687 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.8.7 | Weather Station Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0079 |  |  |  | 1.4687 | 100 | % | 45 | 0% | 45% | 45% | 0% | 0% | 0% | 45% | 45%
| 3.8.8 | Solar Structure Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0080 |  |  |  | 1.4687 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.8.9 | SCADA and Monitoring System Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0081 |  |  |  | 1.4687 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.8.10 | Project O&M General Instructions | 410-DE-QA-REP-0083 |  |  |  | 1.4687 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.8.11 | Test Report of Solar Structure | 410-DE-QA-REP-0118 |  |  |  | 1.4687 | 100 | % | 90 | 100% | 90% | -10% | 0% | 0% | 100% | 90% | -10%
| 3.8.12 | Test Reports for PV Modules | 410-DE-QA-REP-0119 |  |  |  | 1.4687 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| 3.8.13 | Test Reports for Inverter | 410-DE-QA-REP-0120 |  |  |  | 1.4687 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.8.14 | Test Reports for MV Sation | 410-DE-QA-REP-0121 |  |  |  | 1.4687 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.8.15 | Test Reports for AC and DC Cables | 410-DE-QA-REP-0122 |  |  |  | 0 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| New | Test Reports for AC Cables | 410-DE-QA-REP-0196 |  |  |  | 0.73436 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| New | Test Reports for DC Cables | 410-DE-QA-REP-0197 |  |  |  | 0.73436 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.8.16 | Test Reports for Diesel Generators | 410-DE-QA-REP-0123 |  |  |  | 1.4687 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.8.17 | Test Reports for AUX Transformer | 410-DE-QA-REP-0124 |  |  |  | 1.4687 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.8.18 | Test Reports for Earthing and Ligthtning | 410-DE-QA-REP-0125 |  |  |  | 1.4687 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.8.19 | Test Reports for MV Switchgear (CT, PT, Relay, …) | 410-DE-QA-REP-0126 |  |  |  | 1.4687 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.8.20 | Test Reports for UPS and Battery | 410-DE-QA-REP-0127 |  |  |  | 1.4687 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.4 | Telecom |  |  |  |  | 15.5482 |  |  |  | 90.23% | 81.42% | -8.811% | 1.954% | 5.977% | 88.27% | 75.44% | -12.83%
| 3.2.2.13 | Monitoring System Technical Specification | 410-BE-TL-SPC-0010 |  |  |  | 0.40517 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.2.14 | Data Logger Technical Specification | 410-BE-TL-SPC-0011 |  |  |  | 0.40517 | 100 | % | 100 | 100% | 100% | 0% | 0% | 25% | 100% | 75% | -25%
| 3.2.2.15 | Weather Station Technical Specification | 410-BE-TL-SPC-0012 |  |  |  | 0.40517 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.2.16 | CCTV and NVR Technical Specification | 410-BE-TL-SPC-0014 |  |  |  | 0.40517 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.7.1 | CCTV System Block Diagram | 410-DE-TL-DRW-0054 |  |  |  | 0.96227 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.7.2 | CCTV System Arrangement & Layout | 410-DE-TL-DRW-0055 |  |  |  | 0.96227 | 100 | % | 60 | 100% | 60% | -40% | 0% | 15% | 100% | 45% | -55%
| 3.7.3 | CCTV Pole Detail Drawing, Switchboard, CAFU Details | 410-DE-TL-DRW-0056 |  |  |  | 1.1142 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.7.4 | CCTV System MTO | 410-DE-TL-MTO-0057 |  |  |  | 0.91162 | 100 | % | 90 | 100% | 90% | -10% | 0% | 0% | 100% | 90% | -10%
| 3.7.5 | SCADA System I/O List | 410-DE-TL-LST-0063 |  |  |  | 0.70904 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.7.6 | Monitoring System Overall Diagram | 410-DE-TL-DRW-0064 |  |  |  | 1.0129 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.7.7 | Telecommunication and Monitoring System MTO | 410-DE-TL-MTO-0065 |  |  |  | 0.96227 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.13 | Monitoring System Datasheet | 410-BE-TL-DSH-0158 |  |  |  | 0.35452 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.14 | Data Logger Datasheet | 410-BE-TL-DSH-0159 |  |  |  | 0.35452 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.15 | Weather Station Datasheet | 410-BE-TL-DSH-0160 |  |  |  | 0.15194 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.16 | CCTV and NVR Datasheet | 410-BE-TL-DSH-0161 |  |  |  | 0.35452 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.7.8 | Material Requisition forTelecommunication and Monitoring Cable | 410-DE-TL-MRE-0178 |  |  |  | 1.5194 | 100 | % | 45 | 0% | 45% | 45% | 0% | 0% | 0% | 45% | 45%
| 3.7.9 | Material Requisition forFiber Optics | 410-BE-TL-MRE-0179 |  |  |  | 1.5194 | 100 | % | 45 | 100% | 45% | -55% | 20% | 45% | 80% | 0% | -80%
| 3.7.10 | Material Requisition for CCTV and NVR | 410-DE-TL-MRE-0180 |  |  |  | 1.5194 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.7.11 | Material Requisition for Weather Station | 410-BE-TL-MRE-0185 |  |  |  | 1.5194 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.5 | Mechanical |  |  |  |  | 11.4459 |  |  |  | 100% | 64.73% | -35.27% | 0% | 0% | 100% | 64.73% | -35.27%
| 3.2.2.17 | HVAC Technical Specification | 410-BE-ME-SPC-0017 |  |  |  | 0.40517 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.2.2.18 | Piping Material, Plumbing Fittings, Pumps Technical Specification | 410-BE-ME-SPC-0018 |  |  |  | 0.40517 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.5.1 | Solar Panel Cleaning & Maintenance Procedures | 410-DE-ME-REP-0062 |  |  |  | 0.75969 | 100 | % | 60 | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
| 3.5.2 | HVAC Equipment Calculation | 410-DE-ME-CAL-0066 |  |  |  | 1.0129 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.5.3 | HVAC Equipment Layout for Building | 410-DE-ME-DRW-0067 |  |  |  | 0 | 100 | % | 0 | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
| New | HVAC Equipment Layout for Swichgear Building | 410-DE-ME-DRW-0198 |  |  |  | 0.33764 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| New | HVAC Equipment Layout for Control Building | 410-DE-ME-DRW-0199 |  |  |  | 0.33764 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| New | HVAC Equipment Layout for Guard Building | 410-DE-ME-DRW-0200 |  |  |  | 0.33764 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.5.4 | HVAC and Piping System MTO | 410-DE-ME-MTO-0068 |  |  |  | 0.96227 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.5.5 | Mechanical Drawing (Water Supply and Sewage Systems) | 410-DE-ME-DRW-0095 |  |  |  | 1.0129 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.2.2.19 | Septic Tank Technical Specification | 410-DE-ME-SPC-0096 |  |  |  | 0.20258 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.2.20 | Water Tank Technical Specification | 410-DE-ME-SPC-0097 |  |  |  | 0.20258 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.17 | HVAC Datasheet | 410-BE-ME-DSH-0162 |  |  |  | 0.35452 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.2.1.18 | Piping Material, Plumbing Fittings, Pumps Datasheet | 410-BE-ME-DSH-0163 |  |  |  | 0.35452 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.19 | Septic Tank Datasheet | 410-BE-ME-DSH-0164 |  |  |  | 0.35452 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.2.1.20 | Water Tank Datasheet | 410-BE-ME-DSH-0165 |  |  |  | 0.35452 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.5.6 | Material Requisition for Septic Tank | 410-BE-ME-MRE-0183 |  |  |  | 2.0258 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.5.7 | Material Requisition for Water Tank | 410-BE-ME-MRE-0184 |  |  |  | 2.0258 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.6 | Safety |  |  |  |  | 7.5462 |  |  |  | 69.8% | 73.26% | 3.456% | 0% | 1.51% | 69.8% | 71.74% | 1.946%
| 3.2.2.21 | Fire Alarm System Technical Specification | 410-BE-SF-SPC-0019 |  |  |  | 0.40517 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.6.1 | Fire Fighting Equipment Arrangement of MV Switchgear Buildings | 410-DE-SF-DRW-0069 |  |  |  | 0.96227 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.6.2 | Outdoor Fire Fighting Equipment & Shelter Arrangement | 410-DE-SF-DRW-0070 |  |  |  | 0.96227 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.6.3 | Fire Alarm System Layout and Block Diagram | 410-DE-SF-DRW-0071 |  |  |  | 0.96227 | 100 | % | 45 | 100% | 45% | -55% | 0% | 0% | 100% | 45% | -55%
| 3.6.4 | Fire and Safety and F & G System MTO | 410-DE-SF-MTO-0072 |  |  |  | 0.96227 | 100 | % | 90 | 100% | 90% | -10% | 0% | 0% | 100% | 90% | -10%
| 3.2.1.21 | Fire Alarm System Datasheet | 410-BE-SF-DSH-0166 |  |  |  | 0.25323 | 100 | % | 45 | 100% | 45% | -55% | 0% | 45% | 100% | 0% | -100%
| 3.6.5 | Material Requisition for Fire Alarm System | 410-DE-SF-MRE-0181 |  |  |  | 1.5194 | 100 | % | 45 | 0% | 45% | 45% | 0% | 0% | 0% | 45% | 45%
| 3.6.6 | Material Requisition for Fire Fighting Equipment Arrangement | 410-DE-SF-MRE-0182 |  |  |  | 0.75969 | 100 | % | 45 | 0% | 45% | 45% | 0% | 0% | 0% | 45% | 45%
| New | HSE Plan | 410-DE-SF-REP-0201 |  |  |  | 0.75969 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.7 | Project Management |  |  |  |  | 5.4697 |  |  |  | 76.67% | 74.07% | -2.593% | 76.67% | 0% |  | 74.07% | 74.07%
| 3.1.1 | Master Document List | 410-DE-PM-LST-0084 |  |  |  | 0.70904 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.1.2 | Time Schedule | 410-DE-PM-REP-0085 |  |  |  | 1.1649 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.1.3 | Cash Flow | 410-DE-PM-CAF-0086 |  |  |  | 0.75969 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.1.4 | Monthly Report 410-M-001 | 410-DE-PM-REP-0138 |  |  |  | 0.35452 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.1.5 | Monthly Report 410-M-002 | 410-DE-PM-REP-0139 |  |  |  | 0.35452 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.1.6 | Monthly Report 410-M-003 | 410-DE-PM-REP-0140 |  |  |  | 0.35452 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.1.7 | Monthly Report 410-M-004 | 410-DE-PM-REP-0141 |  |  |  | 0.35452 | 100 | % | 100 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
| 3.1.8 | Monthly Report 410-M-005 | 410-DE-PM-REP-0142 |  |  |  | 0.35452 | 100 | % | 0 | 40% | 0% | -40% | 40% | 0% | 0% | 0% | 0%
| 3.1.9 | Monthly Report 410-M-006 | 410-DE-PM-REP-0143 |  |  |  | 0.35452 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.1.10 | Monthly Report 410-M-007 | 410-DE-PM-REP-0144 |  |  |  | 0.35452 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3.1.11 | Monthly Report 410-M-008 | 410-DE-PM-REP-0145 |  |  |  | 0.35452 | 100 | % | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
218 | 4 | تامین و حمل کالا تجهیزات |  | 195 روز | 1404/11/30 | 1405/6/15 | 7000 |  |  |  | 53.45% | 30.04% | -23.41% | 1.28% | 4.246% | 52.17% | 25.79% | -26.38%
219 | 4.1 | خرید و حمل داخلی |  | 178 روز | 1404/12/17 | 1405/6/15 | 4171.38 |  |  |  | 21.88% | 44.3% | 22.42% | 2.15% | 7.13% | 19.73% | 37.17% | 17.44%
220 | 4.1.1 | خرید مصالح و تجهیز کارگاه |  | 75 روز | 1404/12/17 | 1405/3/5 | 547.34 |  |  |  | 100% | 50.21% | -49.79% | 0% | -49.79% | 100% | 100% | 0%
221 | 4.1.1.1 | مصالح ساختمانی و ملزومات عمرانی |  | 30 روز | 1404/12/17 | 1405/1/22 | 408.17 | PSR-Local |  |  | 100% | 41.5% | -58.5% | 0% | -58.5% | 100% | 100% | 0%
222 | 4.1.1.2 | مصالح ،تجهیزات و ملزومات برقی ساختمان ها |  | 30 روز | 1405/2/7 | 1405/3/5 | 33.73 | PSR-Local |  |  | 100% | 0% | -100% | 0% | -100% | 100% | 100% | 0%
223 | 4.1.1.3 | تانک سپتیک و دو مخزن 10 هزار لیتری سه لایه |  | 5 روز | 1405/1/10 | 1405/1/14 | 8.43 | PSR-Local |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
224 | 4.1.1.4 | کلیه تجهیزات و ملزومات اداری |  | 15 روز | 1404/12/17 | 1405/1/7 | 16.87 | PSR-Local |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
225 | 4.1.1.5 | سایر خرید تجهیز کارگاه |  | 15 روز | 1405/1/8 | 1405/1/22 | 80.14 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
226 | 4.1.2 | فنس پیرامونی |  | 20 روز | 1405/3/1 | 1405/3/20 | 185.53 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
227 | 4.1.2.1 | سفارش گذاری فنس پیرامونی |  | 3 روز | 1405/3/1 | 1405/3/3 | 9.28 | PSR-Local |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
228 | 4.1.2.2 | ساخت و بازرسی فنس پیرامونی |  | 10 روز | 1405/3/4 | 1405/3/13 | 148.42 | PSR-Local |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
229 | 4.1.2.3 | حمل فنس پیرامونی |  | 7 روز | 1405/3/14 | 1405/3/20 | 27.83 | PSR-Local |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
230 | 4.1.3 | تابلو های توزیع داخلی و روشنایی |  | 28 روز | 1405/4/24 | 1405/5/20 | 489.62 |  |  |  | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0%
231 | 4.1.3.1 | سفارش گذاری تابلو های توزیع داخلی و روشنایی |  | 1 روز | 1405/4/24 | 1405/4/24 | 24.48 | PSR-Local |  |  | 0% | 20% | 20% | 0% | 20% | 0% | 0% | 0%
232 | 4.1.3.2 | ساخت و بازرسی تابلو های توزیع داخلی و روشنایی |  | 20 روز | 1405/4/25 | 1405/5/13 | 391.7 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
233 | 4.1.3.3 | حمل تابلو های توزیع داخلی و روشنایی |  | 7 روز | 1405/5/14 | 1405/5/20 | 73.44 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
234 | 4.1.4 | ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 30 روز | 1405/4/23 | 1405/5/21 | 78.81 |  |  |  | 0% | 29% | 29% | 0% | 29% | 0% | 0% | 0%
235 | 4.1.4.1 | سفارش گذاری ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 3 روز | 1405/4/23 | 1405/4/25 | 3.94 | PSR-Local |  |  | 0% | 100% | 100% | 0% | 100% | 0% | 0% | 0%
236 | 4.1.4.2 | ساخت و بازرسی ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 25 روز | 1405/4/26 | 1405/5/19 | 63.05 | PSR-Local |  |  | 0% | 30% | 30% | 0% | 30% | 0% | 0% | 0%
237 | 4.1.4.3 | حمل ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 7 روز | 1405/5/15 | 1405/5/21 | 11.82 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
238 | 4.1.5 | تابلوهای پست سوییچگیر |  | 80 روز | 1405/3/13 | 1405/5/30 | 244.81 |  |  |  | 26.6% | 0% | -26.6% | 9.6% | 0% | 17% | 0% | -17%
239 | 4.1.5.1 | سفارش گذاری تابلوهای پست سوییچگیر |  | 5 روز | 1405/3/13 | 1405/3/17 | 12.24 | PSR-Local |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
240 | 4.1.5.2 | ساخت و بازرسی تابلوهای پست سوییچگیر |  | 60 روز | 1405/3/18 | 1405/5/15 | 195.85 | PSR-Local |  |  | 27% | 0% | -27% | 12% | 0% | 15% | 0% | -15%
241 | 4.1.5.3 | حمل تابلوهای پست سوییچگیر |  | 15 روز | 1405/5/16 | 1405/5/30 | 36.72 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
242 | 4.1.6 | ct& pt |  | 28 روز | 1405/5/4 | 1405/5/31 | 244.81 |  |  |  | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0%
243 | 4.1.6.1 | سفارش گذاری ct& pt |  | 1 روز | 1405/5/4 | 1405/5/4 | 12.24 | PSR-Local |  |  | 0% | 20% | 20% | 0% | 20% | 0% | 0% | 0%
244 | 4.1.6.2 | ساخت و بازرسی ct& pt |  | 20 روز | 1405/5/5 | 1405/5/24 | 195.85 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
245 | 4.1.6.3 | حمل ct& pt |  | 7 روز | 1405/5/25 | 1405/5/31 | 36.72 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
246 | 4.1.7 | AC/LV و AC/MV کابل های |  | 50 روز | 1405/3/28 | 1405/5/15 | 768.4 |  |  |  | 4.3% | 77% | 72.7% | 4.3% | 74.5% | 0% | 2.5% | 2.5%
247 | 4.1.7.1 | AC/LV و AC/MV سفارش گذاری کابل های |  | 7 روز | 1405/3/28 | 1405/4/3 | 38.42 | PSR-Local |  |  | 86% | 100% | 14% | 86% | 50% | 0% | 50% | 50%
248 | 4.1.7.2 | AC/LV و AC/MV ساخت و بازرسی کابل های |  | 36 روز | 1405/4/4 | 1405/5/8 | 614.72 | PSR-Local |  |  | 0% | 90% | 90% | 0% | 90% | 0% | 0% | 0%
249 | 4.1.7.3 | AC/LV و AC/MV حمل کابل های |  | 10 روز | 1405/5/6 | 1405/5/15 | 115.26 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
250 | 4.1.8 | DC کابل های |  | 20 روز | 1405/4/14 | 1405/5/2 | 372.24 |  |  |  | 0% | 85% | 85% | 0% | -11.25% | 0% | 96.25% | 96.25%
251 | 4.1.8.1 | DC سفارش گذاری کابل های |  | 3 روز | 1405/4/14 | 1405/4/16 | 18.61 | PSR-Local |  |  | 0% | 100% | 100% | 0% | 0% | 0% | 100% | 100%
252 | 4.1.8.2 | DC ساخت و بازرسی کابل های |  | 10 روز | 1405/4/17 | 1405/4/26 | 297.79 | PSR-Local |  |  | 0% | 100% | 100% | 0% | 0% | 0% | 100% | 100%
253 | 4.1.8.3 | DC حمل کابل های |  | 7 روز | 1405/4/27 | 1405/5/2 | 55.84 | PSR-Local |  |  | 0% | 0% | 0% | 0% | -75% | 0% | 75% | 75%
254 | 4.1.9 | کابل های ارتباطی |  | 20 روز | 1405/5/11 | 1405/5/30 | 91.84 |  |  |  | 0% | 0.9996% | 0.9996% | 0% | 0.9996% | 0% | 0% | 0%
255 | 4.1.9.1 | سفارش گذاری کابل های ارتباطی |  | 3 روز | 1405/5/11 | 1405/5/13 | 4.59 | PSR-Local |  |  | 0% | 20% | 20% | 0% | 20% | 0% | 0% | 0%
256 | 4.1.9.2 | ساخت و بازرسی کابل های ارتباطی |  | 10 روز | 1405/5/14 | 1405/5/23 | 73.47 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
257 | 4.1.9.3 | حمل کابل های ارتباطی |  | 7 روز | 1405/5/24 | 1405/5/30 | 13.78 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
258 | 4.1.10 | Fiber Optics (انتقال دیتا داخلی نیروگاه) |  | 50 روز | 1405/4/7 | 1405/5/25 | 91.84 |  |  |  | 0% | 0.9996% | 0.9996% | 0% | 0.9996% | 0% | 0% | 0%
259 | 4.1.10.1 | Fiber Optics سفارش گذاری (انتقال دیتا داخلی نیروگاه) |  | 10 روز | 1405/4/7 | 1405/4/16 | 4.59 | PSR-Local |  |  | 0% | 20% | 20% | 0% | 20% | 0% | 0% | 0%
260 | 4.1.10.2 | Fiber Optics ساخت و بازرسی (انتقال دیتا داخلی نیروگاه) |  | 30 روز | 1405/4/17 | 1405/5/15 | 73.47 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
261 | 4.1.10.3 | Fiber Optics حمل (انتقال دیتا داخلی نیروگاه) |  | 10 روز | 1405/5/16 | 1405/5/25 | 13.78 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
262 | 4.1.11 | کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 42 روز | 1405/4/5 | 1405/5/15 | 209.62 |  |  |  | 0% | 0.9999% | 0.9999% | 0% | 0.9999% | 0% | 0% | 0%
263 | 4.1.11.1 | سفارش گذاری کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 5 روز | 1405/4/5 | 1405/4/9 | 10.48 | PSR-Local |  |  | 0% | 20% | 20% | 0% | 20% | 0% | 0% | 0%
264 | 4.1.11.2 | ساخت و بازرسی کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 30 روز | 1405/4/10 | 1405/5/8 | 167.7 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
265 | 4.1.11.3 | حمل کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 7 روز | 1405/5/9 | 1405/5/15 | 31.44 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
266 | 4.1.12 | MC4 |  | 32 روز | 1405/4/15 | 1405/5/15 | 440.21 |  |  |  | 0% | 100% | 100% | 0% | 0% | 0% | 100% | 100%
267 | 4.1.12.1 | MC4 سفارش گذاری |  | 5 روز | 1405/4/15 | 1405/4/19 | 22.01 | PSR-Local |  |  | 0% | 100% | 100% | 0% | 0% | 0% | 100% | 100%
268 | 4.1.12.2 | MC4 ساخت و بازرسی |  | 20 روز | 1405/4/20 | 1405/5/8 | 352.17 | PSR-Local |  |  | 0% | 100% | 100% | 0% | 0% | 0% | 100% | 100%
269 | 4.1.12.3 | MC4 حمل |  | 7 روز | 1405/5/9 | 1405/5/15 | 66.03 | PSR-Local |  |  | 0% | 100% | 100% | 0% | 0% | 0% | 100% | 100%
270 | 4.1.13 | و تجهیزات جانبیCCTV سیستم |  | 52 روز | 1405/3/24 | 1405/5/13 | 284.53 |  |  |  | 12.2% | 1% | -11.2% | 10.05% | 1% | 2.15% | 0% | -2.15%
271 | 4.1.13.1 | و تجهیزات جانبیCCTV سفارش گذاری سیستم |  | 7 روز | 1405/3/24 | 1405/3/30 | 14.23 | PSR-Local |  |  | 100% | 20% | -80% | 57% | 20% | 43% | 0% | -43%
272 | 4.1.13.2 | و تجهیزات جانبیCCTV ساخت و بازرسی سیستم |  | 35 روز | 1405/3/31 | 1405/5/3 | 227.62 | PSR-Local |  |  | 9% | 0% | -9% | 9% | 0% | 0% | 0% | 0%
273 | 4.1.13.3 | و تجهیزات جانبیCCTV حمل سیستم |  | 10 روز | 1405/5/4 | 1405/5/13 | 42.68 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
274 | 4.1.14 | تجهیزات سیستم روشنایی |  | 55 روز | 1405/3/25 | 1405/5/17 | 38.48 |  |  |  | 12.99% | 0% | -12.99% | 10.99% | 0% | 2% | 0% | -2%
275 | 4.1.14.1 | سفارش گذاری تجهیزات سیستم روشنایی |  | 5 روز | 1405/3/25 | 1405/3/29 | 1.92 | PSR-Local |  |  | 100% | 0% | -100% | 60% | 0% | 40% | 0% | -40%
276 | 4.1.14.2 | ساخت و بازرسی تجهیزات سیستم روشنایی |  | 40 روز | 1405/3/30 | 1405/5/7 | 30.79 | PSR-Local |  |  | 10% | 0% | -10% | 10% | 0% | 0% | 0% | 0%
277 | 4.1.14.3 | حمل تجهیزات سیستم روشنایی |  | 10 روز | 1405/5/8 | 1405/5/17 | 5.77 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
278 | 4.1.15 | UPS سیستم |  | 84 روز | 1405/2/25 | 1405/5/15 | 39.87 |  |  |  | 85% | 0% | -85% | 0% | 0% | 85% | 0% | -85%
279 | 4.1.15.1 | UPS سفارش گذاری سیستم |  | 10 روز | 1405/2/25 | 1405/3/3 | 1.99 | PSR-Local |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
280 | 4.1.15.2 | UPS خرید سیستم |  | 20 روز | 1405/3/4 | 1405/3/23 | 31.9 | PSR-Local |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
281 | 4.1.15.3 | UPS حمل سیستم |  | 7 روز | 1405/5/9 | 1405/5/15 | 5.98 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
282 | 4.1.16 | سیستم اعلان حریق و تجهیزات جانبی |  | 16 روز | 1405/5/15 | 1405/5/30 | 5.86 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
283 | 4.1.16.1 | سفارش گذاری سیستم اعلان حریق و تجهیزات جانبی |  | 2 روز | 1405/5/15 | 1405/5/16 | 0.29 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
284 | 4.1.16.2 | ساخت و بازرسی سیستم اعلان حریق و تجهیزات جانبی |  | 7 روز | 1405/5/17 | 1405/5/23 | 4.69 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
285 | 4.1.16.3 | حمل سیستم اعلان حریق و تجهیزات جانبی |  | 7 روز | 1405/5/24 | 1405/5/30 | 0.88 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
286 | 4.1.17 | سیستم اطفا حریق و تجهیزات جانبی |  | 20 روز | 1405/5/1 | 1405/5/20 | 17.6 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
287 | 4.1.17.1 | سفارش گذاری سیستم اطفا حریق و تجهیزات جانبی |  | 3 روز | 1405/5/1 | 1405/5/3 | 0.88 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
288 | 4.1.17.2 | ساخت و بازرسی سیستم اطفا حریق و تجهیزات جانبی |  | 10 روز | 1405/5/4 | 1405/5/13 | 14.08 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
289 | 4.1.17.3 | حمل سیستم اطفا حریق و تجهیزات جانبی |  | 7 روز | 1405/5/14 | 1405/5/20 | 2.64 | PSR-Local |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
290 | 4.1.18 | ایستگاه هواشناسی و سنسورها |  | 20 روز | 1405/3/8 | 1405/3/27 | 7.92 |  |  |  | 100% | 29.03% | -70.97% | 2.1% | 29.03% | 97.9% | 0% | -97.9%
291 | 4.1.18.1 | سفارش گذاری ایستگاه هواشناسی و سنسورها |  | 3 روز | 1405/3/8 | 1405/3/10 | 0.4 | PSR-Local |  |  | 100% | 100% | 0% | 0% | 100% | 100% | 0% | -100%
292 | 4.1.18.2 | ساخت و بازرسی ایستگاه هواشناسی و سنسورها |  | 10 روز | 1405/3/11 | 1405/3/20 | 6.33 | PSR-Local |  |  | 100% | 30% | -70% | 0% | 30% | 100% | 0% | -100%
293 | 4.1.18.3 | حمل ایستگاه هواشناسی و سنسورها |  | 7 روز | 1405/3/21 | 1405/3/27 | 1.19 | PSR-Local |  |  | 100% | 0% | -100% | 14% | 0% | 86% | 0% | -86%
294 | 4.1.19 | لوازم یدکی |  | 75 روز | 1405/4/3 | 1405/6/15 | 12.05 |  |  |  | 0% | 0% | 0% | 0% | -1% | 0% | 1% | 1%
295 | 4.1.19.1 | لوازم یدکی |  | 75 روز | 1405/4/3 | 1405/6/15 | 12.05 | PSR-Local |  |  | 0% | 0% | 0% | 0% | -1% | 0% | 1% | 1%
296 | 4.2 | خرید خارجی، حمل بین المللی و ترخیص |  | 148 روز | 1404/11/30 | 1405/4/30 | 2828.62 |  |  |  | 100% | 9% | -91% | 0% | -6.364e-05% | 100% | 9% | -91%
297 | 4.2.1 | خرید سازه های نگهدارنده پنل ها و اینورترها |  | 82 روز | 1404/12/4 | 1405/2/30 | 2828.62 |  |  |  | 100% | 9% | -91% | 0% | -6.364e-05% | 100% | 9% | -91%
298 | 4.2.1.1 | استعلام قیمت و سفارش گذاری سازه های نگهدارنده |  | 5 روز | 1404/12/4 | 1404/12/8 | 424.29 | PSR-Local |  |  | 100% | 60% | -40% | 0% | 0% | 100% | 60% | -40%
299 | 4.2.1.2 | ساخت سازه های نگهدارنده و بازرسی قبل حمل |  | 20 روز | 1404/12/9 | 1404/12/28 | 1272.88 | PSR-Local |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
300 | 4.2.1.3 | حمل خارجی سازه های نگهدارنده |  | 35 روز | 1405/1/5 | 1405/2/8 | 282.86 | PSR-Local |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
301 | 4.2.1.4 | ترخیص سازه های نگهدارنده |  | 15 روز | 1405/2/9 | 1405/2/23 | 141.43 | PSR-Local |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
302 | 4.2.1.5 | حمل داخلی سازه های نگهدارنده و تحویل در سایت |  | 7 روز | 1405/2/24 | 1405/2/30 | 707.16 | PSR-Local |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
303 | 4.2.2 | خرید پنل های خورشیدی |  | 105 روز | 1404/11/30 | 1405/3/18 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
304 | 4.2.2.1 | استعلام قیمت و ثبت سفارش پنل های خورشیدی |  | 5 روز | 1404/11/30 | 1404/12/4 | 0 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
305 | 4.2.2.2 | ساخت پنل های خورشیدی و بازرسی قبل حمل |  | 30 روز | 1404/12/9 | 1405/1/14 | 0 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
306 | 4.2.2.3 | حمل خارجی پنل های خورشیدی |  | 45 روز | 1405/1/15 | 1405/2/28 | 0 |  |  |  | 100% | 70% | -30% | 0% | 0% | 100% | 70% | -30%
307 | 4.2.2.4 | ترخیص پنل های خورشیدی |  | 14 روز | 1405/2/29 | 1405/3/11 | 0 |  |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
308 | 4.2.2.5 | حمل داخلی پنل های خورشیدی و تحویل در سایت |  | 7 روز | 1405/3/12 | 1405/3/18 | 0 |  |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
309 | 4.2.3 | خرید اینورترهای خورشیدی |  | 148 روز | 1404/11/30 | 1405/4/30 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
310 | 4.2.3.1 | استعلام قیمت و ثبت سفارش اینورترهای خورشیدی |  | 7 روز | 1404/11/30 | 1404/12/6 | 0 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
311 | 4.2.3.2 | ساخت اینورترهای خورشیدی و بازرسی قبل حمل |  | 73 روز | 1404/12/9 | 1405/2/26 | 0 |  |  |  | 100% | 95% | -5% | 0% | 0% | 100% | 95% | -5%
312 | 4.2.3.3 | حمل خارجی اینورترهای خورشیدی |  | 45 روز | 1405/2/27 | 1405/4/9 | 0 |  |  |  | 84% | 0% | -84% | 15% | 0% | 69% | 0% | -69%
313 | 4.2.3.4 | ترخیص اینورترهای خورشیدی |  | 14 روز | 1405/4/10 | 1405/4/23 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
314 | 4.2.3.5 | حمل داخلی اینورترهای خورشیدی و تحویل در سایت |  | 7 روز | 1405/4/24 | 1405/4/30 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
315 | 4.2.4 | خرید MV Station |  | 148 روز | 1404/11/30 | 1405/4/30 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
316 | 4.2.4.1 | استعلام قیمت و ثبت سفارش MV Station |  | 7 روز | 1404/11/30 | 1404/12/6 | 0 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
317 | 4.2.4.2 | ساخت MV Station و بازرسی قبل حمل |  | 73 روز | 1404/12/9 | 1405/2/26 | 0 |  |  |  | 100% | 55% | -45% | 0% | 5% | 100% | 50% | -50%
318 | 4.2.4.3 | حمل خارجی MV Station |  | 45 روز | 1405/2/27 | 1405/4/9 | 0 |  |  |  | 84% | 0% | -84% | 15% | 0% | 69% | 0% | -69%
319 | 4.2.4.4 | ترخیص MV Station |  | 14 روز | 1405/4/10 | 1405/4/23 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
320 | 4.2.4.5 | حمل داخلی MV Station و تحویل در سایت |  | 7 روز | 1405/4/24 | 1405/4/30 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
321 | 5 | عملیات اجرایی |  | 154 روز | 1405/1/15 | 1405/6/13 | 2612 |  |  |  | 19.79% | 4.108% | -15.68% | 3.89% | 0.1979% | 15.9% | 3.91% | -11.99%
322 | 5.1 | تجهیز کارگاه |  | 14 روز | 1405/1/15 | 1405/1/28 | 22.32 |  |  |  | 100% | 100% | 0% | 0% | 0.46% | 100% | 99.54% | -0.46%
323 | 5.1.1 | عملیات اجرایی |  | 14 روز | 1405/1/15 | 1405/1/28 | 21.42 |  |  |  | 100% | 100% | 0% | 0% | 0.46% | 100% | 99.54% | -0.46%
324 | 5.1.1.1 | تانک سپتیک و دو مخزن 10 هزار لیتری سه لایه |  | 6 روز | 1405/1/15 | 1405/1/20 | 2.64 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
|  | باراندازی ، زیرسازی و نصب مخازن 10 هزار لیتری |  |  |  |  | 2.244 | 2 | عدد | 2 | 100% | 100% | 0% |  |  | 100% | 100%
|  | باراندازی ، زیرسازی و نصب مخزن سپتیک |  |  |  |  | 0.396 | 1 | عدد | 1 | 100% | 100% | 0% |  |  | 100% | 100%
325 | 5.1.1.2 | کانکس نگهبانی |  | 3 روز | 1405/1/21 | 1405/1/23 | 18.68 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
|  | باراندازی ، اجرای فونداسیون و نصب کانکس نگهبانی |  |  |  |  | 18.68 | 1 | عدد | 1 | 100% | 100% | 0% |  |  | 100% | 100%
326 | 5.1.1.3 | تجهیز کارگاه دستگاه نظارت و کارفرما |  | 5 روز | 1405/1/24 | 1405/1/28 | 0.1 |  |  |  | 100% | 100% | 0% | 0% | 15% | 100% | 85% | -15%
|  | اجرای تجهیز کارگاه دستگاه نظارت و کارفرما |  |  |  |  | 0.1 | 1 | ست | 1 | 100% | 100% | 0% |  |  | 100% | 85% | -15%
|  | تجهیز کارگاه پیمانکار |  | 5 روز | 1405/1/24 | 1405/1/28 | 0.9 |  |  |  | 100% | 100% | 0%
|  | تسطیح و شن ریزی محوطه تجهیز کارگاه |  |  |  |  | 0.03704 | 1400 | متر مربع | 1400 | 100% | 100% | 0% |  |  | 100% | 100%
|  | استقرار کانکس تیم مهندسی و اجرایی |  |  |  |  | 0.03704 | 2 | عدد | 2 | 100% | 100% | 0% |  |  | 100% | 100%
|  | اجرای سرویس بهداشتی |  |  |  |  | 0.03704 | 2 | عدد | 2 | 100% | 100% | 0% |  |  | 100% | 100%
|  | تامین خودرو |  |  |  |  | 0.60368 | 1 | عدد | 1 | 100% | 100% | 0% |  |  | 100% | 100%
|  | استقرار ملزومات اداری و پشتیبانی |  |  |  |  | 0.03704 | 1 | ست | 1 | 100% | 100% | 0% |  |  | 100% | 100%
|  | استقرار تجهیزات آشپزخانه |  |  |  |  | 0.03704 | 1 | ست | 1 | 100% | 100% | 0% |  |  | 100% | 100%
|  | استقرار سیستم سرمایش و گرمایش کانکس ها |  |  |  |  | 0.03704 | 5 | عدد | 5 | 100% | 100% | 0% |  |  | 100% | 100%
|  | تامین آب شرب |  |  |  |  | 0.03704 | 1 | عدد | 1 | 100% | 100% | 0% |  |  | 100% | 100%
|  | تامین موتور برق |  |  |  |  | 0.03704 | 4 | عدد | 4 | 100% | 100% | 0% |  |  | 100% | 100%
327 | 5.2 | اجرای جاده دسترسی تا جاده اصلی |  | 8 روز | 1405/1/21 | 1405/1/28 | 73.06 |  |  |  | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
|  | اجرای جاده دسترسی تا جاده اصلی | 0 | 8 روز | 1405/1/21 | 1405/1/28 | 73.06 | 0 | 0 | 0 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
|  | اجرای جاده دسترسی تا جاده اصلی | 0 | 8 روز | 1405/1/21 | 1405/1/28 | 73.06 | 0 | 0 | 0 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
328 | 5.2.1 | زیرسازی |  | 6 روز | 1405/1/21 | 1405/1/26 | 36.53 | 1.5 | کیلومتر | 1.5 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
329 | 5.2.2 | شن ریزی |  | 2 روز | 1405/1/27 | 1405/1/28 | 36.53 | 1.5 | کیلومتر | 1.5 | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0%
330 | 5.3 | عملیات عمرانی |  | 131 روز | 1405/2/1 | 1405/6/7 | 240.88 |  |  |  | 39.91% | 4.948% | -34.96% | 10.12% | 2.128% | 29.79% | 2.82% | -26.97%
331 | 5.3.1 | عملیات دسترسی و آماده سازی سایت |  | 128 روز | 1405/2/1 | 1405/6/4 | 17.6 |  |  |  | 55% | 37.71% | -17.29% | 0% | 3.614% | 55% | 34.1% | -20.9%
332 | 5.3.1.1 | تسطیح و تحکیم زمین |  | 20 روز | 1405/2/1 | 1405/2/20 | 9.68 |  |  |  | 100% | 68.57% | -31.43% | 0% | 6.571% | 100% | 62% | -38%
|  | پاکسازی زمین از نخاله و گیاهان |  |  |  |  | 3.2267 | 280000 | متر مربع | 192000 | 100% | 68.57% | -31.43% | 0% | 6.571% | 100% | 62% | -38%
|  | خاکبرداری |  |  |  |  | 3.2267 | 280000 | متر مربع | 192000 | 100% | 68.57% | -31.43% | 0% | 6.571% | 100% | 62% | -38%
|  | تسطیح و رگلاژ نهایی |  |  |  |  | 3.2267 | 280000 | متر مربع | 192000 | 100% | 68.57% | -31.43% | 0% | 6.571% | 100% | 62% | -38%
333 | 5.3.1.2 | اجرای گیت ورودی |  | 15 روز | 1405/5/14 | 1405/5/28 | 4.4 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | اجرای ستون های دوطرفه |  |  |  |  | 2.2 | 2 | عدد |  |  | 0% | 0%
|  | اجرای گیت |  |  |  |  | 2.2 | 1 | ست |  |  | 0% | 0%
334 | 5.3.1.3 | احداث پارکینگ مسقف |  | 7 روز | 1405/5/29 | 1405/6/4 | 3.52 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | اجرای سازه پارکینگ |  |  |  |  | 1.76 | 1 | عدد |  |  | 0% | 0%
|  | اجرای سقف پارکینگ |  |  |  |  | 1.76 | 1 | عدد |  |  | 0% | 0%
335 | 5.3.2 | اجرای سیستم زهکشی |  | 40 روز | 1405/3/7 | 1405/4/15 | 38.73 |  |  |  | 68% | 0% | -68% | 18% | 0% | 50% | 0% | -50%
336 | 5.3.2.1 | اجرای سیستم زهکشی |  | 40 روز | 1405/3/7 | 1405/4/15 | 38.73 |  |  |  | 68% | 0% | -68% | 18% | 0% | 50% | 0% | -50%
|  | زهکشی و کنترل آبهای سطحی |  |  |  |  | 38.73 | 3000 | متر |  | 68% | 0% | -68% | 18% | 0% | 50% | 0% | -50%
337 | 5.3.3 | اجرای فنس پیرامونی |  | 55 روز | 1405/3/1 | 1405/4/24 | 63.37 |  |  |  | 42.25% | 8.332% | -33.92% | 18.33% | 7.082% | 23.92% | 1.25% | -22.67%
338 | 5.3.3.1 | اجرای فونداسیون و پایه فنس |  | 24 روز | 1405/3/1 | 1405/3/24 | 5.28 |  |  |  | 100% | 100% | 0% | 0% | 85% | 100% | 15% | -85%
|  | نقشه برداری و تعیین خطوط مبنا |  |  |  |  | 1.76 | 850 | عدد | 850 |  | 100% | 100%
|  | تسطیح و زیرسازی پایه های فنس |  |  |  |  | 1.76 | 850 | عدد | 850 |  | 100% | 100%
|  | چاله کنی پایه ها |  |  |  |  | 1.76 | 850 | عدد | 850 |  | 100% | 100%
339 | 5.3.3.2 | اجرای فنس |  | 35 روز | 1405/3/21 | 1405/4/24 | 58.09 |  |  |  | 37% | 0% | -37% | 20% | 0% | 17% | 0% | -17%
|  | اجرای فونداسیون و نصب پایه ها |  |  |  |  | 19.3633 | 850 | عدد |  |  |  | 0%
|  | نصب فنس و متعلقات |  |  |  |  | 19.3633 | 4260 | متر مربع |  |  | 0% | 0%
|  | نصب سیم خاردار |  |  |  |  | 19.3633 | 4260 | متر مربع |  |  | 0% | 0%
340 | 5.3.4 | اجرای فونداسیون MV Station |  | 33 روز | 1405/4/14 | 1405/5/15 | 2 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
341 | 5.3.4.1 | گودبرداری فونداسیون |  | 3 روز | 1405/4/14 | 1405/4/16 | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | گودبرداری |  |  |  |  | 0.5 | 50 | متر مکعب |  |  | 0% | 0%
|  | اجرای آرماتوربندی در صورت نیاز و قالب بندی |  |  |  |  | 0.5 | 2500 | کیلوگرم |  |  | 0% | 0%
342 | 5.3.4.2 | بتن ریزی فونداسیون |  | 30 روز | 1405/4/17 | 1405/5/15 | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | بتن ریزی |  |  |  |  | 1 | 25 | متر مکعب |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
343 | 5.3.5 | ساختمان پست سوییچگیر |  | 123 روز | 1405/2/6 | 1405/6/4 | 47.84 |  |  |  | 35.6% | 0% | -35.6% | 5.01% | 0% | 30.59% | 0% | -30.59%
344 | 5.3.5.1 | اجرای فونداسیون ساختمان پست سوییچگیر |  | 28 روز | 1405/2/6 | 1405/3/2 | 6.65 |  |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
|  | گودبرداری |  |  |  |  | 2.2167 | 180 | متر مکعب |  |  | 0% | 0%
|  | آرماتوربندی و قالب بندی |  |  |  |  | 2.2167 | 5000 | کیلوگرم |  |  | 0% | 0%
|  | بتن ریزی |  |  |  |  | 2.2167 | 40 | متر مکعب |  |  | 0% | 0%
345 | 5.3.5.2 | سفت کاری ساختمان پست سوییچگیر |  | 60 روز | 1405/3/3 | 1405/4/31 | 19.96 |  |  |  | 52% | 0% | -52% | 12% | 0% | 40% | 0% | -40%
|  | دیوار چینی |  |  |  |  | 9.98 | 200 | متر مربع |  |  | 0% | 0%
|  | اجرای سقف |  |  |  |  | 9.98 | 100 | متر مربع |  |  | 0% | 0%
346 | 5.3.5.3 | اجرای تاسیسات ساختمان پست سوییچگیر |  | 10 روز | 1405/5/1 | 1405/5/10 | 4.44 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | اجرای تاسیسات مکانیکی |  |  |  |  | 2.22 | 1 | ست |  |  | 0% | 0%
|  | اجرای تاسیسات برقی |  |  |  |  | 2.22 | 1 | ست |  |  | 0% | 0%
347 | 5.3.5.4 | نازک کاری ساختمان پست سوییچگیر |  | 10 روز | 1405/5/11 | 1405/5/20 | 2.22 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | تکمیل گچ کاری |  |  |  |  | 1.11 | 300 | متر مربع |  |  | 0% | 0%
|  | تکمیل سنگ کاری |  |  |  |  | 1.11 | 10 | متر مربع |  |  | 0% | 0%
348 | 5.3.5.5 | اجرای نمای ساختمان پست سوییچگیر |  | 10 روز | 1405/5/21 | 1405/5/30 | 11.09 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | اجرای نمای ضلع ورودی |  |  |  |  | 5.545 | 50 | متر مربع |  |  | 0% | 0%
|  | اجرای نمای ضلع فرعی |  |  |  |  | 5.545 | 90 | متر مربع |  |  | 0% | 0%
349 | 5.3.5.6 | اجرای سیستم اعلام حریق ساختمان پست سوییچگیر |  | 5 روز | 1405/5/31 | 1405/6/4 | 0.87 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | نصبیات سیستم اعلام حریق |  |  |  |  | 0.87 | 1 | ست |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
350 | 5.3.5.7 | اجرای سیستم اطفا حریق ساختمان پست سوییچگیر |  | 5 روز | 1405/5/21 | 1405/5/25 | 2.61 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | نصبیات سیستم اطفاء حریق |  |  |  |  | 2.61 | 1 | ست |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
351 | 5.3.6 | ساختمان مانیتورینگ |  | 100 روز | 1405/3/1 | 1405/6/7 | 64.01 |  |  |  | 15.85% | 0% | -15.85% | 4.52% | 0% | 11.33% | 0% | -11.33%
352 | 5.3.6.1 | اجرای فونداسیون ساختمان مانیتورینگ |  | 21 روز | 1405/3/1 | 1405/3/21 | 5.18 |  |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
|  | گودبرداری |  |  |  |  | 1.7267 | 60 | متر مکعب |  |  | 0% | 0%
|  | آرماتوربندی و قالب بندی |  |  |  |  | 1.7267 | 10000 | کیلوگرم |  |  | 0% | 0%
|  | بتن ریزی |  |  |  |  | 1.7267 | 50 | متر مکعب |  |  | 0% | 0%
353 | 5.3.6.2 | سفت کاری ساختمان مانیتورینگ |  | 50 روز | 1405/3/22 | 1405/5/9 | 20.7 |  |  |  | 24% | 0% | -24% | 14% | 0% | 10% | 0% | -10%
|  | دیوار چینی |  |  |  |  | 10.35 | 180 | متر مربع |  |  | 0% | 0%
|  | اجرای سقف |  |  |  |  | 10.35 | 140 | متر مربع |  |  | 0% | 0%
354 | 5.3.6.3 | اجرای تاسیسات ساختمان مانیتورینگ |  | 10 روز | 1405/5/10 | 1405/5/19 | 15.53 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | اجرای تاسیسات مکانیکی |  |  |  |  | 7.765 | 1 | ست |  |  | 0% | 0%
|  | اجرای تاسیسات برقی |  |  |  |  | 7.765 | 1 | ست |  |  | 0% | 0%
355 | 5.3.6.4 | نازک کاری ساختمان مانیتورینگ |  | 10 روز | 1405/5/20 | 1405/5/29 | 5.18 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | تکمیل گچ کاری |  |  |  |  | 2.59 | 300 | متر مربع |  |  | 0% | 0%
|  | تکمیل سنگ کاری |  |  |  |  | 2.59 | 10 | متر مربع |  |  | 0% | 0%
356 | 5.3.6.5 | اجرای نمای ساختمان مانیتورینگ |  | 9 روز | 1405/5/30 | 1405/6/7 | 5.18 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | اجرای نمای ضلع ورودی |  |  |  |  | 2.59 | 60 | متر مربع |  |  | 0% | 0%
|  | اجرای نمای ضلع فرعی |  |  |  |  | 2.59 | 180 | متر مربع |  |  | 0% | 0%
357 | 5.3.6.6 | اجرای سیستم اعلام حریق ساختمان مانیتورینگ |  | 5 روز | 1405/5/31 | 1405/6/4 | 1.74 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | نصبیات سیستم اعلام حریق |  |  |  |  | 1.74 | 1 | ست |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
358 | 5.3.6.7 | اجرای سیستم اطفا حریق ساختمان مانیتورینگ |  | 5 روز | 1405/5/21 | 1405/5/25 | 5.22 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | نصبیات سیستم اطفاء حریق |  |  |  |  | 5.22 | 1 | ست |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
359 | 5.3.6.8 | کلیه تجهیزات و ملزومات |  | 5 روز | 1405/5/2 | 1405/5/6 | 5.28 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | نصب تجهیزات و ملزومات نهایی |  |  |  |  | 5.28 | 1 | ست |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
360 | 5.3.7 | ساختمان نگهبانی |  | 114 روز | 1405/2/12 | 1405/6/1 | 7.33 |  |  |  | 84.17% | 0% | -84.17% | 6.76% | 0% | 77.41% | 0% | -77.41%
361 | 5.3.7.1 | اجرای فونداسیون ساختمان نگهبانی |  | 10 روز | 1405/2/12 | 1405/2/21 | 0.62 |  |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
|  | گودبرداری |  |  |  |  | 0.20667 | 20 | متر مکعب |  |  | 0% | 0%
|  | آرماتوربندی و قالب بندی |  |  |  |  | 0.20667 | 2000 | کیلوگرم |  |  | 0% | 0%
|  | بتن ریزی |  |  |  |  | 0.20667 | 10 | متر مکعب |  |  | 0% | 0%
362 | 5.3.7.2 | سفت کاری ساختمان نگهبانی |  | 20 روز | 1405/2/22 | 1405/3/10 | 2.46 |  |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
|  | دیوار چینی |  |  |  |  | 1.23 | 30 | متر مربع |  |  | 0% | 0%
|  | اجرای سقف |  |  |  |  | 1.23 | 15 | متر مربع |  |  | 0% | 0%
363 | 5.3.7.3 | اجرای تاسیسات ساختمان نگهبانی |  | 10 روز | 1405/3/11 | 1405/3/20 | 1.85 |  |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
|  | اجرای تاسیسات مکانیکی |  |  |  |  | 0.925 | 1 | ست |  |  | 0% | 0%
|  | اجرای تاسیسات برقی |  |  |  |  | 0.925 | 1 | ست |  |  | 0% | 0%
364 | 5.3.7.4 | نازک کاری ساختمان نگهبانی |  | 5 روز | 1405/3/21 | 1405/3/25 | 0.62 |  |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
|  | تکمیل گچ کاری |  |  |  |  | 0.31 | 40 | متر مربع |  |  | 0% | 0%
|  | تکمیل سنگ کاری |  |  |  |  | 0.31 | 5 | متر مربع |  |  | 0% | 0%
365 | 5.3.7.5 | اجرای نمای ساختمان نگهبانی |  | 5 روز | 1405/3/26 | 1405/3/30 | 0.62 |  |  |  | 100% | 0% | -100% | 80% | 0% | 20% | 0% | -20%
|  | اجرای نمای ضلع ورودی |  |  |  |  | 0.31 | 18 | متر مربع |  |  | 0% | 0%
|  | اجرای نمای ضلع فرعی |  |  |  |  | 0.31 | 35 | متر مربع |  |  | 0% | 0%
366 | 5.3.7.6 | اجرای سیستم اعلام حریق ساختمان نگهبانی |  | 2 روز | 1405/5/31 | 1405/6/1 | 0.29 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | نصبیات سیستم اعلام حریق |  |  |  |  | 0.29 | 1 | ست |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
367 | 5.3.7.7 | اجرای سیستم اطفا حریق ساختمان نگهبانی |  | 2 روز | 1405/5/21 | 1405/5/22 | 0.87 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | نصبیات سیستم اطفاء حریق |  |  |  |  | 0.87 | 1 | ست |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
368 | 5.4 | عملیات مکانیکال |  | 103 روز | 1405/2/21 | 1405/5/30 | 967.21 |  |  |  | 33.63% | 0% | -33.63% | 7.96% | 0% | 25.67% | 0% | -25.67%
369 | 5.4.1 | نقشه برداری پایه ها و میخ کوبی |  | 6 روز | 1405/2/21 | 1405/2/26 | 42.17 |  |  |  | 100% | 0% | -100% | 0% | 0% | 100% | 0% | -100%
|  | نقشه برداری موقعیت پایه ها |  |  |  |  | 12.17 | 14000 | نقطه |  |  | 0% | 0%
|  | اجرای میخ کوبی |  |  |  |  | 30 | 2000 | نقطه |  |  | 0% | 0%
370 | 5.4.2 | پایه کوبی |  | 46 روز | 1405/2/31 | 1405/4/14 | 42.84 |  |  |  | 74% | 0% | -74% | 15% | 0% | 59% | 0% | -59%
|  | اجرای پایه های پیرامونی |  |  |  |  | 21.42 | 2000 | عدد |  |  | 0% | 0%
|  | اجرای پایه های داخلی |  |  |  |  | 21.42 | 12000 | عدد |  |  | 0% | 0%
371 | 5.4.3 | نصب متعلقات استراکچرها |  | 56 روز | 1405/3/4 | 1405/4/28 | 441.1 |  |  |  | 54% | 0% | -54% | 13% | 0% | 41% | 0% | -41%
|  | نصب متعلقات تکمیلی استراکچر پیرامونی |  |  |  |  | 220.55 | 109 | میز |  |  | 0% | 0%
|  | نصب متعلقات تکمیلی استراکچر داخلی |  |  |  |  | 220.55 | 400 | میز |  |  | 0% | 0%
372 | 5.4.4 | نصب پنل ها |  | 61 روز | 1405/4/1 | 1405/5/30 | 441.1 |  |  |  | 3% | 0% | -3% | 3% | 0% | 0% | 0% | 0%
|  | نصب نهایی پنل های پیرامونی |  |  |  |  | 220.55 | 109 | میز |  |  | 0% | 0%
|  | نصب نهایی پنل های داخلی |  |  |  |  | 220.55 | 400 | میز |  |  | 0% | 0%
373 | 5.5 | عملیات الکتریکال |  | 60 روز | 1405/4/16 | 1405/6/13 | 1308.53 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | عملیات اجرایی الکتریکال | 0 | 60 روز | 1405/4/16 | 1405/6/13 | 1108.14 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
374 | 5.5.1 | اجرای ترانشه و کانال عبور فیبر نوری |  | 10 روز | 1405/4/16 | 1405/4/25 | 26.41 | 4000 | متر |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
375 | 5.5.2 | نصب سازه اینورتر و وایرینگ اینورترهای سایت |  | 8 روز | 1405/4/31 | 1405/5/7 | 7.02 | 30 | عدد |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
376 | 5.5.3 | اجرای سیستم زمین نیروگاه |  | 15 روز | 1405/5/16 | 1405/5/30 | 290.7 | 5000 | متر |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
377 | 5.5.4 | تابلوهای فشار متوسط و کلیه متعلقات |  | 5 روز | 1405/5/31 | 1405/6/4 | 58 | 6 | سلول |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
378 | 5.5.5 | تابلوهای فشار ضعیف و کلیه متعلقات |  | 2 روز | 1405/6/1 | 1405/6/2 | 43.5 | 1 | سلول |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
379 | 5.5.6 | کلیه کابل های فشار ضعیف نیروگاهac |  | 15 روز | 1405/5/16 | 1405/5/30 | 266.42 | 35406 | متر |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
380 | 5.5.7 | کلیه کابل های فشار متوسط نیروگاهac |  | 6 روز | 1405/5/16 | 1405/5/21 | 108.85 | 2520 | متر |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
381 | 5.5.8 | کابل dc |  | 34 روز | 1405/5/11 | 1405/6/13 | 135.72 | 82000 | متر |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
382 | 5.5.9 | اجرای کابل های فیبر نوری |  | 3 روز | 1405/5/26 | 1405/5/28 | 6.25 | 4000 | متر |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
383 | 5.5.10 | نصب ایستگاه هواشناسی و سنسورها |  | 3 روز | 1405/6/6 | 1405/6/8 | 1 | 7 | سنسور |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
384 | 5.5.11 | MV Station نصب |  | 2 روز | 1405/5/21 | 1405/5/22 | 1 | 3 | عدد |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
385 | 5.5.12 | اجرای کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و بستر مخابراتی با پست بالادست به جز فیبر نوری |  | 3 روز | 1405/6/3 | 1405/6/5 | 56.55 | 4000 | متر |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
386 | 5.5.13 | نصب ترانسفورماتور کمکی و دیزل |  | 1 روز | 1405/6/8 | 1405/6/8 | 36.25 | 1 | عدد |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
387 | 5.5.14 | نصب یو پی اس |  | 1 روز | 1405/5/31 | 1405/5/31 | 18.85 | 3 | پکیج |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
388 | 5.5.15 | سیستم حفاظت صاعقه |  | 2 روز | 1405/6/2 | 1405/6/3 | 29 | 4 | سیستم |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
389 | 5.5.16 | اجرای کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و ارسال دیتا |  | 2 روز | 1405/6/9 | 1405/6/10 | 22.62 | 4000 | متر |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
390 | 5.5.17 | کلیه متعلقات مربوط به کابل کشی و سیم کشی |  | 12 روز | 1405/5/22 | 1405/6/2 | 95.4 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | کلیه متعلقات مربوط به کابل کشی و سیم کشی |  | 12 روز | 1405/5/22 | 1405/6/2 | 95.4 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
391 | 5.5.17.1 | نصب لدر |  | 3 روز | 1405/5/31 | 1405/6/2 | 23.85 | 100 | متر |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
392 | 5.5.17.2 | اجرای لوله پلی اتیلن و فلکسی |  | 5 روز | 1405/5/26 | 1405/5/30 | 23.85 | 4000 | متر |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
393 | 5.5.17.3 | اجرای سرسیم و کابل شو |  | 3 روز | 1405/5/31 | 1405/6/2 | 23.85 | 500 | عدد |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
394 | 5.5.17.4 | اجرای سر کابل |  | 2 روز | 1405/5/22 | 1405/5/23 | 23.85 | 27 | عدد |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
395 | 5.5.18 | نصب سیستم روشنایی |  | 22 روز | 1405/5/10 | 1405/5/31 | 35.7 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | نصب سیستم روشنایی |  | 22 روز | 1405/5/10 | 1405/5/31 | 35.7 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
396 | 5.5.18.1 | اجرای فونداسیون سیستم روشنایی |  | 8 روز | 1405/5/10 | 1405/5/17 | 17.6 | 24 | پایه |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
397 | 5.5.18.2 | کابل کشی سیستم روشنایی |  | 5 روز | 1405/5/21 | 1405/5/25 | 12.67 | 24 | پایه |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
398 | 5.5.18.3 | نصب پایه ها و چراغ ها |  | 6 روز | 1405/5/26 | 1405/5/31 | 5.43 | 24 | پایه |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
399 | 5.5.19 | CCTV نصب سیستم |  | 14 روز | 1405/5/25 | 1405/6/7 | 69.29 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | CCTV نصب سیستم |  | 14 روز | 1405/5/25 | 1405/6/7 | 69.29 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
400 | 5.5.19.1 | اجرای فونداسیون دوربین |  | 5 روز | 1405/5/25 | 1405/5/29 | 17.46 | 24 | پایه |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
401 | 5.5.19.2 | کابل کشی دوربین ها |  | 5 روز | 1405/5/30 | 1405/6/3 | 25.64 | 24 | پایه |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
402 | 5.5.19.3 | نصب پایه ها و دوربین ها |  | 4 روز | 1405/6/4 | 1405/6/7 | 26.19 | 24 | پایه |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
403 | 6 | تست و تحویل |  | 31 روز | 1405/5/22 | 1405/6/21 | 188 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
404 | 6.1 | تست و راه اندازی نیروگاه |  | 27 روز | 1405/5/22 | 1405/6/17 | 130.9 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | تست و راه اندازی نیروگاه | 0 | 27 روز | 1405/5/22 | 1405/6/17 | 130.9 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | تست و راه اندازی نیروگاه | 0 | 27 روز | 1405/5/22 | 1405/6/17 | 130.9 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
405 | 6.1.1 | تست کلیه کابل های فشار ضعیف نیروگاهac |  | 2 روز | 1405/5/31 | 1405/6/1 | 34.06 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
406 | 6.1.2 | تست کلیه کابل های فشار متوسط نیروگاهac |  | 2 روز | 1405/5/22 | 1405/5/23 | 11.54 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
407 | 6.1.3 | تست کابل dc |  | 4 روز | 1405/6/14 | 1405/6/17 | 14.38 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
408 | 6.1.4 | تست تابلوهای فشار متوسط و کلیه متعلقات |  | 1 روز | 1405/6/5 | 1405/6/5 | 6.15 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
409 | 6.1.5 | تست کابل شبکه مورد نیازسیستم انتقال دیتا و اسکادا |  | 1 روز | 1405/5/29 | 1405/5/29 | 0.38 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
410 | 6.1.6 | تست سیستم زمین نیروگاه |  | 2 روز | 1405/5/31 | 1405/6/1 | 14.55 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
411 | 6.1.7 | تست کلیه متعلقات مربوط به کابل کشی و سیم کشی |  | 2 روز | 1405/6/3 | 1405/6/4 | 4.5 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
412 | 6.1.8 | تست تابلوهای فشار ضعیف و کلیه متعلقات |  | 2 روز | 1405/6/3 | 1405/6/4 | 2.31 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
413 | 6.1.9 | تست کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و بستر مخابراتی با پست بالادست |  | 1 روز | 1405/6/6 | 1405/6/6 | 6 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
414 | 6.1.10 | تست کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و ارسال دیتا |  | 1 روز | 1405/6/11 | 1405/6/11 | 2.38 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
415 | 6.1.11 | تست یو پی اس |  | 1 روز | 1405/6/1 | 1405/6/1 | 0.8 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
416 | 6.1.12 | تست کلیه تجهیزات مربوط به دوربین |  | 2 روز | 1405/6/8 | 1405/6/9 | 15.38 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
417 | 6.1.13 | تست سیستم روشنایی |  | 1 روز | 1405/6/1 | 1405/6/1 | 1.92 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
418 | 6.1.14 | تست سیستم اعلام حریق |  | 1 روز | 1405/6/5 | 1405/6/5 | 0.31 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
419 | 6.1.15 | تست سیستم اطفا حریق |  | 1 روز | 1405/5/26 | 1405/5/26 | 0.92 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
420 | 6.1.16 | تست سیستم حفاظت صاعقه |  | 1 روز | 1405/6/4 | 1405/6/4 | 14.55 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
421 | 6.1.17 | تست ترانسفورماتور کمکی و دیزل |  | 1 روز | 1405/6/9 | 1405/6/9 | 0.77 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
422 | 6.2 | ارایه نقشه های ازبیلت |  | 22 روز | 1405/5/31 | 1405/6/21 | 45 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | ارایه نقشه های ازبیلت | 0 | 22 روز | 1405/5/31 | 1405/6/21 | 45 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | ارایه نقشه های ازبیلت | 0 | 22 روز | 1405/5/31 | 1405/6/21 | 45 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
423 | 6.2.1 | ارایه نقشه های ازبیلت الکتریکال |  | 4 روز | 1405/6/18 | 1405/6/21 | 15 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
424 | 6.2.2 | ارایه نقشه های ازبیلت مکانیکال |  | 14 روز | 1405/5/31 | 1405/6/13 | 15 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
425 | 6.2.3 | ارایه نقشه های ازبیلت civil |  | 12 روز | 1405/6/8 | 1405/6/19 | 15 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
426 | 6.3 | راه اندازی، اتصال به شبکه و پلمپ کنتور |  | 1 روز | 1405/6/18 | 1405/6/18 | 4.5 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | راه اندازی، اتصال به شبکه و پلمپ کنتور | 0 | 1 روز | 1405/6/18 | 1405/6/18 | 4.5 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | راه اندازی، اتصال به شبکه و پلمپ کنتور | 0 | 1 روز | 1405/6/18 | 1405/6/18 | 4.5 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
427 | 6.3.1 | راه اندازی، اتصال به شبکه و پلمپ کنتور |  | 1 روز | 1405/6/18 | 1405/6/18 | 4.5 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
428 | 6.4 | آموزش |  | 6 روز | 1405/6/16 | 1405/6/21 | 7.6 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | آموزش | 0 | 6 روز | 1405/6/16 | 1405/6/21 | 7.6 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | آموزش | 0 | 6 روز | 1405/6/16 | 1405/6/21 | 7.6 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
429 | 6.4.1 | آموزش |  | 6 روز | 1405/6/16 | 1405/6/21 | 7.6 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
430 | 6.5 | برچیدن کارگاه |  | 5 روز | 1405/6/17 | 1405/6/21 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | برچیدن کارگاه | 0 | 5 روز | 1405/6/17 | 1405/6/21 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | برچیدن کارگاه | 0 | 5 روز | 1405/6/17 | 1405/6/21 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
431 | 6.5.1 | برچیدن کارگاه |  | 5 روز | 1405/6/17 | 1405/6/21 | 0 | 100 | % |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
432 | 7 | پایان |  | 0 روز | 1405/6/21 | 1405/6/21 | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## MDR
|  | پروژه احداث نیروگاه خورشیدی 20 مگاواتی زارچ یزد شماره قرارداد: PKPS-P2-C2-0410 | [24 empty] | 2026-06-27 |  | RJ
[27 empty] | RJ | IFC | CM
[27 empty] | CM | IFA | AN
DOCUMENT NO. : 410-DE-PM-LST-0084 |  | Document Name : Master Document List | [21 empty] | Discipline |  | Rev. | AN | IFI | AP
[24 empty] | PM |  | 06 | AP | AFC | IFC
[24 empty] | Page 1 of 1 |  |  | AFC |  | IFA
|  | #REF! | [26 empty] | IFI
No | Document Number | Description | Discipline | Class | Status | Man-Hour | W.V | %Complete | 1st Issue Date | تاریخ برنامه ای ارسال مدرک براساس برنامه جبرانی | تاریخ پایان طبق برنامه اولیه تائید شده | Hold By | Delay | Last Status
Engineering | [5 empty] | 3949 | 100% | 61.1% | [5 empty] | Transmittal No. | Date of Receive | status | Rev | Comment Sheet No. | Comment Sheet Date | Comment Sheet Status | Reply Sheet ID | Reply Sheet Date | Reply Sheet Status | Conclusion ID | Conclusion Date | Conclusion Status
Electrical | [5 empty] | 1448 | 36.67% | 72.33%
1 | 410-BE-EL-SPC-0001 | Solar Panel Technical Specification | Electrical | FA | AP | 5 | 0.1266% | 100% |  | Done | 1404/11/3 |  |  | 50 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AP |  |  | 0 |  |  | 0
2 | 410-BE-EL-SPC-0002 | Inverter Technical Specification | Electrical | FA | AP | 5 | 0.1266% | 100% |  | Done | 1404/11/3 |  |  | 51 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | CM | - | 2026-05-11 | N | - | 2026-05-12 | AP
3 | 410-BE-EL-SPC-0003 | MV Station Technical Specification | Electrical | FA | AP | 5 | 0.1266% | 100% |  | Done | 1404/11/3 |  |  | 52 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | CM | - | 2026-05-11 | N | - | 2026-05-12 | AP
4 | 410-BE-EL-SPC-0004 | DC Connection (MC4) Technical Specification | Electrical | FA | AP | 5 | 0.1266% | 100% |  | Done | 1404/11/3 |  |  | 22 | 2026-04-19 | IFA | 01 | - | 2026-05-02 | CM | - | 2026-05-13 | N | - | 2026-05-16 | AP
5 | 410-BE-EL-SPC-0005 | DC Cable Technical Specification | Electrical | FA | AP | 5 | 0.1266% | 100% |  | Done | 1404/11/3 |  |  | 24 | 2026-04-19 | IFA | 01 | - | 2026-05-02 | AP | - | 2026-04-13 | C |  |  | 0
6 | 410-BE-EL-SPC-0006 | LV Cable Technical Specification | Electrical | FA | IFC | 5 | 0.1266% | 45% |  | 1405/03/17 | 1404/11/3 | PK | 15 | 127 | 2026-06-08 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
7 | 410-BE-EL-SPC-0007 | MV Cable Technical Specification | Electrical | FA | IFC | 5 | 0.1266% | 45% |  | 1405/03/17 | 1404/11/3 | PK | 15 | 128 | 2026-06-08 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
8 | 410-BE-EL-SPC-0008 | MV Switchgear (CT, PT, Relay) Technical Specification | Electrical | FA | AN | 5 | 0.1266% | 75% |  | Done | 1404/11/3 | NT | 17 | 53 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AN | - | 2026-05-11 | N | 410-05-PK-NT-CC-0076 | 2026-06-06 | OP
9 | 410-BE-EL-SPC-0009 | Earthing and Lightning Technical Specification | Electrical | FA |  | 5 | 0.1266% | 0% |  | 1405/03/20 | 1404/11/3 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
10 | 410-BE-EL-SPC-0013 | Auxiliary Transformer Technical Specification | Electrical | FA |  | 5 | 0.1266% | 0% |  | 1405/03/31 | 1404/11/3 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
11 | 410-BE-EL-SPC-0015 | UPS and Battery Technical Specification | Electrical | FA |  | 5 | 0.1266% | 0% |  | 1405/03/31 | 1404/11/3 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
12 | 410-BE-EL-SPC-0016 | Diesel Generator Technical Specification | Electrical | FA |  | 5 | 0.1266% | 0% |  | 1405/03/23 | 1404/11/3 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
13 | 410-BE-EL-DRW-0020 | General Single Line Diagram (GSLD) | Electrical | FA | DAP | 21 | 0.5318% | 100% |  | Done | 1404/11/14 |  |  | 1 | 2026-02-16 | IFA | 01 | 410-04-PK-NT-C-011 | 2026-02-18 | AN | 410-04-NT-PK-R-011 | 2026-04-19 | N | 410-04-PK-NT-CC-011 | 2026-06-14 | AN
14 | 410-BE-EL-DRW-0021 | General Layout | Electrical | FA | AP | 21 | 0.5318% | 100% |  | Done | 1404/11/10 |  |  | 47 | 2026-05-04 | AFC | 04 | - | 2026-04-26 | AP |  |  | 0 |  |  | 0
15 | 410-DE-EL-CAL-0022 | PV System Calculation Study (String Size, Optimum Tilt and Pitch) | Electrical | FA | CM | 27 | 0.6837% | 60% |  | 1405/03/04 | 1404/11/21 | NT | 17 | 89 | 2026-05-25 | IFC | 00 | 410-05-PK-NT-C-0108 | 2026-06-06 | CM |  |  | 0 |  |  | 0
16 | 410-BE-EL-REP-0023 | PVSYST Report | Electrical | FA | AN | 18 | 0.4558% | 75% |  | Done | 1404/11/11 | NT | 16 | 1 | 2026-02-16 | IFA | 01 | 410-05-PK-NT-C-0013 | 2026-06-07 | AN | - | 2026-02-14 | N |  |  | 0
17 | 410-BE-EL-REP-0024 | Plant Detailed Report | Electrical | FA | AP | 21 | 0.5318% | 100% |  | Done | 1404/11/15 |  |  | 1 | 2026-02-16 | IFA | 01 | - | 2026-02-18 | AP |  |  | 0 |  |  | 0
18 | 410-BE-EL-MTO-0025 | Solar Module, Connector, Inverter and MV station MTO | Electrical | FI | DAP | 18 | 0.4558% | 100% |  | Done | 1404/11/25 |  |  | 10 | 2026-03-07 | IFC | 00 | 410-04-PK-NT-C-0022 | 2026-03-11 | AN | 410-04-NT-PK-R-0022 | 2026-05-25 | N | 410-04-PK-NT-CC-0022 | 2026-06-17 | AP
19 | 410-DE-EL-DRW-0026 | Strings Connection Diagram & Inverter Arrangement (DC Side) | Electrical | FA | DAP | 21 | 0.5318% | 100% |  | Done | 1404/11/24 |  |  | 10 | 2026-03-07 | IFC | 00 | 410-04-PK-NT-C-0023 | 2026-03-11 | AN | 410-04-NT-PK-R-0023 | 2026-05-23 | C | 410-04-PK-NT-CC-0023 | 2026-06-14 | AN
20 | 410-DE-EL-DRW-0027 | Module & Table Arrangement (DC Side) | Electrical | FA | DAP | 21 | 0.5318% | 100% |  | Done | 1404/11/20 |  |  | 10 | 2026-03-07 | IFC | 00 | 410-04-PK-NT-C-0024 | 2026-03-11 | AN | 410-04-NT-PK-R-0024 | 2026-05-23 | A | 410-04-PK-NT-CC-0024 | 2026-06-14 | AN
21 | 410-DE-EL-CAL-0028 | DC Cable Calculation | Electrical | FA | IFA | 27 | 0.6837% | 75% |  | Done | 1404/12/4 | PK | 0 | 159 | 2026-06-23 | IFA | 02 | 410-05-PK-NT-C-0107 | 2026-06-06 | AN | 410-05-NT-PK-R-0107 | 2026-06-23 | N |  |  | 0
22 | 410-DE-EL-MTO-0029 | DC Cable List, Labeling Code and MTO | Electrical | FI | CM | 19 | 0.4811% | 60% |  | Done | 1404/12/7 | NT | 16 | 85 | 2026-05-25 | IFA | 01 | 410-05-PK-NT-C-0110 | 2026-06-07 | CM | 410-05-NT-PK-R-0026 | 2026-05-23 | C | 410-05-PK-NT-CC-0026 | 2026-06-02 | OP
23 | 410-DE-EL-CAL-0030 | LVAC Cable Calculation | Electrical | FA | AP | 27 | 0.6837% | 100% |  | Done | 1404/11/25 |  |  | 70 | 2026-05-12 | IFA | 02 | - | 2026-05-13 | AP |  |  | 0 |  |  | 0
24 | 410-DE-EL-LST-0031 | LV Cable Termination List and MTO | Electrical | FI | IFI | 14 | 0.3545% | 90% |  | 1405/03/23 | 1404/12/4 | PK | 0 | 161 | 2026-06-23 | IFI | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
25 | 410-DE-EL-MTO-0032 | LV Cable List, Labeling Code and MTO | Electrical | FI | DAP | 19 | 0.4811% | 100% |  | Done | 1404/12/8 |  |  | 78 | 2026-05-18 | IFI | 02 | - | 2026-05-03 | CM |  |  | 0 |  |  | 0
26 | 410-DE-EL-CAL-0033 | MV Cable Calculations | Electrical | FA | AP | 27 | 0.6837% | 100% |  | Done | 1404/11/25 |  |  | 65 | 2026-05-11 | IFA | 02 | - | 2026-05-11 | AP |  |  | 0 |  |  | 0
27 | 410-DE-EL-MTO-0034 | MV Cable List, Labeling Code and MTO | Electrical | FI | AP | 18 | 0.4558% | 100% |  | Done | 1404/12/4 |  |  | 17 | 2026-04-06 | IFI | 00 | - | 2026-04-20 | CM | - | 2026-05-02 | N | - | 2026-05-03 | AP
28 | 410-DE-EL-LST-0035 | MV Cable Termination List and MTO | Electrical | FI | IFI | 14 | 0.3545% | 90% |  | 1405/03/23 | 1404/12/13 | PK | 0 | 163 | 2026-06-23 | IFI | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
29 | 410-DE-EL-DRW-0036 | Electrical Cable Route and Section | Electrical | FA | IFC | 22 | 0.5571% | 45% |  | 1405/03/20 | 1404/11/20 | PK | 8 | 151 | 2026-06-15 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
30 | 410-DE-EL-DRW-0037 | Cable Trench Layout | Electrical | FA | IFC | 22 | 0.5571% | 45% |  | 1405/03/20 | 1404/11/20 | PK | 0 | 166 | 2026-06-23 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
31 | 410-DE-EL-CAL-0038 | Earthing System Calculation | Electrical | FA | CM | 27 | 0.6837% | 60% |  | Done | 1404/11/25 | NT | 0 | 148 | 2026-06-14 | IFA | 01 | 410-05-PK-NT-C-0134 | 2026-06-23 | CM |  |  | 0 |  |  | 0
32 | 410-DE-EL-DRW-0039 | Earthing System Layout | Electrical | FA | CM | 22 | 0.5571% | 60% |  | Done | 1404/12/5 | NT | 0 | 158 | 2026-06-17 | IFA | 01 | 410-05-PK-NT-C-0133 | 2026-06-23 | CM |  |  | 0 |  |  | 0
33 | 410-DE-EL-CAL-0040 | Lightning Protection Calculation | Electrical | FA | AP | 27 | 0.6837% | 100% |  | Done | 1404/11/15 |  |  | 107 | 2026-05-31 | IFA | 01 | 410-05-PK-NT-C-0109 | 2026-06-07 | AP |  |  | 0 |  |  | 0
34 | 410-DE-EL-DRW-0041 | Lightning Protection Layout | Electrical | FA | CM | 21 | 0.5318% | 60% |  | Done | 1404/11/25 | NT | 41 | 62 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM |  |  | 0 |  |  | 0
35 | 410-DE-EL-MTO-0042 | Earthing and Lightning Protection MTO | Electrical | FI | IFI | 19 | 0.4811% | 90% |  | 1405/03/23 | 1404/12/5 | PK | 8 | 150 | 2026-06-15 | IFI | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
36 | 410-DE-EL-DRW-0043 | Protection Single Line Diagram (PSLD) | Electrical | FA | CM | 21 | 0.5318% | 60% |  | Done | 1404/11/24 | NT | 41 | 63 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM |  |  | 0 |  |  | 0
37 | 410-DE-EL-CAL-0044 | CT and PT Calculations | Electrical | FA |  | 27 | 0.6837% | 0% |  | 1405/05/23 | 1404/11/19 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
38 | 410-DE-EL-DRW-0045 | MV Switchgear Logic Diagram | Electrical | FA | CM | 20 | 0.5065% | 60% |  | 1405/03/04 | 1404/11/29 | NT | 17 | 88 | 2026-05-25 | IFC | 00 | 410-05-PK-NT-C-0106 | 2026-06-06 | CM |  |  | 0 |  |  | 0
39 | 410-DE-EL-REP-0046 | Trip Table | Electrical | FA | AN | 21 | 0.5318% | 75% |  | 1405/03/09 | 1404/12/9 | NT | 17 | 103 | 2026-05-30 | IFC | 00 | 410-05-PK-NT-C-105 | 2026-06-06 | AN |  |  | 0 |  |  | 0
40 | 410-DE-EL-LST-0047 | Alarm List | Electrical | FA |  | 14 | 0.3545% | 0% |  | 1405/04/15 | 1404/12/9 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
41 | 410-DE-EL-DRW-0048 | Indoor and Outdoor Electrical Plan & Details for Building | Electrical | FA |  | 21 | 0.5318% | 0% |  | 1405/03/23 | 1404/11/20 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
42 | 410-DE-EL-MTO-0049 | MV Switchgear MTO | Electrical | FI |  | 19 | 0.4811% | 0% |  | 1405/05/15 | 1404/12/4 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
43 | 410-DE-EL-LST-0050 | Load List | Electrical | FA |  | 14 | 0.3545% | 0% |  | 1405/03/25 | 1404/12/17 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
44 | 410-DE-EL-DRW-0051 | LVAC Auxiliary Panel Single Line Diagram | Electrical | FA |  | 21 | 0.5318% | 0% |  | 1405/03/27 | 1404/11/17 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
45 | 410-DE-EL-CAL-0052 | UPS Calculation | Electrical | FA | DAP | 27 | 0.6837% | 100% |  | 1405/03/16 | 1404/11/22 |  |  | 114 | 2026-06-03 | IFC | 00 | 410-05-PK-NT-C-0122 | 2026-06-14 | CM |  |  | 0 |  |  | 0
46 | 410-DE-EL-MTO-0053 | AUX Equipment MTO (AUX Transformer, Diesel, UPS, Battery) | Electrical | FA |  | 19 | 0.4811% | 0% |  | 1405/03/27 | 1404/12/2 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
47 | 410-DE-EL-CAL-0058 | Indoor and Outdoor Lighting Calculation | Electrical | FA |  | 27 | 0.6837% | 0% |  | 1405/03/24 | 1404/11/15 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
48 | 410-DE-EL-DRW-0059 | Outdoor Lighting Pole Drawing | Electrical | FA | DAP | 23 | 0.5824% | 100% |  | 1405/03/16 | 1404/11/24 |  |  | 126 | 2026-06-07 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
49 | 410-DE-EL-DRW-0060 | Outdoor Lighting Layout and Switchboard | Electrical | FA |  | 23 | 0.5824% | 0% |  | 1405/03/24 | 1404/12/3 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
50 | 410-DE-EL-MTO-0061 | Lighting System MTO | Electrical | FI |  | 19 | 0.4811% | 0% |  | 1405/03/31 | 1404/12/12 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
51 | 410-DE-EL-REP-0082 | Special Tools | Electrical | FA | DAP | 22 | 0.5571% | 100% |  | Done | 1405/3/26 |  | 0 | 58 | 2026-05-06 | IFC | 00 |  | 2026-05-12 | CM | - | 2026-05-30 | N |  |  | 0
52 | 410-DE-EL-DRW-0128 | MV Switchgear Schematic Diagram | Electrical | FA |  | 20 | 0.5065% | 0% |  | 1405/04/15 | 1404/11/19 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
53 | 410-DE-EL-DRW-0129 | MV Switchgear Front View Drawing | Electrical | FA |  | 20 | 0.5065% | 0% |  | 1405/04/15 | 1404/11/24 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
54 | 410-BE-EL-DSH-0146 | Solar Panel Datasheet | Electrical | FA | AP | 5 | 0.1266% | 100% |  | Done | 1404/11/7 |  |  | 55 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | AP |  |  | 0 |  |  | 0
55 | 410-BE-EL-DSH-0147 | Inverter Datasheet | Electrical | FA | IFC | 5 | 0.1266% | 45% |  | Done | 1404/11/7 | PK | 8 | 152 | 2026-06-15 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
56 | 410-BE-EL-DSH-0148 | MV Station Datasheet | Electrical | FA | DAP | 5 | 0.1266% | 100% |  | Done | 1404/11/7 |  | 0 | 15 | 2026-03-26 | IFC | 00 | 2 | 2026-03-28 | AN | - | 2026-05-23 | N |  |  | 0
57 | 410-BE-EL-DSH-0149 | DC Connection (MC4) Datasheet | Electrical | FA | AP | 5 | 0.1266% | 100% |  | Done | 1404/11/7 |  |  | 21 | 2026-04-19 | IFC | 00 | - | 2026-05-02 | AP |  |  | 0 |  |  | 0
58 | 410-BE-EL-DSH-0150 | DC Cable Datasheet | Electrical | FA | AP | 5 | 0.1266% | 100% |  | Done | 1404/11/7 |  |  | 23 | 2026-04-19 | IFC | 00 | - | 2026-05-02 | AP |  |  | 0 |  |  | 0
59 | 410-BE-EL-DSH-0151 | LV Cable Datasheet | Electrical | FA | DAP | 5 | 0.1266% | 100% |  | 1405/03/09 | 1404/11/7 |  |  | 105 | 2026-05-30 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
60 | 410-BE-EL-DSH-0152 | MV Cable Datasheet | Electrical | FA | DAP | 5 | 0.1266% | 100% |  | 1405/03/09 | 1404/11/7 |  |  | 104 | 2026-05-30 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
61 | 410-BE-EL-DSH-0153 | MV Switchgear (CT, PT, Relay) Datasheet | Electrical | FA |  | 5 | 0.1266% | 0% |  | 1405/05/15 | 1404/11/7 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
62 | 410-BE-EL-DSH-0154 | Earthing and Lightning Datasheet | Electrical | FA | CM | 5 | 0.1266% | 60% |  | Done | 1404/11/7 | NT | 116 | Email | 2026-02-02 | IFC | 00 | - | 2026-02-27 | CM |  |  | 0 |  |  | 0
63 | 410-BE-EL-DSH-0155 | Auxiliary Transformer Datasheet | Electrical | FA | RJ | 5 | 0.1266% | 0% |  | Done | 1404/11/7 | NT | 49 | 56 | 2026-05-04 | IFC | 00 | - | 2026-05-05 | RJ |  |  | 0 |  |  | 0
64 | 410-BE-EL-DSH-0156 | UPS and Battery Datasheet | Electrical | FA |  | 5 | 0.1266% | 0% |  | 1405/03/25 | 1404/11/7 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
65 | 410-BE-EL-DSH-0157 | Diesel Generator Datasheet | Electrical | FA |  | 2 | 0.05065% | 0% |  | 1405/03/31 | 1404/11/7 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
66 | 410-DE-EL-MRE-0168 | Material Requisition for Indoor Power and Lighting Distribution Panel | Electrical | FA | DAP | 45 | 1.14% | 100% |  | 1405/03/16 | 1404/12/8 |  |  | 120 | 2026-06-06 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
67 | 410-DE-EL-MRE-0169 | Material Requisition for Auxiliary Transformer | Electrical | FA | DAP | 45 | 1.14% | 100% |  | 1405/03/16 | 1404/12/12 |  |  | 125 | 2026-06-07 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
68 | 410-DE-EL-MRE-0170 | Material Requisition for PCC | Electrical | Deleted |  |  | 0% | 0% |  | Deleted | 1405/3/1 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
69 | 410-DE-EL-MRE-0171 | Material Requisition for MV Switchgear (CT, PT, Relay) | Electrical | FA | DAP | 90 | 2.279% | 100% |  | 1405/03/16 | 1405/4/25 |  |  | 117 | 2026-06-06 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
70 | 410-DE-EL-MRE-0172 | Material Requisition for AC Cable | Electrical | FA | DAP | 35 | 0.8863% | 100% |  | 1405/03/13 | 1405/3/8 |  |  | 111 | 2026-06-03 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
71 | 410-DE-EL-MRE-0173 | Material Requisition for DC Cable | Electrical | FA | DAP | 35 | 0.8863% | 100% |  | 1405/03/13 | 1405/4/15 |  |  | 112 | 2026-06-03 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
72 | 410-DE-EL-MRE-0174 | Material Requisition for Earthing and Lightning | Electrical | FA | DAP | 45 | 1.14% | 100% |  | 1405/03/16 | 1405/3/14 |  |  | 118 | 2026-06-06 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
73 | 410-DE-EL-MRE-0175 | Material Requisition for DC Connection (MC4) | Electrical | FA | DAP | 35 | 0.8863% | 100% |  | 1405/03/13 | 1405/4/12 |  |  | 109 | 2026-06-03 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
74 | 410-DE-EL-MRE-0176 | Material Requisition for Lighting System | Electrical | FA | DAP | 45 | 1.14% | 100% |  | 1405/03/16 | 1404/12/16 |  |  | 119 | 2026-06-06 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
75 | 410-DE-EL-MRE-0177 | Material Requisition for UPS and Battery | Electrical | FA | DAP | 45 | 1.14% | 100% |  | 1405/03/16 | 1405/2/17 |  |  | 121 | 2026-06-06 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
76 | 410-BE-EL-MRE-0186 | Material Requisition for Diesel Generator | Electrical | FA | DAP | 40 | 1.013% | 100% |  | 1405/03/16 | 1405/4/15 |  |  | 122 | 2026-06-06 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
Civil | [5 empty] | 1131 | 28.64% | 55.52% | [11 empty] | 0% |  |  | 0 |  |  | 0
77 | 410-DE-CV-REP-0087 | Topography of Field | Civil | FI | AP | 28 | 0.709% | 100% |  | Done | 1404/11/23 |  |  | 35 | 2026-04-27 | IFC | 00 | - | 2026-05-02 | AP |  |  | 0 |  |  | 0
78 | 410-DE-CV-REP-0088 | Geotechnical Test Report | Civil | FI | CM | 28 | 0.709% | 90% |  | Done | 1404/11/23 | PK | 14 | 33 | 2026-04-27 | IFI | 00 | 410-05-PK-NT-C-0104 | 2026-06-02 | CM | 410-05-NT-PK-R-0104 | 2026-06-09 | N |  |  | 0
79 | 410-DE-CV-REP-0089 | Ramming and Pull-Out Test Report | Civil | FI | RJ | 28 | 0.709% | 0% |  | Done | 1404/11/23 | NT | 22 | 34 | 2026-04-27 | IFI | 00 | 410-05-PK-NT-C-0102 | 2026-06-01 | RJ |  |  | 0 |  |  | 0
80 | 410-DE-CV-REP-0090 | Hydrology Study Report | Civil | FI | DAP | 28 | 0.709% | 100% |  | Done | 1404/11/23 |  |  | 37 | 2026-04-28 | IFC | 00 | 410-05-PK-NT-C-0065 | 2026-05-02 | CM | 410-05-NT-PK-R-0065 | 2026-05-25 | C | 410-05-PK-NT-CC-0065 | 2026-06-14 | CM
81 | 410-DE-CV-DRW-0091 | Site Fence Detail Drawing | Civil | FA | AP | 28 | 0.709% | 100% |  | Done | 1404/12/8 |  |  | 49 | 2026-05-04 | AFC | 06 | - | 2026-05-05 | AP |  |  | 0 |  |  | 0
82 | 410-DE-CV-DRW-0092 | Logistic Area | Civil | FA | AN | 28 | 0.709% | 75% |  | Done | 1404/11/20 | NT | 49 | 48 | 2026-05-04 | AFC | 02 | - | 2026-05-05 | AN |  |  | 0 |  |  | 0
83 | 410-DE-CV-CAL-0093 | Buildings Foundation & Structure Calculation | Civil | Deleted |  |  |  | 0% |  | Done | 1404/11/23 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
84 | 410-DE-CV-CAL-0187 | Swichgear Building Foundation & Structure Calculation | Civil | FA |  | 11 | 0.2786% | 0% |  | 1405/03/30 | [8 empty] | 0 | 0 |  |  | 0 |  |  | 0
85 | 410-DE-CV-CAL-0188 | Control Building Foundation & Structure Calculation | Civil | FA |  | 11 | 0.2786% | 0% |  | 1405/03/30 | [8 empty] | 0 | 0 |  |  | 0 |  |  | 0
86 | 410-DE-CV-CAL-0189 | Guard Building Foundation & Structure Calculation | Civil | FA |  | 11 | 0.2786% | 0% |  | 1405/03/30 | [8 empty] | 0 | 0 |  |  | 0 |  |  | 0
87 | 410-DE-CV-DRW-0094 | Buildings Foundation & Structure Drawing | Civil | Deleted |  |  |  | 0% |  | Done | 1404/11/28 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
88 | 410-DE-CV-DRW-0190 | Swichgear Building Foundation & Structure Drawing | Civil | FA |  | 9 | 0.2279% | 0% |  | 1405/03/30 | [8 empty] | 0 | 0 |  |  | 0 |  |  | 0
89 | 410-DE-CV-DRW-0191 | Control Building Foundation & Structure Drawing | Civil | FA |  | 9 | 0.2279% | 0% |  | 1405/03/30 | [8 empty] | 0 | 0 |  |  | 0 |  |  | 0
90 | 410-DE-CV-DRW-0192 | Guard Building Foundation & Structure Drawing | Civil | FA |  | 9 | 0.2279% | 0% |  | 1405/03/30 | [8 empty] | 0 | 0 |  |  | 0 |  |  | 0
91 | 410-DE-CV-DRW-0098 | Parking Foundation & Structure Detail Drawing | Civil | FA |  | 26 | 0.6584% | 0% |  | 1405/03/20 | 1404/11/23 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
92 | 410-DE-CV-DRW-0099 | Power Plant Entrance Gate Drawing | Civil | FA |  | 26 | 0.6584% | 0% |  | 1405/03/22 | 1404/12/12 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
93 | 410-DE-CV-DRW-0100 | Parking Architectural Drawing | Civil | FA | CM | 29 | 0.7344% | 60% |  | 1405/03/20 | 1404/11/30 | NT | 0 | 164 | 2026-06-23 | IFC | 00 | 410-05-PK-NT-C-0135 | 2026-06-23 | CM |  |  | 0 |  |  | 0
94 | 410-DE-CV-DRW-0101 | Landscaping Layout | Civil | FA | IFC | 29 | 0.7344% | 45% |  | 1405/03/22 | 1404/11/19 | PK | 12 | 142 | 2026-06-11 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
95 | 410-DE-CV-DRW-0102 | Buildings Architectural Detail drawing | Civil | Deleted |  |  |  | 0% |  | Done | 1404/12/2 |  |  | 12 | 2026-03-15 | IFC | 00 | 11 | 2026-03-17 | RJ |  |  | 0 |  |  | 0
96 | 410-DE-CV-DRW-0193 | Swichgear Building Architectural Detail drawing | Civil | FA | AN | 10 | 0.2532% | 75% |  | 1405/03/05 |  | NT | 21 | 93 | 2026-05-26 | IFA | 01 | 410-05-PK-NT-C-0103 | 2026-06-02 | AN |  |  | 0 |  |  | 0
97 | 410-DE-CV-DRW-0194 | Control Building Architectural Detail drawing | Civil | FA | DAP | 10 | 0.2532% | 100% |  | Done |  |  |  | 79 | 2026-05-20 | IFA | 01 | 410-05-PK-NT-C-0119 | 2026-06-14 | CM |  |  | 0 |  |  | 0
98 | 410-DE-CV-DRW-0195 | Guard Building Architectural Detail drawing | Civil | FA | DAP | 10 | 0.2532% | 100% |  | Done |  |  |  | 84 | 2026-05-25 | IFA | 01 | 410-05-PK-NT-C-0118 | 2026-06-14 | CM |  |  | 0 |  |  | 0
99 | 410-DE-CV-MTO-0103 | Fence MTO | Civil | FI | AP | 25 | 0.6331% | 100% |  | Done | 1404/12/11 | 0 | 0 | 26 | 2026-04-21 | IFI | 2 | - | 2026-04-26 | AN | - | 2026-04-27 | N | 410-05-PK-NT-CC-0058 | 2026-06-09 | AP
100 | 410-DE-CV-DRW-0104 | Site Grading and Leveling | Civil | FA | DAP | 29 | 0.7344% | 100% |  | Done | 1404/12/3 |  |  | 32 | 2026-04-27 | IFA | 01 | 410-05-PK-NT-C-0117 | 2026-06-14 | AN |  |  | 0 |  |  | 0
101 | 410-DE-CV-DRW-0105 | Drainage For Insite of Plant & Implementation Detail Drawing | Civil | FA | DAP | 29 | 0.7344% | 100% |  | Done | 1404/12/2 |  |  | 38 | 2026-04-28 | IFC | 01 | 410-05-PK-NT-C-0123 | 2026-06-14 | CM |  |  | 0 |  |  | 0
102 | 410-DE-CV-DRW-0106 | Flood Managmant For Outsite of Plant & Implementation Detail Drawing | Civil | FA | DAP | 29 | 0.7344% | 100% |  | Done | 1404/12/6 |  |  | 40 | 2026-04-28 | IFC | 01 | 410-05-PK-NT-C-0124 | 2026-06-14 | CM |  |  | 0 |  |  | 0
103 | 410-DE-CV-DRW-0107 | Internal Road Layout & Implementation Detail Drawing | Civil | FA | DAP | 29 | 0.7344% | 100% |  | Done | 1404/11/20 |  |  | 36 | 2026-04-28 | IFA | 01 | 15 | 2026-03-17 | CM |  |  | 0 |  |  | 0
104 | 410-DE-CV-DRW-0108 | Access Road Layout & Implementation Detail Drawing | Civil | FA | DAP | 29 | 0.7344% | 100% |  | 1405/03/13 | 1404/11/20 |  |  | 108 | 2026-06-03 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
105 | 410-DE-CV-CAL-0109 | MV Station Foundation Calculation | Civil | FA | AN | 36 | 0.9116% | 75% |  | Done | 1404/11/17 | NT | 37 | 67 | 2026-05-11 | IFC | 00 | 410-05-PK-NT-C-0091 | 2026-05-17 | AN |  |  | 0 |  |  | 0
106 | 410-DE-CV-DRW-0110 | MV Station Foundation Drawings | Civil | FA | CM | 29 | 0.7344% | 60% |  | Done | 1404/11/22 | NT | 15 | 97 | 2026-05-30 | IFA | 01 | 410-05-PK-NT-C-0111 | 2026-06-08 | CM |  |  | 0 |  |  | 0
107 | 410-DE-CV-DRW-0111 | Auxiliary Transformer Foundation Detail Drawings | Civil | FA |  | 29 | 0.7344% | 0% |  | 1405/03/20 | 1404/11/17 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
108 | 410-DE-CV-CAL-0112 | Calculation Report for Structure | Civil | FA | CM | 36 | 0.9116% | 60% |  | Done | 1404/11/27 | NT | 0 | 156 | 2026-06-16 | IFA | 01 | 410-05-PK-NT-C-0132 | 2026-06-23 | CM |  |  | 0 |  |  | 0
109 | 410-DE-CV-DRW-0113 | Structure Detail Drawings | Civil | FA | CM | 29 | 0.7344% | 60% |  | Done | 1404/12/3 | NT | 64 | 16 | 2026-04-04 | IFC | 00 | - | 2026-04-20 | CM |  |  | 0 |  |  | 0
110 | 410-DE-CV-DRW-0114 | PV Structure Ramming Location Details Drawing (Stacking) | Civil | FA |  | 29 | 0.7344% | 0% |  | 1405/03/31 | 1404/11/27 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
111 | 410-DE-CV-MTO-0115 | Solar Module Structure MTO | Civil | FI | AN | 25 | 0.6331% | 75% |  | Done | 1404/12/7 | NT | 72 | 16 | 2026-04-04 | IFI | 00 | - | 2026-04-12 | AN |  |  | 0 |  |  | 0
112 | 410-DE-CV-DRW-0116 | Table UTM Point | Civil | FA |  | 29 | 0.7344% | 0% |  | 1405/03/31 | 1404/12/6 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
113 | 410-DE-CV-MTO-0117 | Structure, Entrance Gate and Foundation of Building MTO | Civil | FI |  | 25 | 0.6331% | 0% |  | 1405/03/22 | 1404/12/16 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
114 | 410-DE-CV-CAL-0130 | System Drainage Calculation | Civil | FA | DAP | 36 | 0.9116% | 100% |  | Done | 1404/12/3 |  |  | 31 | 2026-04-27 | IFC | 00 | 410-05-PK-NT-C-0116 | 2026-06-14 | CM |  |  | 0 |  |  | 0
115 | 410-DE-CV-CAL-0131 | Lighting Foundation Calculation | Civil | FA |  | 36 | 0.9116% | 0% |  | 1405/03/26 | 1404/11/15 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
116 | 410-DE-CV-CAL-0132 | Lightning Foundation Calculation | Civil | FA |  | 36 | 0.9116% | 0% |  | 1405/03/26 | 1404/11/12 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
117 | 410-DE-CV-DRW-0133 | Lightning Foundation Drawing | Civil | FA |  | 28 | 0.709% | 0% |  | 1405/03/26 | 1404/11/20 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
118 | 410-DE-CV-CAL-0134 | Lighting and CCTV Pole Calculation | Civil | FA |  | 36 | 0.9116% | 0% |  | 1405/03/26 | 1404/11/15 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
119 | 410-DE-CV-DRW-0135 | Septic Tank Detail Drawing | Civil | FA | CM | 28 | 0.709% | 60% |  | 1405/03/19 | 1404/11/25 | NT | 3 | 147 | 2026-06-14 | IFC | 00 | 410-05-PK-NT-C-0128 | 2026-06-20 | CM |  |  | 0 |  |  | 0
120 | 410-DE-CV-DRW-0136 | Water Tank Foundation Detail Drawing | Civil | FA | CM | 28 | 0.709% | 60% |  | 1405/03/19 | 1404/11/24 | NT | 2 | 143 | 2026-06-11 | IFC | 00 | 410-05-PK-NT-C-0130 | 2026-06-21 | CM |  |  | 0 |  |  | 0
121 | 410-DE-CV-CAL-0137 | Calculation for Fence | Civil | FA | DAP | 28 | 0.709% | 100% |  | Done | 1404/12/3 |  |  | 25 | 2026-04-21 | IFA | 3 | 410-05-PK-NT-C-0059 | 2026-04-26 | AN | 410-05-NT-PK-R-0059 | 2026-04-27 | N | 410-05-PK-NT-CC-0059 | 2026-06-14 | AN
122 | 410-DE-CV-MRE-0167 | Material Requisition for Fence | Civil | FA | DAP | 70 | 1.773% | 100% |  | Done | 1404/12/12 |  |  | 124 | 2026-06-07 | IFC | 00 | 410-05-PK-NT-C-0129 | 2026-06-21 | CM |  |  | 0 |  |  | 0
Quality | [5 empty] | 580 | 14.69% | 26.25% | [11 empty] | 0% |  |  | 0 |  |  | 0
123 | 410-DE-QA-REP-0073 | Solar Panel Installation Manual & Operation & Maintenance | Quality | FI | DAP | 29 | 0.7344% | 100% |  | 1405/03/04 | 1405/3/13 |  |  | 86 | 2026-05-25 | IFI | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
124 | 410-DE-QA-REP-0074 | Inverter Installation Manual & Operation & Maintenance | Quality | FI | DAP | 29 | 0.7344% | 100% |  | 1405/03/02 | 1405/4/25 |  |  | 81 | 2026-05-23 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
125 | 410-DE-QA-REP-0075 | MV Station Installation Manual & Operation & Maintenance | Quality | FI | DAP | 29 | 0.7344% | 100% |  | 1405/02/28 | 1405/5/14 |  |  | 74 | 2026-05-18 | IFI | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
126 | 410-DE-QA-REP-0076 | UPS Installation Manual & Operation & Maintenance | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/03/25 | 1405/5/25 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
127 | 410-DE-QA-REP-0077 | AUX Transformer Installation Manual & Operation & Maintenance | Quality | FI | IFI | 29 | 0.7344% | 90% |  | 1405/03/25 | 1405/5/13 | PK | 0 | 162 | 2026-06-23 | IFI | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
128 | 410-DE-QA-REP-0078 | Diesel Generator Installation Manual & Operation & Maintenance | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/04/25 | 1405/5/13 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
129 | 410-DE-QA-REP-0079 | Weather Station Installation Manual & Operation & Maintenance | Quality | FI | IFC | 29 | 0.7344% | 45% |  | 1405/03/17 | 1405/5/26 | PK | 15 | 130 | 2026-06-08 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
130 | 410-DE-QA-REP-0080 | Solar Structure Installation Manual & Operation & Maintenance | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/03/31 | 1405/2/14 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
131 | 410-DE-QA-REP-0081 | SCADA and Monitoring System Installation Manual & Operation & Maintenance | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/03/31 | 1405/5/15 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
132 | 410-DE-QA-REP-0083 | Project O&M General Instructions | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/04/05 | 1405/6/4 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
133 | 410-DE-QA-REP-0118 | Test Report of Solar Structure | Quality | FI | CM | 29 | 0.7344% | 90% |  | Done | 1405/3/14 | NT | 73 | 16 | 2026-04-04 | IFI | 00 | - | 2026-04-11 | CM |  |  | 0 |  |  | 0
134 | 410-DE-QA-REP-0119 | Test Reports for PV Modules | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/04/10 | 1405/3/14 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
135 | 410-DE-QA-REP-0120 | Test Reports for Inverter | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/04/15 | 1405/4/26 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
136 | 410-DE-QA-REP-0121 | Test Reports for MV Sation | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/05/19 | 1405/5/20 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
137 | 410-DE-QA-REP-0122 | Test Reports for AC and DC Cables | Quality | Deleted |  |  |  | 0% |  | Done | 1405/5/29 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
138 | 410-DE-QA-REP-0196 | Test Reports for AC Cables | Quality | FI |  | 14.5 | 0.3672% | 0% |  | 1405/04/15 | [8 empty] | 0 | 0 |  |  | 0 |  |  | 0
139 | 410-DE-QA-REP-0197 | Test Reports for DC Cables | Quality | FI |  | 14.5 | 0.3672% | 0% |  | 1405/03/31 | [8 empty] | 0 | 0 |  |  | 0 |  |  | 0
140 | 410-DE-QA-REP-0123 | Test Reports for Diesel Generators | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/04/25 | 1405/6/10 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
141 | 410-DE-QA-REP-0124 | Test Reports for AUX Transformer | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/04/10 | 1405/6/10 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
142 | 410-DE-QA-REP-0125 | Test Reports for Earthing and Ligthtning | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/04/25 | 1405/5/16 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
143 | 410-DE-QA-REP-0126 | Test Reports for MV Switchgear (CT, PT, Relay, …) | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/05/19 | 1405/5/27 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
144 | 410-DE-QA-REP-0127 | Test Reports for UPS and Battery | Quality | FI |  | 29 | 0.7344% | 0% |  | 1405/04/28 | 1405/5/29 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
Telecom | [5 empty] | 307 | 7.774% | 81.42% | [11 empty] | 0% |  |  | 0 |  |  | 0
145 | 410-BE-TL-SPC-0010 | Monitoring System Technical Specification | Telecom | FA | DAP | 8 | 0.2026% | 100% |  | 1405/03/09 | 1404/11/3 |  |  | 99 | 2026-05-30 | IFA | 01 |  | 2026-05-16 | AN |  |  | 0 |  |  | 0
146 | 410-BE-TL-SPC-0011 | Data Logger Technical Specification | Telecom | FA | AP | 8 | 0.2026% | 100% |  | 1405/03/17 | 1404/11/16 |  |  | 153 | 2026-06-16 | IFA | 01 | 410-05-PK-NT-C-0125 | 2026-06-20 | AP |  |  | 0 |  |  | 0
147 | 410-BE-TL-SPC-0012 | Weather Station Technical Specification | Telecom | FA | DAP | 8 | 0.2026% | 100% |  | Done | 1404/11/16 |  |  | 95 | 2026-05-30 | IFA | 01 | 410-05-PK-NT-C-0131 | 2026-06-21 | AN |  |  | 0 |  |  | 0
148 | 410-BE-TL-SPC-0014 | CCTV and NVR Technical Specification | Telecom | FA | CM | 8 | 0.2026% | 60% |  | Done | 1404/11/16 | NT | 41 | 66 | 2026-05-11 | IFC | 00 |  | 2026-05-13 | CM |  |  | 0 |  |  | 0
149 | 410-DE-TL-DRW-0054 | CCTV System Block Diagram | Telecom | FA | CM | 19 | 0.4811% | 60% |  | 1405/03/04 | 1404/11/24 | PK | 9 | 83 | 2026-05-25 | IFC | 00 | 410-05-PK-NT-C-0111 | 2026-06-09 | CM | 410-05-PK-NT-R-0111 | 2026-06-14 | N |  |  | 0
150 | 410-DE-TL-DRW-0055 | CCTV System Arrangement & Layout | Telecom | FA | CM | 19 | 0.4811% | 60% |  | 1405/03/20 | 1404/11/28 | NT | 3 | 146 | 2026-06-14 | IFC | 00 | 410-05-PK-NT-C-0126 | 2026-06-20 | CM |  |  | 0 |  |  | 0
151 | 410-DE-TL-DRW-0056 | CCTV Pole Detail Drawing, Switchboard, CAFU Details | Telecom | FA | DAP | 22 | 0.5571% | 100% |  | 1405/03/04 | 1404/12/2 |  |  | 87 | 2026-05-25 | IFC | 00 | 410-05-PK-NT-C-0121 | 2026-06-14 | CM |  |  | 0 |  |  | 0
152 | 410-DE-TL-MTO-0057 | CCTV System MTO | Telecom | FI | CM | 18 | 0.4558% | 90% |  | 1405/03/20 | 1404/12/12 | NT | 3 | 145 | 2026-06-14 | IFI | 00 | 410-05-PK-NT-C-0127 | 2026-06-20 | CM |  |  | 0 |  |  | 0
153 | 410-DE-TL-LST-0063 | SCADA System I/O List | Telecom | FA | DAP | 14 | 0.3545% | 100% |  | 1405/03/05 | 1404/11/18 |  |  | 90 | 2026-05-26 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
154 | 410-DE-TL-DRW-0064 | Monitoring System Overall Diagram | Telecom | FA | DAP | 20 | 0.5065% | 100% |  | 1405/03/09 | 1404/12/3 |  |  | 98 | 2026-05-30 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
155 | 410-DE-TL-MTO-0065 | Telecommunication and Monitoring System MTO | Telecom | FI | DAP | 19 | 0.4811% | 100% |  | 1405/03/09 | 1404/12/7 |  |  | 102 | 2026-05-30 | IFI | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
156 | 410-BE-TL-DSH-0158 | Monitoring System Datasheet | Telecom | FA | DAP | 7 | 0.1773% | 100% |  | 1405/03/09 | 1404/11/7 |  |  | 101 | 2026-05-30 | IFA | 01 |  | 2026-05-16 | CM |  |  | 0 |  |  | 0
157 | 410-BE-TL-DSH-0159 | Data Logger Datasheet | Telecom | FA | DAP | 7 | 0.1773% | 100% |  | 1405/03/09 | 1404/11/20 |  |  | 96 | 2026-05-30 | IFC | 00 | 410-05-PK-NT-C-0112 | 2026-06-14 | AP |  |  | 0 |  |  | 0
158 | 410-BE-TL-DSH-0160 | Weather Station Datasheet | Telecom | FA | DAP | 3 | 0.07597% | 100% |  | 1405/03/09 | 1404/11/20 |  |  | 100 | 2026-05-30 | IFC | 00 | 410-05-PK-NT-C-0113 | 2026-06-14 | AP |  |  | 0 |  |  | 0
159 | 410-BE-TL-DSH-0161 | CCTV and NVR Datasheet | Telecom | FA | IFC | 7 | 0.1773% | 45% |  | 1405/03/18 | 1404/11/20 | PK | 13 | 141 | 2026-06-10 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
160 | 410-DE-TL-MRE-0178 | Material Requisition forTelecommunication and Monitoring Cable | Telecom | FA | IFC | 30 | 0.7597% | 45% |  | 1405/03/24 | 1405/4/30 | PK | 8 | 178 | 2026-06-15 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
161 | 410-BE-TL-MRE-0179 | Material Requisition forFiber Optics | Telecom | FA | IFC | 30 | 0.7597% | 45% |  | 1405/03/25 | 1405/3/22 | PK | 6 | 157 | 2026-06-17 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
162 | 410-DE-TL-MRE-0180 | Material Requisition for CCTV and NVR | Telecom | FA | DAP | 30 | 0.7597% | 100% |  | 1405/03/17 | 1404/12/17 |  |  | 110 | 2026-06-03 | IFC | 00 | 410-05-PK-NT-C-0120 | 2026-06-14 | CM | 410-05-NT-PK-R-0120 | 2026-06-17 | N |  |  | 0
163 | 410-BE-TL-MRE-0185 | Material Requisition for Weather Station | Telecom | FA | DAP | 30 | 0.7597% | 100% |  | Done | 1405/2/28 |  | 0 | 115 | 2026-06-03 | IFA | 01 | 410-05-PK-NT-C-0114 | 2026-06-14 | AN | 410-05-NT-PK-R-0114 | 2026-06-16 | N |  |  | 0
Mechanical | [5 empty] | 226 | 5.723% | 64.73% | [11 empty] | 0% |  |  | 0 |  |  | 0
164 | 410-BE-ME-SPC-0017 | HVAC Technical Specification | Mechanical | FA | IFC | 8 | 0.2026% | 45% |  | 1405/03/18 | 1404/11/16 | PK | 14 | 138 | 2026-06-09 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
165 | 410-BE-ME-SPC-0018 | Piping Material, Plumbing Fittings, Pumps Technical Specification | Mechanical | FA | DAP | 8 | 0.2026% | 100% |  | 1405/03/09 | 1404/11/16 |  |  | 94 | 2026-05-30 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
166 | 410-DE-ME-REP-0062 | Solar Panel Cleaning & Maintenance Procedures | Mechanical | FA | IFA | 15 | 0.3798% | 60% |  | Done | 1404/12/7 | PK | 0 | 165 | 2026-06-23 | IFA | 01 | - | 2026-05-03 | CM |  |  | 0 |  |  | 0
167 | 410-DE-ME-CAL-0066 | HVAC Equipment Calculation | Mechanical | FA | IFC | 20 | 0.5065% | 45% |  | 1405/03/18 | 1404/11/30 | PK | 14 | 137 | 2026-06-09 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
168 | 410-DE-ME-DRW-0067 | HVAC Equipment Layout for Building | Mechanical | Deleted |  |  |  | 0% |  | Done | 1404/12/4 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
169 | 410-DE-ME-DRW-0198 | HVAC Equipment Layout for Swichgear Building | Mechanical | FA | IFC | 6.6667 | 0.1688% | 45% |  | 1405/03/18 |  | PK | 14 | 136 | 2026-06-09 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
170 | 410-DE-ME-DRW-0199 | HVAC Equipment Layout for Control Building | Mechanical | FA | IFC | 6.6667 | 0.1688% | 45% |  | 1405/03/18 |  | PK | 14 | 134 | 2026-06-09 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
171 | 410-DE-ME-DRW-0200 | HVAC Equipment Layout for Guard Building | Mechanical | FA | IFC | 6.6667 | 0.1688% | 45% |  | 1405/03/18 |  | PK | 14 | 135 | 2026-06-09 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
172 | 410-DE-ME-MTO-0068 | HVAC and Piping System MTO | Mechanical | FI | IFC | 19 | 0.4811% | 45% |  | 1405/03/19 | 1404/12/8 | PK | 13 | 140 | 2026-06-10 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
173 | 410-DE-ME-DRW-0095 | Mechanical Drawing (Water Supply and Sewage Systems) | Mechanical | FA | IFC | 20 | 0.5065% | 45% |  | 1405/03/20 | 1404/11/24 | PK | 12 | 144 | 2026-06-11 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
174 | 410-DE-ME-SPC-0096 | Septic Tank Technical Specification | Mechanical | FA | DAP | 4 | 0.1013% | 100% |  | 1405/02/28 | 1404/11/16 |  |  | 75 | 2026-05-18 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
175 | 410-DE-ME-SPC-0097 | Water Tank Technical Specification | Mechanical | FA | DAP | 4 | 0.1013% | 100% |  | 1405/03/16 | 1404/11/16 |  |  | 113 | 2026-06-03 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
176 | 410-BE-ME-DSH-0162 | HVAC Datasheet | Mechanical | FA | IFC | 7 | 0.1773% | 45% |  | 1405/03/18 | 1404/11/20 | PK | 14 | 139 | 2026-06-09 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
177 | 410-BE-ME-DSH-0163 | Piping Material, Plumbing Fittings, Pumps Datasheet | Mechanical | FA | DAP | 7 | 0.1773% | 100% |  | 1405/03/05 | 1404/11/20 |  |  | 91 | 2026-05-26 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
178 | 410-BE-ME-DSH-0164 | Septic Tank Datasheet | Mechanical | FA | DAP | 7 | 0.1773% | 100% |  | 1405/02/28 | 1404/11/20 |  |  | 76 | 2026-05-18 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
179 | 410-BE-ME-DSH-0165 | Water Tank Datasheet | Mechanical | FA | DAP | 7 | 0.1773% | 100% |  | 1405/03/05 | 1404/11/20 |  |  | 92 | 2026-05-26 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
180 | 410-BE-ME-MRE-0183 | Material Requisition for Septic Tank | Mechanical | FA | DAP | 40 | 1.013% | 100% |  | 1405/03/16 | 1404/11/28 |  |  | 116 | 2026-06-06 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
181 | 410-BE-ME-MRE-0184 | Material Requisition for Water Tank | Mechanical | FA | IFC | 40 | 1.013% | 45% |  | 1405/03/16 | 1404/11/27 | PK | 15 | 131 | 2026-06-08 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
Safety | [5 empty] | 149 | 3.773% | 73.26% | [11 empty] | 0% |  |  | 0 |  |  | 0
182 | 410-BE-SF-SPC-0019 | Fire Alarm System Technical Specification | Safety | FA | DAP | 8 | 0.2026% | 100% |  | Done | 1404/11/16 |  |  | 69 | 2026-05-12 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
183 | 410-DE-SF-DRW-0069 | Fire Fighting Equipment Arrangement of MV Switchgear Buildings | Safety | FA | DAP | 19 | 0.4811% | 100% |  | 1405/03/13 | 1404/12/4 |  |  | 106 | 2026-05-31 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
184 | 410-DE-SF-DRW-0070 | Outdoor Fire Fighting Equipment & Shelter Arrangement | Safety | FA | DAP | 19 | 0.4811% | 100% |  | 1405/02/28 | 1404/12/9 |  |  | 77 | 2026-05-18 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
185 | 410-DE-SF-DRW-0071 | Fire Alarm System Layout and Block Diagram | Safety | FA | IFC | 19 | 0.4811% | 45% |  | 1405/03/23 | 1404/12/8 | PK | 7 | 154 | 2026-06-16 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
186 | 410-DE-SF-MTO-0072 | Fire and Safety and F & G System MTO | Safety | FI | IFI | 19 | 0.4811% | 90% |  | 1405/03/23 | 1404/12/15 | PK | 7 | 155 | 2026-06-16 | IFI | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
187 | 410-BE-SF-DSH-0166 | Fire Alarm System Datasheet | Safety | FA | IFC | 5 | 0.1266% | 45% |  | 1405/03/27 | 1404/11/20 | PK | 0 | 160 | 2026-06-23 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
188 | 410-DE-SF-MRE-0181 | Material Requisition for Fire Alarm System | Safety | FA | IFC | 30 | 0.7597% | 45% |  | 1405/03/19 | 1405/4/31 | PK | 14 | 133 | 2026-06-09 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
189 | 410-DE-SF-MRE-0182 | Material Requisition for Fire Fighting Equipment Arrangement | Safety | FA | IFC | 15 | 0.3798% | 45% |  | 1405/03/19 | 1405/4/18 | PK | 14 | 132 | 2026-06-09 | IFC | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
190 | 410-DE-SF-REP-0201 | HSE Plan | Safety | FA | DAP | 15 | 0.3798% | 100% |  | Done |  |  |  | 123 | 2026-06-06 | IFA | 01 |  | 2026-05-11 | CM |  |  | 0 |  |  | 0
Project Management | [5 empty] | 108 | 2.735% | 74.07% | [11 empty] | 0% |  |  | 0 |  |  | 0
191 | 410-DE-PM-LST-0084 | Master Document List | Project Management | FA | AP | 14 | 0.3545% | 100% |  | Done | 1404/11/3 |  |  | 44 | 2026-05-04 | IFA | 06 | نامه 0034 | 2026-05-05 | AP |  |  | 0 |  |  | 0
192 | 410-DE-PM-REP-0085 | Time Schedule | Project Management | FA | AP | 23 | 0.5824% | 100% |  | Done | 1404/11/13 |  |  | 20 | 2026-04-22 | IFA | 02 | 410-05-PK-NT-C-0055 | 2026-04-26 | AP |  |  | 0 |  |  | 0
193 | 410-DE-PM-CAF-0086 | Cash Flow | Project Management | FA | DAP | 15 | 0.3798% | 100% |  | Done | 1405/2/8 |  |  | 82 | 2026-05-24 | IFA | 02 | جلسه کارفرما | 2026-04-07 | CM |  |  | 0 |  |  | 0
194 | 410-DE-PM-REP-0138 | Monthly Report 410-M-001 | Project Management | FI | AP | 7 | 0.1773% | 100% |  | Done | 1404/12/4 |  |  | 7 | 2026-02-24 | IFI | 00 | جلسه 1405/02/09 | 2026-04-29 | AP |  |  | 0 |  |  | 0
195 | 410-DE-PM-REP-0139 | Monthly Report 410-M-002 | Project Management | FI | AP | 7 | 0.1773% | 100% |  | Done | 1405/1/8 |  |  | - | 2026-03-20 | IFI | 00 | جلسه 1405/02/09 | 2026-04-29 | AP |  |  | 0 |  |  | 0
196 | 410-DE-PM-REP-0140 | Monthly Report 410-M-003 | Project Management | FI | AP | 7 | 0.1773% | 100% |  | Done | 1405/2/5 |  |  | 28 | 2026-04-23 | IFI | 00 | 140-05-PK-NT-C-0097 | 2026-05-05 | AP |  |  | 0 |  |  | 0
197 | 410-DE-PM-REP-0141 | Monthly Report 410-M-004 | Project Management | FI | DAP | 7 | 0.1773% | 100% |  | Done | 1405/3/5 |  |  | گزارش هفتگی 12 | 2026-05-26 | IFI | 00 |  | 0 | 0 |  |  | 0 |  |  | 0
198 | 410-DE-PM-REP-0142 | Monthly Report 410-M-005 | Project Management | FI |  | 7 | 0.1773% | 0% |  | Done | 1405/4/5 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
199 | 410-DE-PM-REP-0143 | Monthly Report 410-M-006 | Project Management | FI |  | 7 | 0.1773% | 0% |  | Done | 1405/5/5 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
200 | 410-DE-PM-REP-0144 | Monthly Report 410-M-007 | Project Management | FI |  | 7 | 0.1773% | 0% |  | Done | 1405/6/5 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0
201 | 410-DE-PM-REP-0145 | Monthly Report 410-M-008 | Project Management | FI |  | 7 | 0.1773% | 0% |  | Done | 1405/6/20 | [7 empty] | 0 | 0 |  |  | 0 |  |  | 0

## PSR-Local
| Procurement Status Report ( نیروگاه خورشیدی 20 مگاواتی ) | [31 empty] | Cut off Date: |  | 1405/04/02
| Item | MR No. | MR Description | Discipline | WBS Code | PO No. | QTY | Unit | MR Release Date | Rev | MR Status | RFQ Sent (Tender) | Bid Close Date | TBE Issued Date | CBE Issued Date | Board committee Approval Date | Work Commencement Letter Date | PO Price | P.O. Information Date |  | Vendor Information |  |  | Delivery Condition |  | K.O.M Date | P.I.M Date | ITP/ MPS Approved (Starting) | Inspection Information (Only Final Inspection) |  |  |  | Delivery at Site Dates |  |  | Delivery Information |  |  |  | Current Status | Area of Concerns | 20% | 20% | 20% | 20% | 20% | Before P.O Progress | 10% | 5% | 15% | 60% | 10% | After P.O Progress | 100% | Transport to Site Progress
[19 empty] | P.O Signed with Vendor | Advance Payment Date | Vendor Name | Manufacturer (Brand) | Origin | Duration | Term |  |  |  | 1st Part | 2nd Part | 3rd Part | 4th Part | Plan | ETA | Actual | 1st Part | 2nd Part | 3rd Part | 4th Part |  |  | Inquiry | TCL | TBE | Bid Winner | PO |  | Engineering Progress | Material Sub order Progress | Material Receipt Progress | Manufacturing Progress | IRN Progress |  | MRS Progress
1 | 1 | - | Material Requisition for Building Materials | Civil | 4.1.1.1 |  | 3 | Building | N/A | N/A | N/A | 1405/03/23 | 1405/03/23 | 1405/03/23 | 1405/03/23 | 1405/03/23 | 1405/03/23 | 112814 | 1405/03/25 | 1405/03/25 | مهد بتن یزد - کارخانه سیمان مهریز یزد | - | IRAN | 15 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/01/22 | 1405/04/15 | [7 empty] | 100% | 100% | 100% | 50% | 50% | 80% | 50% | 50% | 50% | 50% |  | 45% |  | 0%
1 | 2 | - | Material Requisition for Electrical Building Materials | Civil | 4.1.1.2 |  | 3 | Building | N/A | N/A | N/A | [6 empty] | 9796 | [7 empty] | N/A | N/A | N/A |  |  |  |  | 1405/03/05 | [13 empty] | 0% | [5 empty] | 0% |  | 0%
1 | 3 | 410-BE-ME-MRE-0183 | Material Requisition for Septic Tank | Mechanical | 4.1.1.3 | 14050312 | 1 | PCS (2000Lit) | 1405/03/16 | 0 | IFC | 1405/03/9 | 1405/03/10 | 1405/03/11 | 1405/03/12 | 1405/03/12 | 1405/03/12 | 949 | 1405/03/12 | 1405/03/18 | تانکرسازی فلز و پلی اتیلن برادران زیارتی | - | IRAN | 1 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/01/14 | 1405/03/20 | 1405/03/20 | 1405/03/20 | - | - | - | Delivery to Site |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1 | 4 | 410-BE-ME-MRE-0184 | Material Requisition for Water Tank | Mechanical | 4.1.1.3 | 14041203 | 3 | PCS (10000Lit + 500Lit) | 1405/03/18 | 0 | IFC | 1404/12/03 | 1404/12/04 | 1404/12/05 | 1404/12/06 | 1404/12/06 | 1404/12/06 | 1500 | 1404/12/06 | 1404/12/06 | آذین الوند آسیا | AZIN ALVAND | IRAN | 1 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/01/14 | 1404/12/08 | 1404/12/08 | 1404/12/08 | - | - | - | Delivery to Site |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1 | 5 | - | Material Requisition for Office Supplies | Civil | 4.1.1.4 | - | 1 | Set | N/A | N/A | N/A | 1404/12/03 | 1404/12/04 | 1404/12/05 | 1404/12/06 | 1404/12/06 | 1404/12/06 | 4898 | 1404/12/06 | 1404/12/06 | بازار ملزومات اداری و وسایل رفاهی | - | IRAN | 1 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/01/07 | 1404/12/08 | 1404/12/08 | 1404/12/08 | - | - | - | Delivery to Site |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1 | 6 | 410-DE-CV-MRE-0167 | Material Requisition for Fence | Civil | 4.1.2 | SK-CO-1405-11517 | 4260 | m | 1405/03/17 | 0 | IFC | 1405/02/12 | 1405/02/13 | 1405/02/14 | 1405/02/15 | 1405/02/15 | 1405/02/15 | 53877 | 1405/02/27 | 1405/02/27 | صنایع مفتولی توران گستر | صنایع مفتولی توران گستر | IRAN | 15 | Day | N/A | N/A | N/A | 1405/03/11 | 1405/03/16 | 1405/03/17 | 1405/03/19 | 1405/03/20 | 1405/03/19 | 1405/03/19 | 1405/03/11 | 1405/03/16 | 1405/03/17 | 1405/03/19 | Delivery to Site |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1 | 7 | 410-DE-EL-MRE-0168 | Material Requisition for Indoor Power and Lighting Distribution Panel | Electrical | 4.1.3 |  | 3 | Building | 1405/03/16 | 0 | IFC | 1405/03/28 | [5 empty] | 132142 | [14 empty] | 1405/05/07 | [8 empty] | 100% |  |  |  |  | 20% | [5 empty] | 0% |  | 0%
1 | 8 | 410-DE-EL-MRE-0169 | Material Requisition for Auxiliary Transformer | Electrical | 4.1.4 | 1405218003612 | 1 | PCS | 1405/03/17 | 0 | IFC | 1405/03/26 | 1405/03/27 | 1405/03/27 | 1405/03/27 | 1405/03/28 | 1405/03/28 | 9694.5 | 1405/04/02 | 1405/04/02 | ایران ترانسفو | ایران ترانسفو | IRAN | 14 | Day | N/A | N/A | N/A |  |  |  |  | 1405/05/21 | 1405/04/20 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 30% |  | 0%
1 | 9 | 410-BE-EL-MRE-0186 | Material Requisition for Diesel Generator | Electrical | 4.1.4 |  | 1 | PCS | 1405/03/16 | 0 | IFC | 1405/04/02 | [5 empty] | 9694.5 | [14 empty] | 1405/05/21 | [8 empty] | 100% |  |  |  |  | 20% | [5 empty] | 0% |  | 0%
1 | 10 | 410-DE-EL-MRE-0171 | Material Requisition for MV Switchgear | Electrical | 4.1.5 |  | 1 | PCS | 1405/03/16 | 0 | IFC | [6 empty] | 66071 | [14 empty] | 1405/05/31 | [13 empty] | 0% | [5 empty] | 0% |  | 0%
1 | 11 | 410-DE-EL-MRE-0171 | Material Requisition for CT, PT, Relay | Electrical | 4.1.6 |  | 1 | Package | 1405/03/16 | 0 | IFC | 1405/03/26 | [5 empty] | 66071 | [14 empty] | 1405/05/31 | [8 empty] | 100% |  |  |  |  | 20% | [5 empty] | 0% |  | 0%
1 | 12 | 410-DE-EL-MRE-0172 | Material Requisition for AC Cable (AC/LV) | Electrical | 4.1.7 | - | 33720 | m | 1405/03/13 | 0 | IFC | 1405/03/17 | 1405/03/17 | 1405/03/17 | 1405/03/18 | 1405/03/19 | 1405/03/19 | 150000 | 1405/03/19 | 1405/03/19 | SHUANGDENG CABLE | SHUANGDENG CABLE | CHINA | 14 | Day | N/A | N/A | N/A |  |  |  |  | 1405/05/15 | 1405/04/15 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 90% |  | 0%
1 | 13 | 410-DE-EL-MRE-0172 | Material Requisition for AC Cable (AC/MV) | Electrical | 4.1.7 |  | 2520 | m | 1405/03/13 | 0 | IFC | [6 empty] | 73151 | [14 empty] | 1405/05/15 | [13 empty] | 0% | [5 empty] | 0% |  | 0%
1 | 14 | 410-DE-EL-MRE-0173 | Material Requisition for DC Cable | Electrical | 4.1.8 | JQR-1017 | 81926.88 | m | 1405/03/13 | 0 | IFC | 1405/02/03 | 1405/02/04 | 1405/02/05 | 1405/02/05 | 1405/02/05 | 1405/02/06 | 107600 | 1405/02/06 | 1405/02/06 | JINQISOLAR | JINQISOLAR | CHINA | 10 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/04/27 | [6 empty] | Delivery to Storage |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0%
1 | 15 | 410-DE-TL-MRE-0178 | Material Requisition for Telecommunication and Monitoring Cable | Telecom | 4.1.9 |  |  | m | 1405/03/25 | 0 | IFC | 1405/03/30 | [5 empty] | 40244 | [14 empty] | 1405/05/30 | [8 empty] | 100% |  |  |  |  | 20% | [5 empty] | 0% |  | 0%
1 | 16 | 410-BE-TL-MRE-0179 | Material Requisition for Fiber Optics | Telecom | 4.1.10 |  | 487 | m | 1405/03/27 | 0 | IFC | 1405/03/30 | [5 empty] | 12098 | [14 empty] | 1405/05/25 | [8 empty] | 100% |  |  |  |  | 20% | [5 empty] | 0% |  | 0%
1 | 17 | 410-DE-EL-MRE-0174 | Material Requisition for Earthing | Electrical | 4.1.11 |  | 1 | Package | 1405/03/16 | 0 | IFC | 1405/03/26 | [5 empty] | 127840 | [14 empty] | 1405/05/15 | [8 empty] | 100% |  |  |  |  | 20% | [5 empty] | 0% |  | 0%
1 | 18 | 410-DE-EL-MRE-0174 | Material Requisition for Lightning | Electrical | 4.1.11 |  | 4 | Package | 1405/03/16 | 0 | IFC | 1405/03/26 | [5 empty] | 15510 | [14 empty] | 1405/05/15 | [8 empty] | 100% |  |  |  |  | 20% | [5 empty] | 0% |  | 0%
1 | 19 | 410-DE-EL-MRE-0175 | Material Requisition for DC Connection (MC4) | Electrical | 4.1.12 | JQR-1017 | 1051 | Pair | 1405/03/13 | 0 | IFC | 1405/02/03 | 1405/02/04 | 1405/02/05 | 1405/02/05 | 1405/02/05 | 1405/02/06 | 45366 | 1405/02/06 | 1405/02/06 | JINQISOLAR | TRINA SOLAR | CHINA | 10 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/05/15 | 1405/02/16 | 1405/02/16 | 1405/02/16 | - | - | - | Delivery to Site |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1 | 20 | 410-DE-TL-MRE-0180 | Material Requisition for CCTV and NVR | Telecom | 4.1.13 |  | 48 | PCS | 1405/03/13 | 0 | IFC | 1405/03/20 | [5 empty] | 77627 | [14 empty] | 1405/05/13 | [8 empty] | 100% |  |  |  |  | 20% | [5 empty] | 0% |  | 0%
1 | 21 | 410-DE-EL-MRE-0176 | Material Requisition for Lighting System | Electrical | 4.1.14 |  | 1 | Package | 1405/03/16 | 0 | IFC | [6 empty] | 9678 | [14 empty] | 1405/05/17 | [13 empty] | 0% | [5 empty] | 0% |  | 0%
1 | 22 | 410-DE-EL-MRE-0177 | Material Requisition for UPS and Battery | Electrical | 4.1.15 |  | 3 | Package | 1405/03/16 | 0 | IFC | [6 empty] | 10081 | [14 empty] | 1405/05/15 | [13 empty] | 0% | [5 empty] | 0% |  | 0%
1 | 23 | 410-DE-SF-MRE-0181 | Material Requisition for Fire Alarm System | Safety | 4.1.16 |  | 1 | Package | 1405/03/19 | 0 | IFC | [6 empty] | 1551 | [14 empty] | 1405/05/30 | [13 empty] | 0% | [5 empty] | 0% |  | 0%
1 | 24 | 410-DE-SF-MRE-0182 | Material Requisition for Fire Fighting Equipment Arrangement | Safety | 4.1.17 |  | 1 | Package | 1405/03/19 | 0 | IFC | [6 empty] | 4653 | [14 empty] | 1405/05/20 | [13 empty] | 0% | [5 empty] | 0% |  | 0%
1 | 25 | 410-BE-TL-MRE-0185 | Material Requisition for Weather Station | Telecom | 4.1.18 | 1405-NT-007 | 1 | Package | 1405/03/13 | 1 | IFA | 1405/03/16 | 1405/03/17 | 1405/03/17 | 1405/03/17 | 1405/03/18 | 1405/03/18 | 2298 | 1405/03/20 | 1405/03/20 | پرتو نگار دانش | پرتو نگار دانش | IRAN | 15 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/03/27 | 1405/04/20 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 30% |  | 0%
1 | 26 | - | Spaire Part | Electrical | 4.1.19 | - | 1 | Package | N/A | N/A | N/A | [6 empty] | 41210 | [7 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/06/15 | [13 empty] | 0% | [5 empty] | 0% |  | 0%
1 | 27 | - | Material Requisition for Panel Support Structure | Electrical | 4.2.1 |  | 1 | Package | N/A | N/A | N/A | 1405/03/20 | 1405/03/26 | 1405/03/26 | 1405/03/26 |  |  | 810000 | [14 empty] | 1405/02/30 | [8 empty] | 100% | 100% | 100% |  |  | 60% | [5 empty] | 0% |  | 0%
1 | 28 | - | Material Requisition for Inverter Support Structure | Electrical | 4.2.1 |  | 1 | Package | N/A | N/A | N/A | 1405/03/20 | 1405/03/26 | 1405/03/26 | 1405/03/26 |  |  | 7457 | [14 empty] | 1405/02/30 | [8 empty] | 100% | 100% | 100% |  |  | 60% | [5 empty] | 0% |  | 0%
1 | 29 | - | Material Requisition for Security Guard Booth | Civil | 5.1.1.2 | 225 | 1 | PCS | N/A | N/A | N/A | 1404/11/11 | 1404/11/13 | 1404/11/14 | 1404/11/14 | 1404/11/14 | 1404/11/18 | 5715 | 1404/11/18 | 1404/11/18 | کانکس و کانتینر اطلس | کانکس اطلس | IRAN | 1 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/01/21 | 1404/11/30 | 1404/11/30 | 1404/11/30 | - | - | - | Delivery to Site |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## Plan (hidden)
|  |  | 1404/10/21 | 1404/10/22 | 1404/10/23 | 1404/10/24 | 1404/10/25 | 1404/10/26 | 1404/10/27 | 1404/10/28 | 1404/10/29 | 1404/10/30 | 1404/11/01 | 1404/11/02 | 1404/11/03 | 1404/11/04 | 1404/11/05 | 1404/11/06 | 1404/11/07 | 1404/11/08 | 1404/11/09 | 1404/11/10 | 1404/11/11 | 1404/11/12 | 1404/11/13 | 1404/11/14 | 1404/11/15 | 1404/11/16 | 1404/11/17 | 1404/11/18 | 1404/11/19 | 1404/11/20 | 1404/11/21 | 1404/11/22 | 1404/11/23 | 1404/11/24 | 1404/11/25 | 1404/11/26 | 1404/11/27 | 1404/11/28 | 1404/11/29 | 1404/11/30 | 1404/12/01 | 1404/12/02 | 1404/12/03 | 1404/12/04 | 1404/12/05 | 1404/12/06 | 1404/12/07 | 1404/12/08 | 1404/12/09 | 1404/12/10 | 1404/12/11 | 1404/12/12 | 1404/12/13 | 1404/12/14 | 1404/12/15 | 1404/12/16 | 1404/12/17 | 1404/12/18 | 1404/12/19 | 1404/12/20 | 1404/12/21 | 1404/12/22 | 1404/12/23 | 1404/12/24 | 1404/12/25 | 1404/12/26 | 1404/12/27 | 1404/12/28 | 1404/12/29 | 1405/01/01 | 1405/01/02 | 1405/01/03 | 1405/01/04 | 1405/01/05 | 1405/01/06 | 1405/01/07 | 1405/01/08 | 1405/01/09 | 1405/01/10 | 1405/01/11 | 1405/01/12 | 1405/01/13 | 1405/01/14 | 1405/01/15 | 1405/01/16 | 1405/01/17 | 1405/01/18 | 1405/01/19 | 1405/01/20 | 1405/01/21 | 1405/01/22 | 1405/01/23 | 1405/01/24 | 1405/01/25 | 1405/01/26 | 1405/01/27 | 1405/01/28 | 1405/01/29 | 1405/01/30 | 1405/01/31 | 1405/02/01 | 1405/02/02 | 1405/02/03 | 1405/02/04 | 1405/02/05 | 1405/02/06 | 1405/02/07 | 1405/02/08 | 1405/02/09 | 1405/02/10 | 1405/02/11 | 1405/02/12 | 1405/02/13 | 1405/02/14 | 1405/02/15 | 1405/02/16 | 1405/02/17 | 1405/02/18 | 1405/02/19 | 1405/02/20 | 1405/02/21 | 1405/02/22 | 1405/02/23 | 1405/02/24 | 1405/02/25 | 1405/02/26 | 1405/02/27 | 1405/02/28 | 1405/02/29 | 1405/02/30 | 1405/02/31 | 1405/03/01 | 1405/03/02 | 1405/03/03 | 1405/03/04 | 1405/03/05 | 1405/03/06 | 1405/03/07 | 1405/03/08 | 1405/03/09 | 1405/03/10 | 1405/03/11 | 1405/03/12 | 1405/03/13 | 1405/03/14 | 1405/03/15 | 1405/03/16 | 1405/03/17 | 1405/03/18 | 1405/03/19 | 1405/03/20 | 1405/03/21 | 1405/03/22 | 1405/03/23 | 1405/03/24 | 1405/03/25 | 1405/03/26 | 1405/03/27 | 1405/03/28 | 1405/03/29 | 1405/03/30 | 1405/03/31 | 1405/04/01 | 1405/04/02 | 1405/04/03 | 1405/04/04 | 1405/04/05 | 1405/04/06 | 1405/04/07 | 1405/04/08 | 1405/04/09 | 1405/04/10 | 1405/04/11 | 1405/04/12 | 1405/04/13 | 1405/04/14 | 1405/04/15 | 1405/04/16 | 1405/04/17 | 1405/04/18 | 1405/04/19 | 1405/04/20 | 1405/04/21 | 1405/04/22 | 1405/04/23 | 1405/04/24 | 1405/04/25 | 1405/04/26 | 1405/04/27 | 1405/04/28 | 1405/04/29 | 1405/04/30 | 1405/04/31 | 1405/05/01 | 1405/05/02 | 1405/05/03 | 1405/05/04 | 1405/05/05 | 1405/05/06 | 1405/05/07 | 1405/05/08 | 1405/05/09 | 1405/05/10 | 1405/05/11 | 1405/05/12 | 1405/05/13 | 1405/05/14 | 1405/05/15 | 1405/05/16 | 1405/05/17 | 1405/05/18 | 1405/05/19 | 1405/05/20 | 1405/05/21 | 1405/05/22 | 1405/05/23 | 1405/05/24 | 1405/05/25 | 1405/05/26 | 1405/05/27 | 1405/05/28 | 1405/05/29 | 1405/05/30 | 1405/05/31 | 1405/06/01 | 1405/06/02 | 1405/06/03 | 1405/06/04 | 1405/06/05 | 1405/06/06 | 1405/06/07 | 1405/06/08 | 1405/06/09 | 1405/06/10 | 1405/06/11 | 1405/06/12 | 1405/06/13 | 1405/06/14 | 1405/06/15 | 1405/06/16 | 1405/06/17 | 1405/06/18 | 1405/06/19 | 1405/06/20 | 1405/06/21
WBS | Task Name | Document No. | time axis 2026-01-11 to 2026-09-12
0 | پروژه احداث نیروگاه خورشیدی 20 مگا واتی زارچ یزد |  | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.02 | 0.02 | 0.03 | 0.03 | 0.04 | 0.05 | 0.05 | 0.06 | 0.07 | 0.07 | 0.08 | 0.08 | 0.09 | 0.1 | 0.11 | 0.11 | 0.12 | 0.13 | 0.14 | 0.16 | 0.17 | 0.19 | 0.2 | 0.23 | 0.25 | 0.27 | 0.3 | 0.32 | 0.34 | 0.37 | 0.4 | 0.42 | 0.45 | 0.46 | 0.48 | 0.5 | 0.52 | 1.38 | 2.25 | 3.13 | 4 | 4.88 | 5.54 | 6.19 | 6.84 | 7.5 | 8.15 | 8.81 | 9.46 | 10.11 | 10.9 | 11.72 | 12.5 | 13.28 | 14.1 | 14.88 | 15.66 | 16.48 | 17.25 | 18.03 | 18.85 | 19.63 | 19.63 | 19.63 | 19.63 | 19.63 | 19.63 | 19.86 | 20.14 | 20.38 | 20.63 | 20.94 | 21.23 | 21.53 | 21.85 | 22.15 | 22.44 | 22.74 | 23.03 | 23.33 | 23.66 | 23.95 | 24.26 | 24.71 | 25.1 | 25.34 | 25.51 | 25.67 | 25.83 | 26.11 | 26.38 | 26.44 | 26.53 | 26.62 | 26.71 | 26.8 | 26.89 | 26.98 | 27.05 | 27.14 | 27.25 | 27.36 | 27.48 | 27.58 | 27.7 | 27.82 | 27.93 | 28.07 | 28.18 | 28.29 | 28.41 | 28.53 | 28.64 | 28.76 | 28.94 | 29.11 | 29.29 | 30.37 | 31.51 | 32.59 | 33.6 | 34.61 | 35.69 | 36.7 | 36.76 | 36.83 | 36.9 | 36.96 | 37.25 | 37.53 | 37.76 | 38.04 | 38.33 | 38.62 | 38.9 | 39.14 | 39.43 | 39.77 | 39.99 | 40.16 | 40.35 | 40.56 | 40.78 | 40.98 | 41.17 | 41.37 | 41.55 | 41.76 | 41.96 | 42.12 | 42.33 | 42.55 | 42.79 | 43.01 | 43.27 | 43.54 | 43.94 | 44.29 | 44.59 | 45.11 | 45.61 | 46.07 | 46.57 | 47.07 | 47.6 | 48.05 | 48.64 | 49.16 | 49.69 | 50.34 | 50.93 | 51.58 | 52.48 | 53.41 | 54.25 | 55.34 | 56.35 | 57.39 | 58.5 | 59.69 | 60.98 | 62.22 | 63.2 | 64.18 | 65.15 | 66.05 | 66.98 | 67.92 | 68.82 | 69.71 | 70.68 | 71.64 | 72.67 | 73.72 | 74.77 | 75.57 | 76.38 | 77.25 | 78.1 | 78.98 | 79.8 | 80.59 | 81.7 | 82.75 | 83.8 | 84.89 | 85.92 | 86.88 | 87.88 | 88.8 | 89.49 | 90.22 | 90.88 | 91.65 | 92.4 | 93.04 | 93.8 | 94.69 | 95.58 | 96.34 | 96.95 | 97.58 | 97.97 | 98.18 | 98.31 | 98.81 | 99.07 | 99.28 | 99.37 | 99.44 | 99.5 | 99.55 | 99.6 | 99.67 | 99.73 | 99.84 | 99.9 | 99.95 | 100
1 | شروع |  | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2 | مایلستون های کلیدی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | دریافت سایر اطلاعات مقدماتی از کارفرما (آزمایش شیمیایی خاک، تست کشش پایه ها و…) |  | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.2 | واریز اولین پیش پرداخت بخش مهندسی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.3 | دریافت مطالعات ژئوتکنیک |  | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.4 | تحویل زمین |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.5 | تاییدیه تجهیزات (پنل، اینورتر و MV Station( |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.6 | اتمام طراحی و اخذ تاییدیه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.7 | اتمام استعلام قیمتی و سفارش گذاری خرید خارجی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.8 | اتمام تامین و تحویل خرید خارجی در سایت پروژه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.9 | اتمام تجهیز کارگاه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.1 | اتمام نصب سازه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.11 | اتمام نصب پنل |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.12 | اتمام ساختمان مانیتورینگ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.13 | اتمام نصب MV Staion |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.14 | اتمام نصب اینورتر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
2.15 | تست پست بالادست |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3 | مهندسی |  | 0 | 0 | 0 | 0.19 | 0.38 | 0.57 | 0.76 | 0.94 | 1.29 | 1.63 | 1.96 | 2.29 | 2.63 | 3.09 | 3.38 | 3.67 | 3.96 | 4.25 | 4.66 | 4.98 | 5.29 | 5.6 | 5.92 | 6.41 | 7.1 | 7.8 | 8.49 | 9.28 | 10.13 | 11.3 | 12.48 | 13.65 | 14.89 | 15.99 | 17.14 | 18.47 | 19.8 | 21.03 | 22.32 | 23.18 | 24.03 | 24.89 | 25.8 | 26.57 | 27.82 | 29.05 | 30.34 | 31.63 | 32.8 | 33.65 | 34.63 | 35.61 | 36.48 | 37.22 | 37.97 | 38.84 | 39.64 | 40.37 | 40.94 | 41.35 | 41.71 | 42.08 | 42.49 | 42.94 | 43.24 | 43.67 | 44.1 | 44.56 | 44.56 | 44.56 | 44.56 | 44.56 | 44.56 | 45.3 | 46.23 | 47.35 | 48.09 | 48.86 | 49.29 | 49.95 | 50.61 | 51.27 | 52.16 | 53.32 | 54.68 | 56.04 | 57.48 | 58.85 | 60.53 | 61.99 | 63.49 | 65.01 | 66.16 | 67.11 | 67.65 | 68.04 | 68.4 | 68.59 | 68.78 | 68.98 | 69.03 | 69.09 | 69.14 | 69.19 | 69.4 | 69.57 | 69.74 | 69.91 | 70.07 | 70.18 | 70.29 | 70.41 | 70.52 | 71.37 | 71.48 | 71.6 | 71.71 | 71.83 | 71.94 | 71.94 | 71.94 | 71.94 | 71.94 | 71.94 | 71.94 | 71.94 | 71.94 | 71.94 | 72.09 | 72.24 | 74.17 | 74.36 | 74.55 | 74.69 | 74.84 | 74.99 | 75.11 | 75.22 | 75.33 | 75.45 | 75.56 | 75.68 | 75.79 | 77.26 | 78 | 78 | 78 | 78 | 78.08 | 78.36 | 78.73 | 79.32 | 79.92 | 80.67 | 81.47 | 82.27 | 83.07 | 83.88 | 84.44 | 84.81 | 85.09 | 85.15 | 85.24 | 85.33 | 85.37 | 85.4 | 85.43 | 85.43 | 85.43 | 85.43 | 85.43 | 85.43 | 85.43 | 85.43 | 85.43 | 85.43 | 85.43 | 85.43 | 85.43 | 85.43 | 85.43 | 85.43 | 85.51 | 85.66 | 85.82 | 85.97 | 87.22 | 87.74 | 88.05 | 88.35 | 88.65 | 88.96 | 89.19 | 89.22 | 89.25 | 89.29 | 89.33 | 89.36 | 89.36 | 89.36 | 89.36 | 89.36 | 89.36 | 89.36 | 89.36 | 89.36 | 90.09 | 90.09 | 90.09 | 90.09 | 90.09 | 90.46 | 92.3 | 92.3 | 93.04 | 93.04 | 93.04 | 93.04 | 93.04 | 93.77 | 93.77 | 93.77 | 94.51 | 94.51 | 94.54 | 94.94 | 95.35 | 95.38 | 96.89 | 97.99 | 98.36 | 98.36 | 98.36 | 99.83 | 99.83 | 99.83 | 99.83 | 99.83 | 99.83 | 99.86 | 99.89 | 99.93 | 99.97 | 100 | 100
3.1 | مدیریت پروژه |  | 0 | 0 | 0 | 1.31 | 2.62 | 3.92 | 5.23 | 6.54 | 7.85 | 9.15 | 10.46 | 11.77 | 13.08 | 15.21 | 17.35 | 19.48 | 21.62 | 23.76 | 25.89 | 28.03 | 30.17 | 32.3 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 34.44 | 35.73 | 37.02 | 38.31 | 39.59 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 42.17 | 42.17 | 42.17 | 42.17 | 42.17 | 42.17 | 43.46 | 44.75 | 46.04 | 47.33 | 47.33 | 47.33 | 47.33 | 47.33 | 47.33 | 47.33 | 47.33 | 47.33 | 47.33 | 47.33 | 47.33 | 48.03 | 48.73 | 49.43 | 50.13 | 50.83 | 51.53 | 52.23 | 52.93 | 53.63 | 54.33 | 55.03 | 55.73 | 57.72 | 59.71 | 61.69 | 63.68 | 65.67 | 66.37 | 67.07 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 67.77 | 69.06 | 70.35 | 71.64 | 72.93 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 74.22 | 75.51 | 76.8 | 78.08 | 79.37 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 80.66 | 81.95 | 83.24 | 84.53 | 85.82 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 87.11 | 88.4 | 89.69 | 90.98 | 92.27 | 93.55 | 93.55 | 93.55 | 93.55 | 93.55 | 93.55 | 93.55 | 93.55 | 93.55 | 93.55 | 93.55 | 94.84 | 96.13 | 97.42 | 98.71 | 100 | 100
3.1.1 | Master Document List | 410-DE-PM-LST-0084 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.1.2 | Time Schedule | 410-DE-PM-REP-0085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.1.3 | Cash Flow | 410-DE-PM-CAF-0086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.1.4 | Monthly Report 410-M-001 | 410-DE-PM-REP-0138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.1.5 | Monthly Report 410-M-002 | 410-DE-PM-REP-0139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.1.6 | Monthly Report 410-M-003 | 410-DE-PM-REP-0140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.1.7 | Monthly Report 410-M-004 | 410-DE-PM-REP-0141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.1.8 | Monthly Report 410-M-005 | 410-DE-PM-REP-0142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.1.9 | Monthly Report 410-M-006 | 410-DE-PM-REP-0143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.1.10 | Monthly Report 410-M-007 | 410-DE-PM-REP-0144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.1.11 | Monthly Report 410-M-008 | 410-DE-PM-REP-0145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100
3.2 | طراحی و اخذ تاییدیه طراحی پایه |  | 0 | 0 | 0 | 1.91 | 3.82 | 5.73 | 7.64 | 9.55 | 13.47 | 17.18 | 20.88 | 24.58 | 28.29 | 33.3 | 36.19 | 39.09 | 41.99 | 44.88 | 49.32 | 51.84 | 54.37 | 56.89 | 59.41 | 62.09 | 63.51 | 64.92 | 66.34 | 67.76 | 69.18 | 69.37 | 69.57 | 69.77 | 69.96 | 70.39 | 70.84 | 71.26 | 71.69 | 72.11 | 73.02 | 73.9 | 74.58 | 75.27 | 75.95 | 76.91 | 77.79 | 78.67 | 79.55 | 80.43 | 81.34 | 82.32 | 83.28 | 84.24 | 85.19 | 86.15 | 87.14 | 87.86 | 88.59 | 89.32 | 90.05 | 90.8 | 91 | 91.19 | 91.39 | 91.58 | 91.78 | 91.78 | 91.78 | 91.78 | 91.78 | 91.78 | 91.78 | 91.78 | 91.78 | 92.24 | 92.7 | 93.16 | 93.62 | 94.08 | 94.59 | 95.05 | 95.51 | 95.97 | 96.43 | 96.89 | 97.17 | 97.45 | 97.73 | 98.01 | 98.29 | 98.6 | 98.88 | 99.16 | 99.44 | 99.72 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1 | ارایه و اخذ تاییدیه دیتاشیت ها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.05 | 10.11 | 15.16 | 20.21 | 25.26 | 30.88 | 35.93 | 40.98 | 46.04 | 51.09 | 56.14 | 56.14 | 56.14 | 56.14 | 56.14 | 56.14 | 56.14 | 56.14 | 56.14 | 56.14 | 56.14 | 56.69 | 57.25 | 57.8 | 58.35 | 58.9 | 59.52 | 60.07 | 60.62 | 61.18 | 61.73 | 62.28 | 62.28 | 62.28 | 62.28 | 62.28 | 62.83 | 63.39 | 63.94 | 64.49 | 65.04 | 67.16 | 69.21 | 71.26 | 73.32 | 75.37 | 78.14 | 80.19 | 82.25 | 84.3 | 86.35 | 88.46 | 89.02 | 89.57 | 90.12 | 90.68 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 91.23 | 92.02 | 92.81 | 93.6 | 94.39 | 95.18 | 96.05 | 96.84 | 97.63 | 98.42 | 99.21 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.1 | Solar Panel Datasheet | 410-BE-EL-DSH-0146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.2 | Inverter Datasheet | 410-BE-EL-DSH-0147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.3 | MV Station Datasheet | 410-BE-EL-DSH-0148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.4 | DC Connection (MC4) Datasheet | 410-BE-EL-DSH-0149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.5 | DC Cable Datasheet | 410-BE-EL-DSH-0150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.6 | LV Cable Datasheet | 410-BE-EL-DSH-0151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.7 | MV Cable Datasheet | 410-BE-EL-DSH-0152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.8 | MV Switchgear (CT, PT, Relay) Datasheet | 410-BE-EL-DSH-0153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.9 | Earthing and Lightning Datasheet | 410-BE-EL-DSH-0154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.10 | Auxiliary Transformer Datasheet | 410-BE-EL-DSH-0155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.11 | UPS and Battery Datasheet | 410-BE-EL-DSH-0156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.12 | Diesel Generator Datasheet | 410-BE-EL-DSH-0157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.13 | Monitoring System Datasheet | 410-BE-TL-DSH-0158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.14 | Data Logger Datasheet | 410-BE-TL-DSH-0159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.15 | Weather Station Datasheet | 410-BE-TL-DSH-0160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.16 | CCTV and NVR Datasheet | 410-BE-TL-DSH-0161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.17 | HVAC Datasheet | 410-BE-ME-DSH-0162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.18 | Piping Material, Plumbing Fittings, Pumps Datasheet | 410-BE-ME-DSH-0163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.19 | Septic Tank Datasheet | 410-BE-ME-DSH-0164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.20 | Water TankDatasheet | 410-BE-ME-DSH-0165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.1.21 | Fire Alarm System Datasheet | 410-BE-SF-DSH-0166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2 | ارایه و اخذ تاییدیه مشخصات |  | 0 | 0 | 0 | 4.89 | 9.79 | 14.68 | 19.58 | 24.47 | 29.91 | 34.81 | 39.7 | 44.6 | 49.49 | 54.39 | 54.39 | 54.39 | 54.39 | 54.39 | 54.97 | 55.56 | 56.15 | 56.74 | 57.33 | 57.98 | 58.57 | 59.16 | 59.75 | 60.34 | 60.93 | 60.93 | 60.93 | 60.93 | 60.93 | 61.51 | 62.1 | 62.69 | 63.28 | 63.87 | 65.68 | 67.44 | 69.19 | 70.94 | 72.69 | 75.16 | 76.91 | 78.66 | 80.41 | 82.16 | 83.98 | 84.57 | 85.16 | 85.74 | 86.33 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 88.1 | 89.28 | 90.45 | 91.63 | 92.81 | 94.11 | 95.29 | 96.47 | 97.65 | 98.82 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.1 | Solar Panel Technical Specification | 410-BE-EL-SPC-0001 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.2 | Inverter Technical Specification | 410-BE-EL-SPC-0002 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.3 | MV Station Technical Specification | 410-BE-EL-SPC-0003 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.4 | DC Connection (MC4) Technical Specification | 410-BE-EL-SPC-0004 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.5 | DC Cable Technical Specification | 410-BE-EL-SPC-0005 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.6 | LV Cable Technical Specification | 410-BE-EL-SPC-0006 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.7 | MV Cable Technical Specification | 410-BE-EL-SPC-0007 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.8 | MV Switchgear (CT, PT, Relay) Technical Specification | 410-BE-EL-SPC-0008 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.9 | Earthing and Lightning Technical Specification | 410-BE-EL-SPC-0009 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.10 | Auxiliary Transformer Technical Specification | 410-BE-EL-SPC-0013 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.11 | UPS and Battery Technical Specification | 410-BE-EL-SPC-0015 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.12 | Diesel Generator Technical Specification | 410-BE-EL-SPC-0016 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.13 | Monitoring System Technical Specification | 410-BE-TL-SPC-0010 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.14 | Data Logger Technical Specification | 410-BE-TL-SPC-0011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.15 | Weather Station Technical Specification | 410-BE-TL-SPC-0012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.16 | CCTV and NVR Technical Specification | 410-BE-TL-SPC-0014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.17 | HVAC Technical Specification | 410-BE-ME-SPC-0017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.18 | Piping Material, Plumbing Fittings, Pumps Technical Specification | 410-BE-ME-SPC-0018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.19 | Septic Tank Technical Specification | 410-DE-ME-SPC-0096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.20 | Water Tank Technical Specification | 410-DE-ME-SPC-0097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.2.21 | Fire Alarm System Technical Specification | 410-BE-SF-SPC-0019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.3 | PVSYST Report | 410-BE-EL-REP-0023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.4 | General Layout | 410-BE-EL-DRW-0021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.5 | General Single Line Diagram (GSLD) | 410-BE-EL-DRW-0020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.2.6 | Plant Detailed Report | 410-BE-EL-REP-0024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 18 | 27 | 36 | 45 | 55 | 64 | 73 | 82 | 91 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3 | طراحی و اخذ تاییدیه عمرانی مطابق MDL ارایه شده |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79 | 1.57 | 2.36 | 3.15 | 4.25 | 5.6 | 6.96 | 8.31 | 9.66 | 11.27 | 12.59 | 15.19 | 18.42 | 21.65 | 24.57 | 27.48 | 29.12 | 30.63 | 32.13 | 33.61 | 34.58 | 35.55 | 36.03 | 36.73 | 37.43 | 37.88 | 38.34 | 38.79 | 39.24 | 39.46 | 39.68 | 40.5 | 41.32 | 41.92 | 42.52 | 43.15 | 43.75 | 44.35 | 44.95 | 45.55 | 46.36 | 46.86 | 47.85 | 48.84 | 49.83 | 49.83 | 49.83 | 49.83 | 49.83 | 49.83 | 50.82 | 52.06 | 52.8 | 53.55 | 54.54 | 55.54 | 57.06 | 58.57 | 60.08 | 61.59 | 63.92 | 66.77 | 69.61 | 72.72 | 75.87 | 79.24 | 82.1 | 84.96 | 87.85 | 90.45 | 92 | 92.78 | 93.56 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 93.81 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.1 | Topography of Field | 410-DE-CV-REP-0087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.2 | Geotechnical Test Report | 410-DE-CV-REP-0088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.3 | Ramming and Pull-Out Test Report | 410-DE-CV-REP-0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.4 | Hydrology Study Report | 410-DE-CV-REP-0090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.5 | Site Fence Detail Drawing | 410-DE-CV-DRW-0091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.6 | Logistic Area | 410-DE-CV-DRW-0092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.7 | Buildings Foundation & Structure Calculation | 410-DE-CV-CAL-0093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.8 | Buildings Foundation & Structure Drawing | 410-DE-CV-DRW-0094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.9 | Parking Foundation & Structure Detail Drawing | 410-DE-CV-DRW-0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.10 | Power Plant Entrance Gate Drawing | 410-DE-CV-DRW-0099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.11 | Parking Architectural Drawing | 410-DE-CV-DRW-0100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.12 | Landscaping Layout | 410-DE-CV-DRW-0101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.13 | Buildings Architectural Detail drawing | 410-DE-CV-DRW-0102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.14 | Fence MTO | 410-DE-CV-MTO-0103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.15 | Site Grading and Leveling | 410-DE-CV-DRW-0104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.16 | Drainage For Insite of Plant & Implementation Detail Drawing | 410-DE-CV-DRW-0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.17 | Flood Managmant For Outsite of Plant & Implementation Detail Drawing | 410-DE-CV-DRW-0106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.18 | Internal Road Layout & Implementation Detail Drawing | 410-DE-CV-DRW-0107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.19 | Access Road Layout & Implementation Detail Drawing | 410-DE-CV-DRW-0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.20 | MV Station Foundation Calculation | 410-DE-CV-CAL-0109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.21 | MV Station Foundation Drawings | 410-DE-CV-DRW-0110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.22 | Auxiliary Transformer Foundation Detail Drawings | 410-DE-CV-DRW-0111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.23 | Calculation Report for Structure | 410-DE-CV-CAL-0112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.24 | Structure Detail Drawings | 410-DE-CV-DRW-0113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.25 | PV Structure Ramming Location Details Drawing (Stacking) | 410-DE-CV-DRW-0114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.26 | Solar Module Structure MTO | 410-DE-CV-MTO-0115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.27 | Table UTM Point | 410-DE-CV-DRW-0116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.28 | Structure, Entrance Gate and Foundation of Building MTO | 410-DE-CV-MTO-0117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.29 | System Drainage Calculation | 410-DE-CV-CAL-0130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.30 | Lighting Foundation Calculation | 410-DE-CV-CAL-0131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.31 | Lightning Foundation Calculation | 410-DE-CV-CAL-0132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.32 | Lightning Foundation Drawing | 410-DE-CV-DRW-0133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.33 | Lighting and CCTV Pole Calculation | 410-DE-CV-CAL-0134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.34 | Septic Tank Detail Drawing | 410-DE-CV-DRW-0135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 60 | 60 | 60 | 60 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.35 | Water Tank Foundation Detail Drawing | 410-DE-CV-DRW-0136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.36 | Calculation for Fence | 410-DE-CV-CAL-0137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.3.37 | Material Requisition for Fence | 410-DE-CV-MRE-0167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4 | طراحی و اخذ تاییدیه الکتریکال مطابق MDL ارایه شده |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17 | 0.33 | 0.5 | 0.67 | 0.84 | 1.95 | 3.07 | 4.19 | 5.3 | 6.42 | 8.57 | 10.71 | 12.86 | 15.01 | 17.15 | 18.32 | 19.48 | 20.64 | 21.81 | 22.99 | 23.88 | 24.78 | 25.67 | 26.57 | 27.43 | 29.52 | 31.61 | 33.71 | 35.81 | 38.11 | 39.42 | 40.73 | 42.04 | 43.2 | 44.35 | 44.98 | 45.6 | 46.23 | 46.66 | 47.09 | 47.65 | 48.21 | 48.76 | 49.48 | 50.11 | 50.56 | 51 | 51.47 | 51.91 | 51.91 | 51.91 | 51.91 | 51.91 | 51.91 | 52.08 | 52.59 | 53.1 | 53.44 | 53.78 | 54.12 | 54.58 | 55.03 | 55.49 | 56.66 | 57.96 | 59.46 | 60.97 | 62.47 | 63.74 | 65.33 | 66.85 | 68.34 | 69.86 | 70.84 | 71.86 | 72.29 | 72.29 | 72.29 | 72.29 | 72.29 | 72.29 | 72.29 | 72.29 | 72.29 | 72.29 | 72.29 | 72.29 | 72.29 | 72.29 | 72.29 | 72.65 | 73.01 | 73.37 | 73.73 | 74.09 | 74.44 | 74.8 | 75.16 | 75.52 | 75.88 | 75.88 | 75.88 | 75.88 | 75.88 | 75.88 | 75.88 | 75.88 | 75.88 | 75.88 | 75.88 | 75.88 | 75.88 | 75.88 | 75.88 | 76.24 | 76.6 | 76.96 | 77.32 | 77.68 | 78.04 | 78.4 | 78.76 | 79.12 | 79.48 | 79.48 | 79.48 | 79.48 | 79.48 | 79.48 | 79.76 | 80.64 | 81.79 | 83.67 | 85.55 | 87.43 | 89.48 | 91.53 | 93.58 | 95.63 | 97.41 | 98.58 | 99.47 | 99.65 | 99.82 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.1 | Solar Module, Connector, Inverter and MV station MTO | 410-BE-EL-MTO-0025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.2 | PV System Calculation Study (String Size, Optimum Tilt and Pitch) | 410-DE-EL-CAL-0022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.3 | Strings Connection Diagram & Inverter Arrangement (DC Side) | 410-DE-EL-DRW-0026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.4 | Module & Table Arrangement (DC Side) | 410-DE-EL-DRW-0027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.5 | DC Cable Calculation | 410-DE-EL-CAL-0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.6 | DC Cable List, Labeling Code and MTO | 410-DE-EL-MTO-0029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.7 | LVAC Cable Calculation | 410-DE-EL-CAL-0030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.8 | LV Cable Termination List and MTO | 410-DE-EL-LST-0031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.9 | LV Cable List, Labeling Code and MTO | 410-DE-EL-MTO-0032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.10 | MV Cable Calculations | 410-DE-EL-CAL-0033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.11 | MV Cable List, Labeling Code and MTO | 410-DE-EL-MTO-0034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.12 | MV Cable Termination List and MTO | 410-DE-EL-LST-0035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.13 | Electrical Cable Route and Section | 410-DE-EL-DRW-0036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.14 | Cable Trench Layout | 410-DE-EL-DRW-0037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.15 | Earthing System Calculation | 410-DE-EL-CAL-0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.16 | Earthing System Layout | 410-DE-EL-DRW-0039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.17 | Lightning Protection Calculation | 410-DE-EL-CAL-0040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.18 | Lightning Protection Layout | 410-DE-EL-DRW-0041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.19 | Earthing and Lightning Protection MTO | 410-DE-EL-MTO-0042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.20 | Protection Single Line Diagram (PSLD) | 410-DE-EL-DRW-0043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.21 | CT and PT Calculations | 410-DE-EL-CAL-0044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.22 | MV Switchgear Logic Diagram | 410-DE-EL-DRW-0045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.23 | Trip Table | 410-DE-EL-REP-0046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.24 | Alarm List | 410-DE-EL-LST-0047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.25 | Indoor and Outdoor Electrical Plan & Details for Building | 410-DE-EL-DRW-0048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.26 | MV Switchgear MTO | 410-DE-EL-MTO-0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.27 | Load List | 410-DE-EL-LST-0050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.28 | LVAC Auxiliary Panel Single Line Diagram | 410-DE-EL-DRW-0051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.29 | UPS Calculation | 410-DE-EL-CAL-0052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.30 | AUX Equipment MTO (AUX Transformer, Diesel, UPS, Battery) | 410-DE-EL-MTO-0053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.31 | Indoor and Outdoor Lighting Calculation | 410-DE-EL-CAL-0058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.32 | Outdoor Lighting Pole Drawing | 410-DE-EL-DRW-0059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.33 | Outdoor Lighting Layout and Switchboard | 410-DE-EL-DRW-0060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.34 | Lighting System MTO | 410-DE-EL-MTO-0061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 67 | 67 | 67 | 67 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.35 | Special Tools | 410-DE-EL-REP-0082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.36 | MV Switchgear Schematic Diagram | 410-DE-EL-DRW-0128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.37 | MV Switchgear Front View Drawing | 410-DE-EL-DRW-0129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.38 | Material Requisition for Indoor Power and Lighting Distribution Panel | 410-DE-EL-MRE-0168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.39 | Material Requisition for Auxiliary Transformer | 410-DE-EL-MRE-0169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.40 | Material Requisition for PCC | 410-DE-EL-MRE-0170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.41 | Material Requisition for MV Switchgear (CT, PT, Relay) | 410-DE-EL-MRE-0171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.42 | Material Requisition for AC Cable | 410-DE-EL-MRE-0172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.43 | Material Requisition for DC Cable | 410-DE-EL-MRE-0173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.44 | Material Requisition for Earthing and Lightning | 410-DE-EL-MRE-0174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.45 | Material Requisition for DC Connection (MC4) | 410-DE-EL-MRE-0175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.46 | Material Requisition for Lighting System | 410-DE-EL-MRE-0176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 25 | 38 | 50 | 63 | 75 | 88 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.47 | Material Requisition for UPS and Battery | 410-DE-EL-MRE-0177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.4.48 | Material Requisition for Diesel Generator | 410-BE-EL-MRE-0186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.5 | طراحی و اخذ تاییدیه مکانیکال مطابق MDL ارایه شده |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.15 | 2.29 | 3.44 | 4.59 | 5.73 | 6.88 | 8.02 | 9.17 | 10.32 | 11.46 | 14.33 | 17.2 | 20.06 | 22.93 | 25.65 | 28.38 | 31.1 | 33.83 | 33.83 | 33.83 | 33.83 | 33.83 | 33.83 | 33.83 | 33.83 | 33.83 | 33.83 | 33.83 | 33.83 | 33.83 | 33.83 | 33.83 | 33.83 | 41.43 | 49.26 | 64.47 | 72.31 | 79.91 | 79.91 | 79.91 | 79.91 | 79.91 | 79.91 | 79.91 | 79.91 | 79.91 | 79.91 | 79.91 | 79.91 | 79.91 | 79.91 | 79.91 | 79.91 | 82.07 | 84.22 | 86.38 | 91.4 | 94.27 | 97.13 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.5.1 | Solar Panel Cleaning & Maintenance Procedures | 410-DE-ME-REP-0062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.5.2 | HVAC Equipment Calculation | 410-DE-ME-CAL-0066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.5.3 | HVAC Equipment Layout for Building | 410-DE-ME-DRW-0067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.5.4 | HVAC and Piping System MTO | 410-DE-ME-MTO-0068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.5.5 | Mechanical Drawing (Water Supply and Sewage Systems) | 410-DE-ME-DRW-0095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.5.6 | Material Requisition for Septic Tank | 410-BE-ME-MRE-0183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.5.7 | Material Requisition for Water | 410-BE-ME-MRE-0184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.6 | طراحی و اخذ تاییدیه ایمنی مطابق MDL ارایه شده |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.81 | 3.49 | 5.3 | 6.98 | 8.79 | 10.47 | 12.28 | 13.95 | 17.3 | 20.51 | 23.86 | 27.07 | 30.56 | 33.77 | 37.12 | 40.33 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 41.86 | 43.26 | 44.65 | 46.05 | 47.44 | 48.84 | 50.23 | 51.63 | 53.02 | 54.42 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 55.81 | 58.02 | 62.44 | 66.86 | 71.28 | 75.7 | 80.12 | 84.53 | 88.95 | 93.37 | 97.79 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.6.1 | Fire Fighting Equipment Arrangement of MV Switchgear Buildings | 410-DE-SF-DRW-0069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 25 | 38 | 50 | 63 | 75 | 88 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.6.2 | Outdoor Fire Fighting Equipment & Shelter Arrangement | 410-DE-SF-DRW-0070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.6.3 | Fire Alarm System Layout and Block Diagram | 410-DE-SF-DRW-0071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 25 | 38 | 50 | 63 | 75 | 88 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.6.4 | Fire and Safety and F & G System MTO | 410-DE-SF-MTO-0072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.6.5 | Material Requisition for Fire Alarm System | 410-DE-SF-MRE-0181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.6.6 | Material Requisition for Fire Fighting Equipment Arrangement | 410-DE-SF-MRE-0182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.7 | طراحی و اخذ تاییدیه ارتباطی مطابق MDL ارایه شده |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 2.8 | 4.19 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 7.58 | 11.46 | 15.33 | 19.21 | 21.1 | 22.99 | 24.88 | 26.77 | 28.66 | 28.66 | 28.66 | 30.85 | 33.03 | 35.22 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 37.4 | 38.12 | 38.83 | 39.55 | 40.27 | 40.98 | 41.7 | 42.42 | 43.13 | 43.85 | 46.46 | 48.35 | 50.24 | 52.13 | 52.13 | 52.13 | 52.13 | 52.13 | 52.13 | 52.13 | 52.13 | 52.13 | 52.13 | 52.13 | 52.13 | 52.13 | 54.52 | 56.91 | 59.31 | 61.7 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 64.09 | 66.49 | 68.88 | 71.28 | 73.67 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 76.06 | 78.46 | 80.85 | 83.24 | 85.64 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 88.03 | 90.43 | 92.82 | 95.21 | 97.61 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.7.1 | CCTV System Block Diagram | 410-DE-TL-DRW-0054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.7.2 | CCTV System Arrangement & Layout | 410-DE-TL-DRW-0055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.7.3 | CCTV Pole Detail Drawing, Switchboard, CAFU Details | 410-DE-TL-DRW-0056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.7.4 | CCTV System MTO | 410-DE-TL-MTO-0057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.7.5 | SCADA System I/O List | 410-DE-TL-LST-0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.7.6 | Monitoring System Overall Diagram | 410-DE-TL-DRW-0064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.7.7 | Telecommunication and Monitoring System MTO | 410-DE-TL-MTO-0065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.7.8 | Material Requisition forTelecommunication and Monitoring Cable | 410-DE-TL-MRE-0178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.7.9 | Material Requisition forFiber Optics | 410-BE-TL-MRE-0179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.7.10 | Material Requisition for CCTV and NVR | 410-DE-TL-MRE-0180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.7.11 | Material Requisition for Weather Station | 410-BE-TL-MRE-0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8 | مستندات حوزه کیفیت مطابق MDL ارایه شده |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 27.5 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 35 | 35 | 35 | 35 | 35 | 37.5 | 50 | 50 | 55 | 55 | 55 | 55 | 55 | 60 | 60 | 60 | 65 | 65 | 65 | 67.5 | 70 | 70 | 80 | 87.5 | 90 | 90 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.1 | Solar Panel Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.2 | Inverter Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.3 | MV Station Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.4 | UPS Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.5 | AUX Transformer Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.6 | Diesel Generator Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.7 | Weather Station Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.8 | Solar Structure Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.9 | SCADA and Monitoring System Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.10 | Project O&M General Instructions | 410-DE-QA-REP-0083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.11 | Test Report of Solar Structure | 410-DE-QA-REP-0118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.12 | Test Reports for PV Modules | 410-DE-QA-REP-0119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.13 | Test Reports for Inverter | 410-DE-QA-REP-0120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.14 | Test Reports for MV Sation | 410-DE-QA-REP-0121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.15 | Test Reports for AC and DC Cables | 410-DE-QA-REP-0122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.16 | Test Reports for Diesel Generators | 410-DE-QA-REP-0123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.17 | Test Reports for AUX Transformer | 410-DE-QA-REP-0124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.18 | Test Reports for Earthing and Ligthtning | 410-DE-QA-REP-0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.19 | Test Reports for MV Switchgear (CT, PT, Relay, …) | 410-DE-QA-REP-0126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.20 | Test Reports for UPS and Battery | 410-DE-QA-REP-0127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3.8.21 | کدگذاری و تحویل مستندات پروژه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4 | تامین و حمل کالا تجهیزات |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 2.42 | 3.64 | 4.85 | 6.06 | 6.97 | 7.88 | 8.79 | 9.7 | 10.61 | 11.52 | 12.43 | 13.33 | 14.44 | 15.59 | 16.69 | 17.79 | 18.95 | 20.05 | 21.15 | 22.31 | 23.41 | 24.51 | 25.67 | 26.77 | 26.77 | 26.77 | 26.77 | 26.77 | 26.77 | 27.08 | 27.45 | 27.77 | 28.1 | 28.52 | 28.92 | 29.33 | 29.77 | 30.17 | 30.57 | 30.96 | 31.33 | 31.71 | 32.13 | 32.51 | 32.88 | 33.31 | 33.64 | 33.76 | 33.89 | 34.01 | 34.13 | 34.25 | 34.37 | 34.45 | 34.57 | 34.69 | 34.82 | 34.94 | 35.06 | 35.18 | 35.26 | 35.38 | 35.52 | 35.66 | 35.81 | 35.95 | 36.11 | 36.27 | 36.4 | 36.56 | 36.72 | 36.85 | 37.01 | 37.17 | 37.31 | 37.47 | 37.62 | 37.76 | 37.92 | 39.35 | 40.88 | 42.32 | 43.75 | 45.18 | 46.72 | 48.15 | 48.17 | 48.23 | 48.29 | 48.36 | 48.61 | 48.86 | 49.09 | 49.33 | 49.56 | 49.8 | 50.04 | 50.28 | 50.53 | 50.8 | 50.93 | 51.05 | 51.18 | 51.3 | 51.44 | 51.56 | 51.71 | 51.79 | 51.84 | 51.92 | 52.01 | 52.07 | 52.17 | 52.26 | 52.4 | 52.57 | 52.75 | 52.96 | 53.2 | 53.45 | 53.63 | 54.06 | 54.52 | 54.86 | 55.33 | 55.8 | 56.24 | 56.62 | 57.16 | 57.64 | 58.15 | 58.77 | 59.31 | 59.97 | 60.99 | 61.99 | 62.93 | 64.16 | 65.35 | 66.56 | 67.82 | 69.26 | 70.77 | 72.32 | 73.51 | 74.64 | 75.88 | 77.08 | 78.26 | 79.5 | 80.62 | 81.72 | 83.01 | 84.21 | 85.52 | 86.93 | 88.29 | 89.3 | 90.32 | 91.33 | 92.36 | 93.39 | 94.29 | 95.23 | 95.76 | 96.28 | 96.81 | 97.34 | 97.83 | 98.17 | 98.48 | 98.79 | 99.02 | 99.18 | 99.32 | 99.46 | 99.6 | 99.74 | 99.89 | 99.97 | 99.97 | 99.97 | 99.97 | 99.97 | 99.98 | 99.98 | 99.98 | 99.98 | 99.99 | 99.99 | 99.99 | 99.99 | 99.99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1 | خرید و حمل داخلی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32 | 0.74 | 1.06 | 1.38 | 1.8 | 2.12 | 2.44 | 2.86 | 3.18 | 3.5 | 3.92 | 4.24 | 4.24 | 4.24 | 4.24 | 4.24 | 4.24 | 4.56 | 4.98 | 5.3 | 5.72 | 6.23 | 6.7 | 7.17 | 7.72 | 8.18 | 8.65 | 9.16 | 9.59 | 10.02 | 10.52 | 10.95 | 11.38 | 11.88 | 12.31 | 12.31 | 12.31 | 12.31 | 12.31 | 12.31 | 12.31 | 12.31 | 12.31 | 12.31 | 12.31 | 12.31 | 12.31 | 12.31 | 12.31 | 12.31 | 12.34 | 12.37 | 12.39 | 12.42 | 12.45 | 12.47 | 12.5 | 12.53 | 12.56 | 12.58 | 12.61 | 12.64 | 12.66 | 12.69 | 12.72 | 12.74 | 12.77 | 12.8 | 12.83 | 12.86 | 12.89 | 12.92 | 12.96 | 12.99 | 13.02 | 13.13 | 13.23 | 13.33 | 13.76 | 14.18 | 14.57 | 14.97 | 15.36 | 15.76 | 16.16 | 16.57 | 16.98 | 17.45 | 17.65 | 17.86 | 18.07 | 18.27 | 18.52 | 18.72 | 18.96 | 19.09 | 19.18 | 19.32 | 19.46 | 19.57 | 19.73 | 19.88 | 20.12 | 20.41 | 20.7 | 21.06 | 21.47 | 21.88 | 22.19 | 22.91 | 23.68 | 24.26 | 25.04 | 25.82 | 26.56 | 27.21 | 28.11 | 28.91 | 29.77 | 30.81 | 31.73 | 32.83 | 34.53 | 36.21 | 37.79 | 39.85 | 41.86 | 43.89 | 45.99 | 48.41 | 50.95 | 53.54 | 55.55 | 57.45 | 59.53 | 61.53 | 63.52 | 65.61 | 67.47 | 69.33 | 71.48 | 73.5 | 75.69 | 78.06 | 80.36 | 82.05 | 83.76 | 85.45 | 87.18 | 88.91 | 90.42 | 91.99 | 92.88 | 93.76 | 94.65 | 95.54 | 96.36 | 96.92 | 97.45 | 97.96 | 98.35 | 98.62 | 98.86 | 99.1 | 99.34 | 99.57 | 99.82 | 99.94 | 99.95 | 99.95 | 99.95 | 99.96 | 99.96 | 99.97 | 99.97 | 99.97 | 99.98 | 99.98 | 99.99 | 99.99 | 99.99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.1 | خرید مصالح و تجهیز کارگاه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.45 | 5.62 | 8.07 | 10.53 | 13.69 | 16.15 | 18.6 | 21.77 | 24.22 | 26.67 | 29.84 | 32.3 | 32.3 | 32.3 | 32.3 | 32.3 | 32.3 | 34.75 | 37.92 | 40.37 | 43.63 | 47.49 | 51.06 | 54.63 | 58.8 | 62.37 | 65.94 | 69.8 | 73.07 | 76.33 | 80.19 | 83.45 | 86.71 | 90.58 | 93.84 | 93.84 | 93.84 | 93.84 | 93.84 | 93.84 | 93.84 | 93.84 | 93.84 | 93.84 | 93.84 | 93.84 | 93.84 | 93.84 | 93.84 | 93.84 | 94.02 | 94.27 | 94.45 | 94.64 | 94.89 | 95.07 | 95.25 | 95.5 | 95.69 | 95.87 | 96.12 | 96.3 | 96.49 | 96.73 | 96.92 | 97.1 | 97.35 | 97.53 | 97.72 | 97.97 | 98.15 | 98.34 | 98.58 | 98.77 | 98.95 | 99.2 | 99.38 | 99.57 | 99.82 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.1.1 | مصالح ساختمانی و ملزومات عمرانی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 10 | 13 | 17 | 20 | 23 | 27 | 30 | 33 | 37 | 40 | 40 | 40 | 40 | 40 | 40 | 43 | 47 | 50 | 53 | 57 | 60 | 63 | 67 | 70 | 73 | 77 | 80 | 83 | 87 | 90 | 93 | 97 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.1.2 | مصالح ،تجهیزات و ملزومات برقی ساختمان ها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 10 | 13 | 17 | 20 | 23 | 27 | 30 | 33 | 37 | 40 | 43 | 47 | 50 | 53 | 57 | 60 | 63 | 67 | 70 | 73 | 77 | 80 | 83 | 87 | 90 | 93 | 97 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.1.3 | تانک سپتیک و دو مخزن 10 هزار لیتری سه لایه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.1.4 | کلیه تجهیزات و ملزومات اداری |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13 | 20 | 27 | 33 | 40 | 47 | 53 | 60 | 67 | 73 | 80 | 80 | 80 | 80 | 80 | 80 | 87 | 93 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.1.5 | سایر خرید تجهیز کارگاه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13 | 20 | 27 | 33 | 40 | 47 | 53 | 60 | 67 | 73 | 80 | 87 | 93 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.2 | فنس پیرامونی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.65 | 3.35 | 5 | 13 | 21 | 29 | 37 | 45 | 53 | 61 | 69 | 77 | 85 | 87.1 | 89.35 | 91.45 | 93.55 | 95.65 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.2.1 | سفارش گذاری فنس پیرامونی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.2.2 | ساخت و بازرسی فنس پیرامونی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.2.3 | حمل فنس پیرامونی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.3 | تابلو های توزیع داخلی و روشنایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 13 | 17 | 21 | 25 | 29 | 33 | 37 | 41 | 45 | 49 | 53 | 57 | 61 | 65 | 69 | 73 | 77 | 81 | 85 | 87.1 | 89.35 | 91.45 | 93.55 | 95.65 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.3.1 | سفارش گذاری تابلو های توزیع داخلی و روشنایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.3.2 | ساخت و بازرسی تابلو های توزیع داخلی و روشنایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.3.3 | حمل تابلو های توزیع داخلی و روشنایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.4 | ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.65 | 3.35 | 5 | 8.2 | 11.4 | 14.6 | 17.8 | 21 | 24.2 | 27.4 | 30.6 | 33.8 | 37 | 40.2 | 43.4 | 46.6 | 49.8 | 53 | 56.2 | 59.4 | 62.6 | 65.8 | 69 | 74.3 | 79.75 | 85.05 | 90.35 | 95.65 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.4.1 | سفارش گذاری ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.4.2 | ساخت و بازرسی ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 12 | 16 | 20 | 24 | 28 | 32 | 36 | 40 | 44 | 48 | 52 | 56 | 60 | 64 | 68 | 72 | 76 | 80 | 84 | 88 | 92 | 96 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.4.3 | حمل ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.5 | تابلوهای پست سوییچگیر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6.6 | 7.4 | 9 | 10.6 | 11.4 | 13 | 14.6 | 15.4 | 17 | 18.6 | 19.4 | 21 | 22.6 | 23.4 | 25 | 26.6 | 27.4 | 29 | 30.6 | 31.4 | 33 | 34.6 | 35.4 | 37 | 38.6 | 39.4 | 41 | 42.6 | 43.4 | 45 | 46.6 | 47.4 | 49 | 50.6 | 51.4 | 53 | 54.6 | 55.4 | 57 | 58.6 | 59.4 | 61 | 62.6 | 63.4 | 65 | 66.6 | 67.4 | 69 | 70.6 | 71.4 | 73 | 74.6 | 75.4 | 77 | 78.6 | 79.4 | 81 | 82.6 | 83.4 | 85 | 86.05 | 86.95 | 88 | 89.05 | 89.95 | 91 | 92.05 | 92.95 | 94 | 95.05 | 95.95 | 97 | 98.05 | 98.95 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.5.1 | سفارش گذاری تابلوهای پست سوییچگیر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.5.2 | ساخت و بازرسی تابلوهای پست سوییچگیر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 5 | 7 | 8 | 10 | 12 | 13 | 15 | 17 | 18 | 20 | 22 | 23 | 25 | 27 | 28 | 30 | 32 | 33 | 35 | 37 | 38 | 40 | 42 | 43 | 45 | 47 | 48 | 50 | 52 | 53 | 55 | 57 | 58 | 60 | 62 | 63 | 65 | 67 | 68 | 70 | 72 | 73 | 75 | 77 | 78 | 80 | 82 | 83 | 85 | 87 | 88 | 90 | 92 | 93 | 95 | 97 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.5.3 | حمل تابلوهای پست سوییچگیر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13 | 20 | 27 | 33 | 40 | 47 | 53 | 60 | 67 | 73 | 80 | 87 | 93 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.6 | ct& pt |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 13 | 17 | 21 | 25 | 29 | 33 | 37 | 41 | 45 | 49 | 53 | 57 | 61 | 65 | 69 | 73 | 77 | 81 | 85 | 87.1 | 89.35 | 91.45 | 93.55 | 95.65 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.6.1 | سفارش گذاری ct& pt |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.6.2 | ساخت و بازرسی ct& pt |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.6.3 | حمل ct& pt |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.7 | AC/LV و AC/MV کابل های |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 1.45 | 2.15 | 2.85 | 3.55 | 4.3 | 5 | 7.4 | 9.8 | 11.4 | 13.8 | 16.2 | 18.6 | 20.2 | 22.6 | 25 | 27.4 | 29.8 | 31.4 | 33.8 | 36.2 | 38.6 | 40.2 | 42.6 | 45 | 47.4 | 49.8 | 51.4 | 53.8 | 56.2 | 58.6 | 60.2 | 62.6 | 65 | 67.4 | 69.8 | 71.4 | 73.8 | 76.2 | 78.6 | 81.7 | 85.6 | 89.5 | 91 | 92.5 | 94 | 95.5 | 97 | 98.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.7.1 | AC/LV و AC/MV سفارش گذاری کابل های |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.7.2 | AC/LV و AC/MV ساخت و بازرسی کابل های |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 8 | 11 | 14 | 17 | 19 | 22 | 25 | 28 | 31 | 33 | 36 | 39 | 42 | 44 | 47 | 50 | 53 | 56 | 58 | 61 | 64 | 67 | 69 | 72 | 75 | 78 | 81 | 83 | 86 | 89 | 92 | 94 | 97 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.7.3 | AC/LV و AC/MV حمل کابل های |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.8 | DC کابل های |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.65 | 3.35 | 5 | 13 | 21 | 29 | 37 | 45 | 53 | 61 | 69 | 77 | 85 | 87.1 | 89.35 | 91.45 | 93.55 | 95.65 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.8.1 | DC سفارش گذاری کابل های |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.8.2 | DC ساخت و بازرسی کابل های |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.8.3 | DC حمل کابل های |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.9 | کابل های ارتباطی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.65 | 3.35 | 5 | 13 | 21 | 29 | 37 | 45 | 53 | 61 | 69 | 77 | 85 | 87.1 | 89.35 | 91.45 | 93.55 | 95.65 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.9.1 | سفارش گذاری کابل های ارتباطی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.9.2 | ساخت و بازرسی کابل های ارتباطی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.9.3 | حمل کابل های ارتباطی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.10 | Fiber Optics (انتقال دیتا داخلی نیروگاه) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 7.4 | 10.6 | 13 | 15.4 | 18.6 | 21 | 23.4 | 26.6 | 29 | 31.4 | 34.6 | 37 | 39.4 | 42.6 | 45 | 47.4 | 50.6 | 53 | 55.4 | 58.6 | 61 | 63.4 | 66.6 | 69 | 71.4 | 74.6 | 77 | 79.4 | 82.6 | 85 | 86.5 | 88 | 89.5 | 91 | 92.5 | 94 | 95.5 | 97 | 98.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.10.1 | Fiber Optics سفارش گذاری (انتقال دیتا داخلی نیروگاه) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.10.2 | Fiber Optics ساخت و بازرسی (انتقال دیتا داخلی نیروگاه) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 10 | 13 | 17 | 20 | 23 | 27 | 30 | 33 | 37 | 40 | 43 | 47 | 50 | 53 | 57 | 60 | 63 | 67 | 70 | 73 | 77 | 80 | 83 | 87 | 90 | 93 | 97 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.10.3 | Fiber Optics حمل (انتقال دیتا داخلی نیروگاه) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.11 | کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 7.4 | 10.6 | 13 | 15.4 | 18.6 | 21 | 23.4 | 26.6 | 29 | 31.4 | 34.6 | 37 | 39.4 | 42.6 | 45 | 47.4 | 50.6 | 53 | 55.4 | 58.6 | 61 | 63.4 | 66.6 | 69 | 71.4 | 74.6 | 77 | 79.4 | 82.6 | 85 | 87.1 | 89.35 | 91.45 | 93.55 | 95.65 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.11.1 | سفارش گذاری کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.11.2 | ساخت و بازرسی کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 10 | 13 | 17 | 20 | 23 | 27 | 30 | 33 | 37 | 40 | 43 | 47 | 50 | 53 | 57 | 60 | 63 | 67 | 70 | 73 | 77 | 80 | 83 | 87 | 90 | 93 | 97 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.11.3 | حمل کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.12 | MC4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 9 | 13 | 17 | 21 | 25 | 29 | 33 | 37 | 41 | 45 | 49 | 53 | 57 | 61 | 65 | 69 | 73 | 77 | 81 | 85 | 87.1 | 89.35 | 91.45 | 93.55 | 95.65 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.12.1 | MC4 سفارش گذاری |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.12.2 | MC4 ساخت و بازرسی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.12.3 | MC4 حمل |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.13 | و تجهیزات جانبیCCTV سیستم |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 1.45 | 2.15 | 2.85 | 3.55 | 4.3 | 5 | 7.4 | 9.8 | 12.2 | 13.8 | 16.2 | 18.6 | 21 | 23.4 | 25.8 | 28.2 | 29.8 | 32.2 | 34.6 | 37 | 39.4 | 41.8 | 44.2 | 45.8 | 48.2 | 50.6 | 53 | 55.4 | 57.8 | 60.2 | 61.8 | 64.2 | 66.6 | 69 | 71.4 | 73.8 | 76.2 | 77.8 | 80.2 | 82.6 | 85 | 86.5 | 88 | 89.5 | 91 | 92.5 | 94 | 95.5 | 97 | 98.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.13.1 | و تجهیزات جانبیCCTV سفارش گذاری سیستم |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.13.2 | و تجهیزات جانبیCCTV ساخت و بازرسی سیستم |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 9 | 11 | 14 | 17 | 20 | 23 | 26 | 29 | 31 | 34 | 37 | 40 | 43 | 46 | 49 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 71 | 74 | 77 | 80 | 83 | 86 | 89 | 91 | 94 | 97 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.13.3 | و تجهیزات جانبیCCTV حمل سیستم |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.14 | تجهیزات سیستم روشنایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2.99 | 3.99 | 4.99 | 7.39 | 8.99 | 11.39 | 12.99 | 15.39 | 16.99 | 19.39 | 20.99 | 23.39 | 24.99 | 27.39 | 28.99 | 31.39 | 33 | 35.4 | 37 | 39.4 | 41 | 43.4 | 45 | 47.4 | 49 | 51.4 | 53 | 55.4 | 57 | 59.4 | 61 | 63.4 | 65 | 67.4 | 69 | 71.4 | 73 | 75.4 | 77 | 79.4 | 81 | 83.4 | 85.01 | 86.5 | 88 | 89.5 | 91 | 92.5 | 94 | 95.5 | 97 | 98.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.14.1 | سفارش گذاری تجهیزات سیستم روشنایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.14.2 | ساخت و بازرسی تجهیزات سیستم روشنایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 8 | 10 | 13 | 15 | 18 | 20 | 23 | 25 | 28 | 30 | 33 | 35 | 38 | 40 | 43 | 45 | 48 | 50 | 53 | 55 | 58 | 60 | 63 | 65 | 68 | 70 | 73 | 75 | 78 | 80 | 83 | 85 | 88 | 90 | 93 | 95 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.14.3 | حمل تجهیزات سیستم روشنایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.15 | UPS سیستم |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1.5 | 2 | 2.5 | 2.99 | 3.49 | 3.99 | 4.49 | 4.99 | 8.99 | 12.99 | 16.99 | 20.99 | 24.99 | 28.99 | 32.99 | 37 | 41 | 45 | 49 | 53 | 57 | 61 | 65 | 69 | 73 | 77 | 81 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 87.1 | 89.35 | 91.45 | 93.55 | 95.65 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.15.1 | UPS سفارش گذاری سیستم |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.15.2 | UPS خرید سیستم |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.15.3 | UPS حمل سیستم |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.16 | سیستم اعلان حریق و تجهیزات جانبی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.47 | 4.95 | 16.15 | 28.16 | 39.36 | 50.57 | 61.77 | 73.78 | 84.98 | 87.09 | 89.34 | 91.44 | 93.54 | 95.65 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.16.1 | سفارش گذاری سیستم اعلان حریق و تجهیزات جانبی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.16.2 | ساخت و بازرسی سیستم اعلان حریق و تجهیزات جانبی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.16.3 | حمل سیستم اعلان حریق و تجهیزات جانبی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.17 | سیستم اطفا حریق و تجهیزات جانبی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.65 | 3.35 | 5 | 13 | 21 | 29 | 37 | 45 | 53 | 61 | 69 | 77 | 85 | 87.1 | 89.35 | 91.45 | 93.55 | 95.65 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.17.1 | سفارش گذاری سیستم اطفا حریق و تجهیزات جانبی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.17.2 | ساخت و بازرسی سیستم اطفا حریق و تجهیزات جانبی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.17.3 | حمل سیستم اطفا حریق و تجهیزات جانبی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.18 | ایستگاه هواشناسی و سنسورها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.67 | 3.38 | 5.05 | 13.04 | 21.04 | 29.03 | 37.02 | 45.01 | 53.01 | 61 | 68.99 | 76.98 | 84.97 | 87.08 | 89.33 | 91.44 | 93.54 | 95.64 | 97.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.18.1 | سفارش گذاری ایستگاه هواشناسی و سنسورها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.18.2 | ساخت و بازرسی ایستگاه هواشناسی و سنسورها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.18.3 | حمل ایستگاه هواشناسی و سنسورها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.19 | لوازم یدکی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 5 | 7 | 8 | 9 | 11 | 12 | 13 | 15 | 16 | 17 | 19 | 20 | 21 | 23 | 24 | 25 | 27 | 28 | 29 | 31 | 32 | 33 | 35 | 36 | 37 | 39 | 40 | 41 | 43 | 44 | 45 | 47 | 48 | 49 | 51 | 52 | 53 | 55 | 56 | 57 | 59 | 60 | 61 | 63 | 64 | 65 | 67 | 68 | 69 | 71 | 72 | 73 | 75 | 76 | 77 | 79 | 80 | 81 | 83 | 84 | 85 | 87 | 88 | 89 | 91 | 92 | 93 | 95 | 96 | 97 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.1.19.1 | لوازم یدکی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 5 | 7 | 8 | 9 | 11 | 12 | 13 | 15 | 16 | 17 | 19 | 20 | 21 | 23 | 24 | 25 | 27 | 28 | 29 | 31 | 32 | 33 | 35 | 36 | 37 | 39 | 40 | 41 | 43 | 44 | 45 | 47 | 48 | 49 | 51 | 52 | 53 | 55 | 56 | 57 | 59 | 60 | 61 | 63 | 64 | 65 | 67 | 68 | 69 | 71 | 72 | 73 | 75 | 76 | 77 | 79 | 80 | 81 | 83 | 84 | 85 | 87 | 88 | 89 | 91 | 92 | 93 | 95 | 96 | 97 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2 | خرید خارجی، حمل بین المللی و ترخیص |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 9 | 12 | 15 | 17.25 | 19.5 | 21.75 | 24 | 26.25 | 28.5 | 30.75 | 33 | 35.25 | 37.5 | 39.75 | 42 | 44.25 | 46.5 | 48.75 | 51 | 53.25 | 55.5 | 57.75 | 60 | 60 | 60 | 60 | 60 | 60 | 60.3 | 60.6 | 60.9 | 61.1 | 61.4 | 61.7 | 62 | 62.3 | 62.6 | 62.9 | 63.1 | 63.4 | 63.7 | 64 | 64.3 | 64.6 | 64.9 | 65.1 | 65.4 | 65.7 | 66 | 66.3 | 66.6 | 66.9 | 67.1 | 67.4 | 67.7 | 68 | 68.3 | 68.6 | 68.9 | 69.1 | 69.4 | 69.7 | 70 | 70.35 | 70.65 | 71 | 71.35 | 71.65 | 72 | 72.35 | 72.65 | 73 | 73.35 | 73.65 | 74 | 74.35 | 74.65 | 75 | 78.5 | 82.25 | 85.75 | 89.25 | 92.75 | 96.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.1 | خرید سازه های نگهدارنده پنل ها و اینورترها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 9 | 12 | 15 | 17.25 | 19.5 | 21.75 | 24 | 26.25 | 28.5 | 30.75 | 33 | 35.25 | 37.5 | 39.75 | 42 | 44.25 | 46.5 | 48.75 | 51 | 53.25 | 55.5 | 57.75 | 60 | 60 | 60 | 60 | 60 | 60 | 60.3 | 60.6 | 60.9 | 61.1 | 61.4 | 61.7 | 62 | 62.3 | 62.6 | 62.9 | 63.1 | 63.4 | 63.7 | 64 | 64.3 | 64.6 | 64.9 | 65.1 | 65.4 | 65.7 | 66 | 66.3 | 66.6 | 66.9 | 67.1 | 67.4 | 67.7 | 68 | 68.3 | 68.6 | 68.9 | 69.1 | 69.4 | 69.7 | 70 | 70.35 | 70.65 | 71 | 71.35 | 71.65 | 72 | 72.35 | 72.65 | 73 | 73.35 | 73.65 | 74 | 74.35 | 74.65 | 75 | 78.5 | 82.25 | 85.75 | 89.25 | 92.75 | 96.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.1.1 | استعلام قیمت و سفارش گذاری سازه های نگهدارنده |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.1.2 | ساخت سازه های نگهدارنده و بازرسی قبل حمل |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.1.3 | حمل خارجی سازه های نگهدارنده |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 9 | 11 | 14 | 17 | 20 | 23 | 26 | 29 | 31 | 34 | 37 | 40 | 43 | 46 | 49 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 71 | 74 | 77 | 80 | 83 | 86 | 89 | 91 | 94 | 97 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.1.4 | ترخیص سازه های نگهدارنده |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13 | 20 | 27 | 33 | 40 | 47 | 53 | 60 | 67 | 73 | 80 | 87 | 93 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.1.5 | حمل داخلی سازه های نگهدارنده و تحویل در سایت |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.2 | خرید پنل های خورشیدی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.2.1 | استعلام قیمت و ثبت سفارش پنل های خورشیدی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.2.2 | ساخت پنل های خورشیدی و بازرسی قبل حمل |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 10 | 13 | 17 | 20 | 23 | 27 | 30 | 33 | 37 | 40 | 43 | 47 | 50 | 53 | 57 | 60 | 63 | 67 | 67 | 67 | 67 | 67 | 67 | 70 | 73 | 77 | 80 | 83 | 87 | 90 | 93 | 97 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.2.3 | حمل خارجی پنل های خورشیدی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 7 | 9 | 11 | 13 | 16 | 18 | 20 | 22 | 24 | 27 | 29 | 31 | 33 | 36 | 38 | 40 | 42 | 44 | 47 | 49 | 51 | 53 | 56 | 58 | 60 | 62 | 64 | 67 | 69 | 71 | 73 | 76 | 78 | 80 | 82 | 84 | 87 | 89 | 91 | 93 | 96 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.2.4 | ترخیص پنل های خورشیدی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 21 | 29 | 36 | 43 | 50 | 57 | 64 | 71 | 79 | 86 | 93 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.2.5 | حمل داخلی پنل های خورشیدی و تحویل در سایت |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.3 | خرید اینورترهای خورشیدی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.3.1 | استعلام قیمت و ثبت سفارش اینورترهای خورشیدی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.3.2 | ساخت اینورترهای خورشیدی و بازرسی قبل حمل |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 5 | 7 | 8 | 10 | 11 | 12 | 14 | 15 | 16 | 18 | 19 | 21 | 22 | 23 | 25 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 29 | 30 | 32 | 33 | 34 | 36 | 37 | 38 | 40 | 41 | 42 | 44 | 45 | 47 | 48 | 49 | 51 | 52 | 53 | 55 | 56 | 58 | 59 | 60 | 62 | 63 | 64 | 66 | 67 | 68 | 70 | 71 | 73 | 74 | 75 | 77 | 78 | 79 | 81 | 82 | 84 | 85 | 86 | 88 | 89 | 90 | 92 | 93 | 95 | 96 | 97 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.3.3 | حمل خارجی اینورترهای خورشیدی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 7 | 9 | 11 | 13 | 16 | 18 | 20 | 22 | 24 | 27 | 29 | 31 | 33 | 36 | 38 | 40 | 42 | 44 | 47 | 49 | 51 | 53 | 56 | 58 | 60 | 62 | 64 | 67 | 69 | 71 | 73 | 76 | 78 | 80 | 82 | 84 | 87 | 89 | 91 | 93 | 96 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.3.4 | ترخیص اینورترهای خورشیدی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 21 | 29 | 36 | 43 | 50 | 57 | 64 | 71 | 79 | 86 | 93 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.3.5 | حمل داخلی اینورترهای خورشیدی و تحویل در سایت |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.4 | خرید MV Station |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.4.1 | استعلام قیمت و ثبت سفارش MV Station |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.4.2 | ساخت MV Station و بازرسی قبل حمل |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 5 | 7 | 8 | 10 | 11 | 12 | 14 | 15 | 16 | 18 | 19 | 21 | 22 | 23 | 25 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 29 | 30 | 32 | 33 | 34 | 36 | 37 | 38 | 40 | 41 | 42 | 44 | 45 | 47 | 48 | 49 | 51 | 52 | 53 | 55 | 56 | 58 | 59 | 60 | 62 | 63 | 64 | 66 | 67 | 68 | 70 | 71 | 73 | 74 | 75 | 77 | 78 | 79 | 81 | 82 | 84 | 85 | 86 | 88 | 89 | 90 | 92 | 93 | 95 | 96 | 97 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.4.3 | حمل خارجی MV Station |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 7 | 9 | 11 | 13 | 16 | 18 | 20 | 22 | 24 | 27 | 29 | 31 | 33 | 36 | 38 | 40 | 42 | 44 | 47 | 49 | 51 | 53 | 56 | 58 | 60 | 62 | 64 | 67 | 69 | 71 | 73 | 76 | 78 | 80 | 82 | 84 | 87 | 89 | 91 | 93 | 96 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.4.4 | ترخیص MV Station |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 21 | 29 | 36 | 43 | 50 | 57 | 64 | 71 | 79 | 86 | 93 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4.2.4.5 | حمل داخلی MV Station و تحویل در سایت |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5 | عملیات اجرایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0.03 | 0.05 | 0.07 | 0.08 | 0.1 | 0.59 | 1.07 | 1.55 | 1.79 | 2.02 | 2.25 | 2.95 | 3.65 | 3.65 | 3.65 | 3.65 | 3.67 | 3.69 | 3.71 | 3.73 | 3.74 | 3.77 | 3.8 | 3.83 | 3.85 | 3.88 | 3.91 | 3.94 | 3.97 | 4 | 4.03 | 4.06 | 4.09 | 4.12 | 4.15 | 4.18 | 4.47 | 4.74 | 5.03 | 5.31 | 5.59 | 5.87 | 5.89 | 5.9 | 5.92 | 5.93 | 5.98 | 6.04 | 6.12 | 6.19 | 6.59 | 7 | 7.24 | 7.69 | 8.14 | 8.6 | 9.03 | 9.31 | 9.75 | 10.2 | 10.66 | 10.94 | 11.38 | 11.83 | 12.27 | 12.72 | 13.01 | 13.53 | 14.03 | 14.56 | 15.04 | 15.4 | 15.9 | 16.42 | 16.92 | 17.27 | 17.77 | 18.27 | 19.1 | 19.79 | 20.45 | 21.3 | 21.96 | 22.82 | 23.47 | 24.15 | 24.98 | 25.66 | 26.49 | 27.19 | 27.85 | 28.69 | 29.5 | 30.22 | 30.93 | 31.79 | 32.5 | 33.38 | 34.05 | 34.76 | 35.64 | 36.34 | 37.15 | 37.68 | 38.22 | 38.92 | 39.29 | 39.49 | 39.89 | 40.13 | 40.57 | 41.02 | 41.3 | 41.74 | 42.19 | 42.42 | 42.8 | 43.17 | 43.5 | 44.15 | 44.63 | 45.27 | 45.93 | 46.42 | 49.28 | 51.88 | 54.49 | 57.21 | 59.69 | 62.48 | 65.19 | 67.65 | 69.7 | 72.05 | 74.17 | 76.68 | 79.18 | 81.22 | 83.7 | 85.92 | 88.24 | 91.09 | 93.22 | 94.86 | 95.95 | 96.38 | 96.81 | 98.35 | 98.94 | 99.53 | 99.69 | 99.84 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.1 | تجهیز کارگاه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.01 | 3.9 | 5.91 | 7.92 | 9.82 | 11.83 | 40.92 | 70.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.1.1 | عملیات اجرایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.01 | 3.9 | 5.91 | 7.92 | 9.82 | 11.83 | 40.92 | 70.9 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.1.1.1 | تانک سپتیک و دو مخزن 10 هزار لیتری سه لایه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 33 | 50 | 67 | 83 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.1.1.2 | کانکس نگهبانی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.1.1.3 | سایر تجهیز کارگاه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.2 | اجرای جاده دسترسی تا جاده اصلی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 16.5 | 25 | 33.5 | 41.5 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.2.1 | زیرسازی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 33 | 50 | 67 | 83 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.2.2 | شن ریزی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3 | عملیات عمرانی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.4 | 0.6 | 0.8 | 1 | 1.32 | 1.6 | 1.91 | 2.19 | 2.51 | 2.79 | 3.13 | 3.46 | 3.77 | 4.11 | 4.42 | 4.76 | 5.07 | 5.4 | 5.74 | 5.85 | 6.01 | 6.14 | 6.31 | 6.44 | 6.6 | 6.76 | 6.9 | 7.06 | 7.19 | 7.35 | 7.68 | 8.04 | 8.45 | 8.78 | 9.19 | 9.61 | 10.4 | 11.13 | 12.05 | 12.7 | 13.59 | 14.35 | 15.19 | 15.95 | 16.87 | 17.55 | 18.47 | 19.23 | 20.04 | 20.8 | 22.44 | 23.88 | 25.56 | 26.84 | 28.36 | 29.79 | 31.38 | 32.74 | 34.33 | 35.77 | 36.98 | 38.37 | 39.91 | 41.21 | 42.75 | 44.14 | 45.6 | 46.74 | 48.28 | 49.58 | 51.13 | 52.51 | 53.97 | 55.35 | 56.79 | 58.23 | 59.43 | 60.5 | 61.5 | 62.57 | 63.64 | 64.4 | 65.47 | 66.55 | 67.54 | 67.89 | 68.24 | 68.51 | 68.86 | 69.21 | 69.48 | 69.83 | 70.2 | 71.01 | 71.82 | 72.63 | 73.44 | 74.25 | 74.61 | 74.99 | 75.36 | 76.2 | 76.95 | 77.7 | 78.45 | 79.33 | 80.19 | 81.05 | 81.92 | 82.77 | 83.63 | 84.07 | 85.68 | 87.31 | 88.77 | 90.2 | 91.66 | 92.46 | 93.25 | 94.05 | 94.93 | 95.84 | 96.56 | 97.28 | 97.94 | 98.63 | 99.29 | 99.53 | 99.76 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.1 | عملیات دسترسی و آماده سازی سایت |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.75 | 5.5 | 8.25 | 11 | 13.75 | 16.5 | 19.25 | 22 | 24.75 | 27.5 | 30.25 | 33 | 35.75 | 38.5 | 41.25 | 44 | 46.75 | 49.5 | 52.25 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 56.75 | 58.25 | 60 | 61.75 | 63.25 | 65 | 66.75 | 68.25 | 70 | 71.75 | 73.25 | 75 | 76.75 | 78.25 | 80 | 82.8 | 85.8 | 88.6 | 91.4 | 94.2 | 97.2 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.1.1 | تسطیح و تحکیم زمین |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.1.2 | اجرای گیت ورودی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13 | 20 | 27 | 33 | 40 | 47 | 53 | 60 | 67 | 73 | 80 | 87 | 93 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.1.3 | احداث پارکینگ مسقف |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 29 | 43 | 57 | 71 | 86 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.2 | اجرای سیستم زهکشی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 8 | 10 | 13 | 15 | 18 | 20 | 23 | 25 | 28 | 30 | 33 | 35 | 38 | 40 | 43 | 45 | 48 | 50 | 53 | 55 | 58 | 60 | 63 | 65 | 68 | 70 | 73 | 75 | 78 | 80 | 83 | 85 | 88 | 90 | 93 | 95 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.2.1 | اجرای سیستم زهکشی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 8 | 10 | 13 | 15 | 18 | 20 | 23 | 25 | 28 | 30 | 33 | 35 | 38 | 40 | 43 | 45 | 48 | 50 | 53 | 55 | 58 | 60 | 63 | 65 | 68 | 70 | 73 | 75 | 78 | 80 | 83 | 85 | 88 | 90 | 93 | 95 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.3 | اجرای فنس پیرامونی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33 | 0.67 | 1.08 | 1.42 | 1.75 | 2.08 | 2.42 | 2.75 | 3.17 | 3.5 | 3.83 | 4.17 | 4.5 | 4.83 | 5.25 | 5.58 | 5.92 | 6.25 | 6.58 | 6.92 | 10.08 | 13.17 | 16.25 | 18.42 | 21.17 | 23.92 | 26.67 | 29.42 | 32.17 | 34.92 | 36.75 | 39.5 | 42.25 | 45 | 47.75 | 50.5 | 53.25 | 55.08 | 57.83 | 60.58 | 63.33 | 66.08 | 68.83 | 71.58 | 73.42 | 76.17 | 78.92 | 81.67 | 84.42 | 87.17 | 89.92 | 91.75 | 94.5 | 97.25 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.3.1 | اجرای فونداسیون و پایه فنس |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 13 | 17 | 21 | 25 | 29 | 33 | 38 | 42 | 46 | 50 | 54 | 58 | 63 | 67 | 71 | 75 | 79 | 83 | 88 | 92 | 96 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.3.2 | اجرای فنس |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 9 | 11 | 14 | 17 | 20 | 23 | 26 | 29 | 31 | 34 | 37 | 40 | 43 | 46 | 49 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 71 | 74 | 77 | 80 | 83 | 86 | 89 | 91 | 94 | 97 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.4 | اجرای فونداسیون MV Station |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.5 | 33.5 | 50 | 51.5 | 53.5 | 55 | 56.5 | 58.5 | 60 | 61.5 | 63.5 | 65 | 66.5 | 68.5 | 70 | 71.5 | 73.5 | 75 | 76.5 | 78.5 | 80 | 81.5 | 83.5 | 85 | 86.5 | 88.5 | 90 | 91.5 | 93.5 | 95 | 96.5 | 98.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.4.1 | گودبرداری فونداسیون |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.4.2 | بتن ریزی فونداسیون |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 10 | 13 | 17 | 20 | 23 | 27 | 30 | 33 | 37 | 40 | 43 | 47 | 50 | 53 | 57 | 60 | 63 | 67 | 70 | 73 | 77 | 80 | 83 | 87 | 90 | 93 | 97 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.5 | ساختمان پست سوییچگیر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56 | 0.97 | 1.53 | 1.95 | 2.5 | 2.92 | 3.48 | 4.03 | 4.45 | 5 | 5.42 | 5.98 | 6.39 | 6.95 | 7.51 | 7.92 | 8.48 | 8.9 | 9.45 | 9.87 | 10.43 | 10.98 | 11.4 | 11.95 | 12.37 | 12.93 | 13.34 | 13.9 | 14.73 | 15.15 | 15.99 | 16.82 | 17.24 | 18.07 | 18.91 | 19.32 | 20.16 | 20.99 | 21.41 | 22.24 | 23.08 | 23.5 | 24.33 | 25.17 | 25.58 | 26.42 | 27.25 | 27.67 | 28.5 | 29.34 | 29.76 | 30.59 | 31.42 | 31.84 | 32.68 | 33.51 | 33.93 | 34.76 | 35.6 | 36.01 | 36.85 | 37.68 | 38.1 | 38.93 | 39.77 | 40.19 | 41.02 | 41.85 | 42.27 | 43.11 | 43.94 | 44.36 | 45.19 | 46.03 | 46.44 | 47.28 | 48.11 | 48.53 | 49.36 | 50.2 | 50.62 | 51.45 | 52.29 | 52.7 | 53.54 | 54.37 | 54.79 | 55.62 | 56.55 | 57.48 | 58.41 | 59.34 | 60.26 | 61.19 | 62.12 | 63.05 | 63.98 | 64.9 | 65.37 | 65.83 | 66.3 | 66.76 | 67.22 | 67.69 | 68.15 | 68.62 | 69.08 | 69.54 | 72.95 | 76.36 | 79.77 | 83.18 | 86.59 | 88.91 | 91.23 | 93.55 | 95.86 | 98.18 | 98.55 | 98.91 | 99.27 | 99.64 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.5.1 | اجرای فونداسیون ساختمان پست سوییچگیر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 7 | 11 | 14 | 18 | 21 | 25 | 29 | 32 | 36 | 39 | 43 | 46 | 50 | 54 | 57 | 61 | 64 | 68 | 71 | 75 | 79 | 82 | 86 | 89 | 93 | 96 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.5.2 | سفت کاری ساختمان پست سوییچگیر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 5 | 7 | 8 | 10 | 12 | 13 | 15 | 17 | 18 | 20 | 22 | 23 | 25 | 27 | 28 | 30 | 32 | 33 | 35 | 37 | 38 | 40 | 42 | 43 | 45 | 47 | 48 | 50 | 52 | 53 | 55 | 57 | 58 | 60 | 62 | 63 | 65 | 67 | 68 | 70 | 72 | 73 | 75 | 77 | 78 | 80 | 82 | 83 | 85 | 87 | 88 | 90 | 92 | 93 | 95 | 97 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.5.3 | اجرای تاسیسات ساختمان پست سوییچگیر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.5.4 | نازک کاری ساختمان پست سوییچگیر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.5.5 | اجرای نمای ساختمان پست سوییچگیر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.5.6 | اجرای سیستم اعلام حریق ساختمان پست سوییچگیر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.5.7 | اجرای سیستم اطفا حریق ساختمان پست سوییچگیر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.6 | ساختمان مانیتورینگ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.81 | 1.13 | 1.54 | 1.94 | 2.35 | 2.67 | 3.08 | 3.48 | 3.88 | 4.21 | 4.61 | 5.02 | 5.42 | 5.75 | 6.15 | 6.55 | 6.96 | 7.28 | 7.69 | 8.09 | 8.74 | 9.39 | 10.03 | 10.68 | 11.33 | 11.97 | 12.62 | 13.27 | 13.91 | 14.56 | 15.21 | 15.85 | 16.5 | 17.15 | 17.79 | 18.44 | 19.09 | 19.73 | 20.38 | 21.03 | 21.67 | 22.32 | 22.97 | 23.62 | 24.26 | 24.91 | 25.56 | 26.2 | 26.85 | 27.5 | 28.14 | 28.79 | 29.44 | 30.08 | 30.73 | 31.38 | 32.02 | 32.67 | 33.32 | 33.96 | 34.61 | 35.26 | 37.55 | 39.85 | 42.15 | 44.44 | 46.74 | 47.39 | 48.03 | 48.68 | 51.11 | 53.53 | 55.96 | 58.38 | 60.81 | 63.24 | 65.66 | 68.09 | 70.52 | 72.94 | 73.75 | 76.19 | 78.63 | 81.07 | 83.51 | 85.95 | 86.76 | 87.57 | 88.38 | 89.19 | 90.08 | 91.51 | 92.95 | 94.38 | 95.9 | 97.33 | 98.22 | 99.11 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.6.1 | اجرای فونداسیون ساختمان مانیتورینگ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 14 | 19 | 24 | 29 | 33 | 38 | 43 | 48 | 52 | 57 | 62 | 67 | 71 | 76 | 81 | 86 | 90 | 95 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.6.2 | سفت کاری ساختمان مانیتورینگ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 56 | 58 | 60 | 62 | 64 | 66 | 68 | 70 | 72 | 74 | 76 | 78 | 80 | 82 | 84 | 86 | 88 | 90 | 92 | 94 | 96 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.6.3 | اجرای تاسیسات ساختمان مانیتورینگ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.6.4 | نازک کاری ساختمان مانیتورینگ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.6.5 | اجرای نمای ساختمان مانیتورینگ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 22 | 33 | 44 | 56 | 67 | 78 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.6.6 | اجرای سیستم اعلام حریق ساختمان مانیتورینگ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.6.7 | اجرای سیستم اطفا حریق ساختمان مانیتورینگ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.6.8 | کلیه تجهیزات و ملزومات |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.7 | ساختمان نگهبانی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 1.69 | 2.54 | 3.38 | 4.23 | 5.08 | 5.92 | 6.77 | 7.61 | 8.46 | 10.14 | 11.81 | 13.49 | 15.17 | 16.85 | 18.53 | 20.2 | 21.88 | 23.56 | 25.24 | 26.92 | 28.59 | 30.27 | 31.95 | 33.63 | 35.31 | 36.98 | 38.66 | 40.34 | 42.02 | 44.54 | 47.07 | 49.59 | 52.11 | 54.64 | 57.16 | 59.69 | 62.21 | 64.73 | 67.26 | 68.95 | 70.64 | 72.33 | 74.02 | 75.72 | 77.41 | 79.1 | 80.79 | 82.48 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 84.17 | 90.11 | 96.04 | 96.04 | 96.04 | 96.04 | 96.04 | 96.04 | 96.04 | 96.04 | 96.04 | 98.02 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.7.1 | اجرای فونداسیون ساختمان نگهبانی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.7.2 | سفت کاری ساختمان نگهبانی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.7.3 | اجرای تاسیسات ساختمان نگهبانی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.7.4 | نازک کاری ساختمان نگهبانی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.7.5 | اجرای نمای ساختمان نگهبانی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.7.6 | اجرای سیستم اعلام حریق ساختمان نگهبانی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.3.7.7 | اجرای سیستم اطفا حریق ساختمان نگهبانی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.4 | عملیات مکانیکال |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.74 | 1.44 | 2.18 | 2.92 | 3.62 | 4.36 | 4.36 | 4.36 | 4.36 | 4.36 | 4.45 | 4.54 | 4.67 | 4.76 | 5.76 | 6.76 | 7.3 | 8.31 | 9.35 | 10.35 | 11.35 | 11.9 | 12.9 | 13.9 | 14.94 | 15.49 | 16.49 | 17.49 | 18.49 | 19.49 | 20.08 | 21.08 | 22.08 | 23.08 | 24.08 | 24.67 | 25.67 | 26.67 | 27.67 | 28.22 | 29.22 | 30.26 | 32.18 | 33.63 | 35.09 | 37 | 38.46 | 40.42 | 41.87 | 43.33 | 45.24 | 46.7 | 48.61 | 50.11 | 51.57 | 53.48 | 55.31 | 56.67 | 58.04 | 59.87 | 61.24 | 63.06 | 64.43 | 65.8 | 67.62 | 68.99 | 70.81 | 72.18 | 73.55 | 75.37 | 76.29 | 76.74 | 77.65 | 78.11 | 79.02 | 79.93 | 80.39 | 81.3 | 82.21 | 82.67 | 83.58 | 84.49 | 84.95 | 85.86 | 86.32 | 87.23 | 88.14 | 88.6 | 89.51 | 90.42 | 90.88 | 91.79 | 92.7 | 93.16 | 94.07 | 94.98 | 95.44 | 96.35 | 96.81 | 97.72 | 98.63 | 99.09 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.4.1 | نقشه برداری پایه ها و میخ کوبی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 33 | 50 | 67 | 83 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.4.2 | پایه کوبی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 7 | 9 | 11 | 13 | 15 | 17 | 20 | 22 | 24 | 26 | 28 | 30 | 33 | 35 | 37 | 39 | 41 | 43 | 46 | 48 | 50 | 52 | 54 | 57 | 59 | 61 | 63 | 65 | 67 | 70 | 72 | 74 | 76 | 78 | 80 | 83 | 85 | 87 | 89 | 91 | 93 | 96 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.4.3 | نصب متعلقات استراکچرها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 7 | 9 | 11 | 13 | 14 | 16 | 18 | 20 | 21 | 23 | 25 | 27 | 29 | 30 | 32 | 34 | 36 | 38 | 39 | 41 | 43 | 45 | 46 | 48 | 50 | 52 | 54 | 55 | 57 | 59 | 61 | 63 | 64 | 66 | 68 | 70 | 71 | 73 | 75 | 77 | 79 | 80 | 82 | 84 | 86 | 88 | 89 | 91 | 93 | 95 | 96 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.4.4 | نصب پنل ها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 5 | 7 | 8 | 10 | 11 | 13 | 15 | 16 | 18 | 20 | 21 | 23 | 25 | 26 | 28 | 30 | 31 | 33 | 34 | 36 | 38 | 39 | 41 | 43 | 44 | 46 | 48 | 49 | 51 | 52 | 54 | 56 | 57 | 59 | 61 | 62 | 64 | 66 | 67 | 69 | 70 | 72 | 74 | 75 | 77 | 79 | 80 | 82 | 84 | 85 | 87 | 89 | 90 | 92 | 93 | 95 | 97 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5 | عملیات الکتریکال |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.4 | 0.61 | 0.81 | 1.01 | 1.21 | 1.41 | 1.61 | 1.82 | 2.02 | 2.02 | 2.02 | 2.02 | 2.02 | 2.02 | 2.09 | 2.15 | 2.22 | 2.29 | 2.36 | 2.42 | 2.49 | 2.55 | 2.55 | 2.55 | 2.73 | 3.2 | 3.69 | 4.16 | 4.65 | 5.12 | 10 | 14.36 | 19.06 | 23.67 | 27.86 | 32.8 | 37.23 | 41.2 | 44.69 | 48.44 | 52.19 | 56.37 | 60.55 | 64.11 | 68.23 | 72.53 | 77.02 | 82.59 | 86.71 | 89.88 | 92.01 | 92.82 | 93.63 | 96.72 | 97.89 | 99.07 | 99.38 | 99.69 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.1 | اجرای ترانشه و کانال عبور فیبر نوری |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.2 | نصب سازه اینورتر و وایرینگ اینورترهای سایت |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 25 | 38 | 50 | 63 | 75 | 88 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.3 | اجرای سیستم زمین نیروگاه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13 | 20 | 27 | 33 | 40 | 47 | 53 | 60 | 67 | 73 | 80 | 87 | 93 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.4 | تابلوهای فشار متوسط و کلیه متعلقات |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.5 | تابلوهای فشار ضعیف و کلیه متعلقات |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.6 | کلیه کابل های فشار ضعیف نیروگاهac |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 13 | 20 | 27 | 33 | 40 | 47 | 53 | 60 | 67 | 73 | 80 | 87 | 93 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.7 | کلیه کابل های فشار متوسط نیروگاهac |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 33 | 50 | 67 | 83 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.8 | کابل dc |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 26 | 29 | 32 | 35 | 38 | 41 | 44 | 47 | 50 | 53 | 56 | 59 | 62 | 65 | 68 | 71 | 74 | 76 | 79 | 82 | 85 | 88 | 91 | 94 | 97 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.9 | اجرای کابل های فیبر نوری |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.10 | نصب ایستگاه هواشناسی و سنسورها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.11 | MV Station نصب |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.12 | اجرای کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و بستر مخابراتی با پست بالادست به جز فیبر نوری |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.13 | نصب ترانسفورماتور کمکی و دیزل |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.14 | نصب یو پی اس |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.15 | سیستم حفاظت صاعقه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.16 | اجرای کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و ارسال دیتا |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.17 | کلیه متعلقات مربوط به کابل کشی و سیم کشی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 25 | 25 | 25 | 30 | 35 | 40 | 45 | 50 | 66.5 | 83.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.17.1 | نصب لدر |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.17.2 | اجرای لوله پلی اتیلن و فلکسی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.17.3 | اجرای سرسیم و کابل شو |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 67 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.17.4 | اجرای سر کابل |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.18 | نصب سیستم روشنایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.41 | 12.32 | 18.73 | 24.65 | 31.06 | 36.97 | 43.38 | 49.3 | 49.3 | 49.3 | 49.3 | 56.4 | 63.5 | 70.59 | 77.69 | 84.79 | 87.38 | 89.81 | 92.39 | 94.98 | 97.41 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.18.1 | اجرای فونداسیون سیستم روشنایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 25 | 38 | 50 | 63 | 75 | 88 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.18.2 | کابل کشی سیستم روشنایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.18.3 | نصب پایه ها و چراغ ها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 33 | 50 | 67 | 83 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.19 | CCTV نصب سیستم |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.04 | 10.08 | 15.12 | 20.16 | 25.2 | 32.6 | 40 | 47.4 | 54.8 | 62.2 | 71.65 | 81.1 | 90.55 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.19.1 | اجرای فونداسیون دوربین |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.19.2 | کابل کشی دوربین ها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5.5.19.3 | نصب پایه ها و دوربین ها |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6 | تست و تحویل |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.07 | 6.14 | 6.14 | 6.14 | 6.63 | 6.63 | 6.63 | 6.83 | 6.83 | 20.32 | 35.25 | 35.81 | 38.26 | 48.37 | 52.36 | 56.11 | 56.67 | 61.96 | 67.73 | 69.01 | 71.47 | 72.75 | 73.95 | 76.5 | 79.13 | 82.37 | 85.56 | 91.36 | 94.68 | 97.32 | 100
6.1 | تست و راه اندازی نیروگاه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.41 | 8.82 | 8.82 | 8.82 | 9.52 | 9.52 | 9.52 | 9.81 | 9.81 | 28.38 | 49.02 | 49.02 | 51.62 | 65.34 | 70.28 | 74.86 | 74.86 | 80.73 | 87.2 | 87.2 | 89.01 | 89.01 | 89.01 | 91.76 | 94.51 | 97.25 | 100 | 100 | 100 | 100 | 100
6.1.1 | تست کلیه کابل های فشار ضعیف نیروگاهac |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.2 | تست کلیه کابل های فشار متوسط نیروگاهac |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.3 | تست کابل dc |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100
6.1.4 | تست تابلوهای فشار متوسط و کلیه متعلقات |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.5 | تست کابل شبکه مورد نیازسیستم انتقال دیتا و اسکادا |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.6 | تست سیستم زمین نیروگاه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.7 | تست کلیه متعلقات مربوط به کابل کشی و سیم کشی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.8 | تست تابلوهای فشار ضعیف و کلیه متعلقات |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.9 | تست کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و بستر مخابراتی با پست بالادست |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.10 | تست کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و ارسال دیتا |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.11 | تست یو پی اس |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.12 | تست کلیه تجهیزات مربوط به دوربین |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.13 | تست سیستم روشنایی |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.14 | تست سیستم اعلام حریق |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.15 | تست سیستم اطفا حریق |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.16 | تست سیستم حفاظت صاعقه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.1.17 | تست ترانسفورماتور کمکی و دیزل |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.2 | ارایه نقشه های ازبیلت |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.33 | 4.67 | 7 | 9.67 | 12 | 14.33 | 16.67 | 19 | 24 | 29.33 | 34.67 | 39.67 | 45 | 50 | 52.67 | 55.67 | 58.33 | 61 | 72.33 | 83.33 | 91.67 | 100
6.2.1 | ارایه نقشه های ازبیلت الکتریکال |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 75 | 100
6.2.2 | ارایه نقشه های ازبیلت مکانیکال |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 21 | 29 | 36 | 43 | 50 | 57 | 64 | 71 | 79 | 86 | 93 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6.2.3 | ارایه نقشه های ازبیلت civil |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 17 | 25 | 33 | 42 | 50 | 58 | 67 | 75 | 83 | 92 | 100 | 100 | 100
6.3 | راه اندازی، اتصال به شبکه و پلمپ کنتور |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100
6.3.1 | راه اندازی، اتصال به شبکه و پلمپ کنتور |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100
6.4 | آموزش |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 33 | 50 | 67 | 83 | 100
6.4.1 | آموزش |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 33 | 50 | 67 | 83 | 100
6.5 | برچیدن کارگاه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.5.1 | برچیدن کارگاه |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100
7 | پایان |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100

## Actual (hidden)
|  |  | 1404/10/21 | 1404/10/22 | 1404/10/23 | 1404/10/24 | 1404/10/25 | 1404/10/26 | 1404/10/27 | 1404/10/28 | 1404/10/29 | 1404/10/30 | 1404/11/01 | 1404/11/02 | 1404/11/03 | 1404/11/04 | 1404/11/05 | 1404/11/06 | 1404/11/07 | 1404/11/08 | 1404/11/09 | 1404/11/10 | 1404/11/11 | 1404/11/12 | 1404/11/13 | 1404/11/14 | 1404/11/15 | 1404/11/16 | 1404/11/17 | 1404/11/18 | 1404/11/19 | 1404/11/20 | 1404/11/21 | 1404/11/22 | 1404/11/23 | 1404/11/24 | 1404/11/25 | 1404/11/26 | 1404/11/27 | 1404/11/28 | 1404/11/29 | 1404/11/30 | 1404/12/01 | 1404/12/02 | 1404/12/03 | 1404/12/04 | 1404/12/05 | 1404/12/06 | 1404/12/07 | 1404/12/08 | 1404/12/09 | 1404/12/10 | 1404/12/11 | 1404/12/12 | 1404/12/13 | 1404/12/14 | 1404/12/15 | 1404/12/16 | 1404/12/17 | 1404/12/18 | 1404/12/19 | 1404/12/20 | 1404/12/21 | 1404/12/22 | 1404/12/23 | 1404/12/24 | 1404/12/25 | 1404/12/26 | 1404/12/27 | 1404/12/28 | 1404/12/29 | 1405/01/01 | 1405/01/02 | 1405/01/03 | 1405/01/04 | 1405/01/05 | 1405/01/06 | 1405/01/07 | 1405/01/08 | 1405/01/09 | 1405/01/10 | 1405/01/11 | 1405/01/12 | 1405/01/13 | 1405/01/14 | 1405/01/15 | 1405/01/16 | 1405/01/17 | 1405/01/18 | 1405/01/19 | 1405/01/20 | 1405/01/21 | 1405/01/22 | 1405/01/23 | 1405/01/24 | 1405/01/25 | 1405/01/26 | 1405/01/27 | 1405/01/28 | 1405/01/29 | 1405/01/30 | 1405/01/31 | 1405/02/01 | 1405/02/02 | 1405/02/03 | 1405/02/04 | 1405/02/05 | 1405/02/06 | 1405/02/07 | 1405/02/08 | 1405/02/09 | 1405/02/10 | 1405/02/11 | 1405/02/12 | 1405/02/13 | 1405/02/14 | 1405/02/15 | 1405/02/16 | 1405/02/17 | 1405/02/18 | 1405/02/19 | 1405/02/20 | 1405/02/21 | 1405/02/22 | 1405/02/23 | 1405/02/24 | 1405/02/25 | 1405/02/26 | 1405/02/27 | 1405/02/28 | 1405/02/29 | 1405/02/30 | 1405/02/31 | 1405/03/01 | 1405/03/02 | 1405/03/03 | 1405/03/04 | 1405/03/05 | 1405/03/06 | 1405/03/07 | 1405/03/08 | 1405/03/09 | 1405/03/10 | 1405/03/11 | 1405/03/12 | 1405/03/13 | 1405/03/14 | 1405/03/15 | 1405/03/16 | 1405/03/17 | 1405/03/18 | 1405/03/19 | 1405/03/20 | 1405/03/21 | 1405/03/22 | 1405/03/23 | 1405/03/24 | 1405/03/25 | 1405/03/26 | 1405/03/27 | 1405/03/28 | 1405/03/29 | 1405/03/30 | 1405/03/31 | 1405/04/01 | 1405/04/02 | 1405/04/03 | 1405/04/04 | 1405/04/05 | 1405/04/06 | 1405/04/07 | 1405/04/08 | 1405/04/09 | 1405/04/10 | 1405/04/11 | 1405/04/12 | 1405/04/13 | 1405/04/14 | 1405/04/15 | 1405/04/16 | 1405/04/17 | 1405/04/18 | 1405/04/19 | 1405/04/20 | 1405/04/21 | 1405/04/22 | 1405/04/23 | 1405/04/24 | 1405/04/25 | 1405/04/26 | 1405/04/27 | 1405/04/28 | 1405/04/29 | 1405/04/30 | 1405/04/31 | 1405/05/01 | 1405/05/02 | 1405/05/03 | 1405/05/04 | 1405/05/05 | 1405/05/06 | 1405/05/07 | 1405/05/08 | 1405/05/09 | 1405/05/10 | 1405/05/11 | 1405/05/12 | 1405/05/13 | 1405/05/14 | 1405/05/15 | 1405/05/16 | 1405/05/17 | 1405/05/18 | 1405/05/19 | 1405/05/20 | 1405/05/21 | 1405/05/22 | 1405/05/23 | 1405/05/24 | 1405/05/25 | 1405/05/26 | 1405/05/27 | 1405/05/28 | 1405/05/29 | 1405/05/30 | 1405/05/31 | 1405/06/01 | 1405/06/02 | 1405/06/03 | 1405/06/04 | 1405/06/05 | 1405/06/06 | 1405/06/07 | 1405/06/08 | 1405/06/09 | 1405/06/10 | 1405/06/11 | 1405/06/12 | 1405/06/13 | 1405/06/14 | 1405/06/15 | 1405/06/16 | 1405/06/17 | 1405/06/18 | 1405/06/19 | 1405/06/20 | 1405/06/21
WBS | Task Name | Document No. | time axis 2026-01-11 to 2026-09-12
0 | پروژه احداث نیروگاه خورشیدی 20 مگا واتی زارچ یزد |  | 2026-01-11: 0; 2026-04-28: 8.66; 2026-05-05: 17.21; 2026-05-12: 17.41; 2026-05-19: 17.57; 2026-05-21: 17.57; 2026-05-26: 18.15; 2026-06-02: 18.83; 2026-06-09: 19.74; 2026-06-16: 20.24
1 | شروع |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
2 | مایلستون های کلیدی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
2.1 | دریافت سایر اطلاعات مقدماتی از کارفرما (آزمایش شیمیایی خاک، تست کشش پایه ها و…) |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
2.2 | واریز اولین پیش پرداخت بخش مهندسی |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
2.3 | دریافت مطالعات ژئوتکنیک |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
2.4 | تحویل زمین |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
2.5 | تاییدیه تجهیزات (پنل، اینورتر و MV Station( |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 100; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
2.6 | اتمام طراحی و اخذ تاییدیه |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
2.7 | اتمام استعلام قیمتی و سفارش گذاری خرید خارجی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 100; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
2.8 | اتمام تامین و تحویل خرید خارجی در سایت پروژه |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
2.9 | اتمام تجهیز کارگاه |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 100; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 100
2.1 | اتمام نصب سازه |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
2.11 | اتمام نصب پنل |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
2.12 | اتمام ساختمان مانیتورینگ |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
2.13 | اتمام نصب MV Staion |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
2.14 | اتمام نصب اینورتر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
2.15 | تست پست بالادست |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3 | مهندسی |  | 2026-01-11: 0; 2026-04-28: 16.06; 2026-05-05: 18.69; 2026-05-12: 22.51; 2026-05-19: 25.27; 2026-05-21: 25.27; 2026-05-26: 27.75; 2026-06-02: 29.18; 2026-06-09: 38.05; 2026-06-16: 58.37
3.1 | مدیریت پروژه |  | 2026-01-11: 0; 2026-04-28: 62.17; 2026-05-05: 62.17; 2026-05-12: 62.17; 2026-05-19: 62.17; 2026-05-21: 62.17; 2026-05-26: 67.97; 2026-06-02: 67.97; 2026-06-09: 67.97; 2026-06-16: 74.22
3.1.1 | Master Document List | 410-DE-PM-LST-0084 | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.1.2 | Time Schedule | 410-DE-PM-REP-0085 | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.1.3 | Cash Flow | 410-DE-PM-CAF-0086 | 2026-01-11: 0; 2026-04-28: 60; 2026-05-05: 60; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 100
3.1.4 | Monthly Report 410-M-001 | 410-DE-PM-REP-0138 | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.1.5 | Monthly Report 410-M-002 | 410-DE-PM-REP-0139 | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.1.6 | Monthly Report 410-M-003 | 410-DE-PM-REP-0140 | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.1.7 | Monthly Report 410-M-004 | 410-DE-PM-REP-0141 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 90; 2026-06-02: 90; 2026-06-09: 90; 2026-06-16: 100
3.1.8 | Monthly Report 410-M-005 | 410-DE-PM-REP-0142 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.1.9 | Monthly Report 410-M-006 | 410-DE-PM-REP-0143 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.1.10 | Monthly Report 410-M-007 | 410-DE-PM-REP-0144 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.1.11 | Monthly Report 410-M-008 | 410-DE-PM-REP-0145 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.2 | طراحی و اخذ تاییدیه طراحی پایه |  | 2026-01-11: 0; 2026-04-28: 30.11; 2026-05-05: 37.87; 2026-05-12: 42.03; 2026-05-19: 47.8; 2026-05-21: 47.8; 2026-05-26: 49.76; 2026-06-02: 53.71; 2026-06-09: 58.95; 2026-06-16: 76.85
3.2.1 | ارایه و اخذ تاییدیه دیتاشیت ها |  | 2026-01-11: 0; 2026-04-28: 11.18; 2026-05-05: 20.39; 2026-05-12: 21.05; 2026-05-19: 27.5; 2026-05-21: 27.5; 2026-05-26: 33.03; 2026-06-02: 40.92; 2026-06-09: 43.68; 2026-06-16: 69.78
3.2.1.1 | Solar Panel Datasheet | 410-BE-EL-DSH-0146 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.2.1.2 | Inverter Datasheet | 410-BE-EL-DSH-0147 | 2026-01-11: 0; 2026-04-28: 45; 2026-05-05: 45; 2026-05-12: 45; 2026-05-19: 45; 2026-05-21: 45; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 45
3.2.1.3 | MV Station Datasheet | 410-BE-EL-DSH-0148 | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 100
3.2.1.4 | DC Connection (MC4) Datasheet | 410-BE-EL-DSH-0149 | 2026-01-11: 0; 2026-04-28: 45; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.2.1.5 | DC Cable Datasheet | 410-BE-EL-DSH-0150 | 2026-01-11: 0; 2026-04-28: 45; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.2.1.6 | LV Cable Datasheet | 410-BE-EL-DSH-0151 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.2.1.7 | MV Cable Datasheet | 410-BE-EL-DSH-0152 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.2.1.8 | MV Switchgear (CT, PT, Relay) Datasheet | 410-BE-EL-DSH-0153 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.2.1.9 | Earthing and Lightning Datasheet | 410-BE-EL-DSH-0154 | 2026-01-11: 0; 2026-04-28: 45; 2026-05-05: 45; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 60
3.2.1.10 | Auxiliary Transformer Datasheet | 410-BE-EL-DSH-0155 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.2.1.11 | UPS and Battery Datasheet | 410-BE-EL-DSH-0156 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.2.1.12 | Diesel Generator Datasheet | 410-BE-EL-DSH-0157 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.2.1.13 | Monitoring System Datasheet | 410-BE-TL-DSH-0158 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 100
3.2.1.14 | Data Logger Datasheet | 410-BE-TL-DSH-0159 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.2.1.15 | Weather Station Datasheet | 410-BE-TL-DSH-0160 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.2.1.16 | CCTV and NVR Datasheet | 410-BE-TL-DSH-0161 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 45
3.2.1.17 | HVAC Datasheet | 410-BE-ME-DSH-0162 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 45
3.2.1.18 | Piping Material, Plumbing Fittings, Pumps Datasheet | 410-BE-ME-DSH-0163 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.2.1.19 | Septic Tank Datasheet | 410-BE-ME-DSH-0164 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 45; 2026-05-21: 45; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.2.1.20 | Water TankDatasheet | 410-BE-ME-DSH-0165 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.2.1.21 | Fire Alarm System Datasheet | 410-BE-SF-DSH-0166 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.2.2 | ارایه و اخذ تاییدیه مشخصات |  | 2026-01-11: 0; 2026-04-28: 9.57; 2026-05-05: 21.08; 2026-05-12: 31.14; 2026-05-19: 40.06; 2026-05-21: 40.06; 2026-05-26: 40.06; 2026-06-02: 43; 2026-06-09: 53.91; 2026-06-16: 71.8
3.2.2.1 | Solar Panel Technical Specification | 410-BE-EL-SPC-0001 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.2.2.2 | Inverter Technical Specification | 410-BE-EL-SPC-0002 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 60; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.2.2.3 | MV Station Technical Specification | 410-BE-EL-SPC-0003 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 60; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.2.2.4 | DC Connection (MC4) Technical Specification | 410-BE-EL-SPC-0004 | 2026-01-11: 0; 2026-04-28: 60; 2026-05-05: 60; 2026-05-12: 60; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.2.2.5 | DC Cable Technical Specification | 410-BE-EL-SPC-0005 | 2026-01-11: 0; 2026-04-28: 60; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.2.2.6 | LV Cable Technical Specification | 410-BE-EL-SPC-0006 | 2026-01-11: 0; 2026-04-28: 60; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 45
3.2.2.7 | MV Cable Technical Specification | 410-BE-EL-SPC-0007 | 2026-01-11: 0; 2026-04-28: 60; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 45
3.2.2.8 | MV Switchgear (CT, PT, Relay) Technical Specification | 410-BE-EL-SPC-0008 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 75
3.2.2.9 | Earthing and Lightning Technical Specification | 410-BE-EL-SPC-0009 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.2.2.10 | Auxiliary Transformer Technical Specification | 410-BE-EL-SPC-0013 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.2.2.11 | UPS and Battery Technical Specification | 410-BE-EL-SPC-0015 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.2.2.12 | Diesel Generator Technical Specification | 410-BE-EL-SPC-0016 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.2.2.13 | Monitoring System Technical Specification | 410-BE-TL-SPC-0010 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 100
3.2.2.14 | Data Logger Technical Specification | 410-BE-TL-SPC-0011 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 75
3.2.2.15 | Weather Station Technical Specification | 410-BE-TL-SPC-0012 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 45; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 100
3.2.2.16 | CCTV and NVR Technical Specification | 410-BE-TL-SPC-0014 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 45; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 60
3.2.2.17 | HVAC Technical Specification | 410-BE-ME-SPC-0017 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 60
3.2.2.18 | Piping Material, Plumbing Fittings, Pumps Technical Specification | 410-BE-ME-SPC-0018 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.2.2.19 | Septic Tank Technical Specification | 410-DE-ME-SPC-0096 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 45; 2026-05-21: 45; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.2.2.20 | Water Tank Technical Specification | 410-DE-ME-SPC-0097 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.2.2.21 | Fire Alarm System Technical Specification | 410-BE-SF-SPC-0019 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 45; 2026-05-19: 45; 2026-05-21: 45; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.2.3 | PVSYST Report | 410-BE-EL-REP-0023 | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 75
3.2.4 | General Layout | 410-BE-EL-DRW-0021 | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.2.5 | General Single Line Diagram (GSLD) | 410-BE-EL-DRW-0020 | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 100
3.2.6 | Plant Detailed Report | 410-BE-EL-REP-0024 | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.3 | طراحی و اخذ تاییدیه عمرانی مطابق MDL ارایه شده |  | 2026-01-11: 0; 2026-04-28: 26.96; 2026-05-05: 31.22; 2026-05-12: 36.26; 2026-05-19: 38.64; 2026-05-21: 38.64; 2026-05-26: 38.69; 2026-06-02: 38.69; 2026-06-09: 38.83; 2026-06-16: 55.72
3.3.1 | Topography of Field | 410-DE-CV-REP-0087 | 2026-01-11: 0; 2026-04-28: 45; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.3.2 | Geotechnical Test Report | 410-DE-CV-REP-0088 | 2026-01-11: 0; 2026-04-28: 45; 2026-05-05: 45; 2026-05-12: 90; 2026-05-19: 90; 2026-05-21: 90; 2026-05-26: 90; 2026-06-02: 90; 2026-06-09: 90; 2026-06-16: 90
3.3.3 | Ramming and Pull-Out Test Report | 410-DE-CV-REP-0089 | 2026-01-11: 0; 2026-04-28: 45; 2026-05-05: 45; 2026-05-12: 90; 2026-05-19: 90; 2026-05-21: 90; 2026-05-26: 90; 2026-06-02: 90; 2026-06-09: 0; 2026-06-16: 0
3.3.4 | Hydrology Study Report | 410-DE-CV-REP-0090 | 2026-01-11: 0; 2026-04-28: 45; 2026-05-05: 60; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 90; 2026-06-16: 100
3.3.5 | Site Fence Detail Drawing | 410-DE-CV-DRW-0091 | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.3.6 | Logistic Area | 410-DE-CV-DRW-0092 | 2026-01-11: 0; 2026-04-28: 60; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 75
3.3.7 | Buildings Foundation & Structure Calculation | 410-DE-CV-CAL-0093 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.3.8 | Buildings Foundation & Structure Drawing | 410-DE-CV-DRW-0094 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 40; 2026-05-19: 47; 2026-05-21: 47; 2026-05-26: 49; 2026-06-02: 49; 2026-06-09: 60; 2026-06-16: 0
3.3.9 | Parking Foundation & Structure Detail Drawing | 410-DE-CV-DRW-0098 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.3.10 | Power Plant Entrance Gate Drawing | 410-DE-CV-DRW-0099 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.3.11 | Parking Architectural Drawing | 410-DE-CV-DRW-0100 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.3.12 | Landscaping Layout | 410-DE-CV-DRW-0101 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 60
3.3.13 | Buildings Architectural Detail drawing | 410-DE-CV-DRW-0102 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 60; 2026-05-12: 30; 2026-05-19: 49; 2026-05-21: 49; 2026-05-26: 49; 2026-06-02: 49; 2026-06-09: 60; 2026-06-16: 70
3.3.14 | Fence MTO | 410-DE-CV-MTO-0103 | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 100; 2026-06-16: 100
3.3.15 | Site Grading and Leveling | 410-DE-CV-DRW-0104 | 2026-01-11: 0; 2026-04-28: 60; 2026-05-05: 60; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 100
3.3.16 | Drainage For Insite of Plant & Implementation Detail Drawing | 410-DE-CV-DRW-0105 | 2026-01-11: 0; 2026-04-28: 45; 2026-05-05: 45; 2026-05-12: 45; 2026-05-19: 45; 2026-05-21: 45; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.3.17 | Flood Managmant For Outsite of Plant & Implementation Detail Drawing | 410-DE-CV-DRW-0106 | 2026-01-11: 0; 2026-04-28: 45; 2026-05-05: 45; 2026-05-12: 45; 2026-05-19: 45; 2026-05-21: 45; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.3.18 | Internal Road Layout & Implementation Detail Drawing | 410-DE-CV-DRW-0107 | 2026-01-11: 0; 2026-04-28: 60; 2026-05-05: 60; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 100
3.3.19 | Access Road Layout & Implementation Detail Drawing | 410-DE-CV-DRW-0108 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.3.20 | MV Station Foundation Calculation | 410-DE-CV-CAL-0109 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 45; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 75
3.3.21 | MV Station Foundation Drawings | 410-DE-CV-DRW-0110 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 45; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 60; 2026-06-16: 75
3.3.22 | Auxiliary Transformer Foundation Detail Drawings | 410-DE-CV-DRW-0111 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.3.23 | Calculation Report for Structure | 410-DE-CV-CAL-0112 | 2026-01-11: 0; 2026-04-28: 60; 2026-05-05: 60; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 75
3.3.24 | Structure Detail Drawings | 410-DE-CV-DRW-0113 | 2026-01-11: 0; 2026-04-28: 60; 2026-05-05: 60; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 75
3.3.25 | PV Structure Ramming Location Details Drawing (Stacking) | 410-DE-CV-DRW-0114 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.3.26 | Solar Module Structure MTO | 410-DE-CV-MTO-0115 | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 75
3.3.27 | Table UTM Point | 410-DE-CV-DRW-0116 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.3.28 | Structure, Entrance Gate and Foundation of Building MTO | 410-DE-CV-MTO-0117 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.3.29 | System Drainage Calculation | 410-DE-CV-CAL-0130 | 2026-01-11: 0; 2026-04-28: 45; 2026-05-05: 45; 2026-05-12: 45; 2026-05-19: 45; 2026-05-21: 45; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.3.30 | Lighting Foundation Calculation | 410-DE-CV-CAL-0131 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.3.31 | Lightning Foundation Calculation | 410-DE-CV-CAL-0132 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.3.32 | Lightning Foundation Drawing | 410-DE-CV-DRW-0133 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.3.33 | Lighting and CCTV Pole Calculation | 410-DE-CV-CAL-0134 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.3.34 | Septic Tank Detail Drawing | 410-DE-CV-DRW-0135 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 75
3.3.35 | Water Tank Foundation Detail Drawing | 410-DE-CV-DRW-0136 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 75
3.3.36 | Calculation for Fence | 410-DE-CV-CAL-0137 | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 100
3.3.37 | Material Requisition for Fence | 410-DE-CV-MRE-0167 | 2026-01-11: 0; 2026-04-28: 60; 2026-05-05: 60; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 56; 2026-06-16: 100
3.4 | طراحی و اخذ تاییدیه الکتریکال مطابق MDL ارایه شده |  | 2026-01-11: 0; 2026-04-28: 9.16; 2026-05-05: 13.01; 2026-05-12: 18.37; 2026-05-19: 20.33; 2026-05-21: 20.33; 2026-05-26: 22.02; 2026-06-02: 22.77; 2026-06-09: 41.19; 2026-06-16: 67.19
3.4.1 | Solar Module, Connector, Inverter and MV station MTO | 410-BE-EL-MTO-0025 | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 100
3.4.2 | PV System Calculation Study (String Size, Optimum Tilt and Pitch) | 410-DE-EL-CAL-0022 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 60; 2026-06-16: 75
3.4.3 | Strings Connection Diagram & Inverter Arrangement (DC Side) | 410-DE-EL-DRW-0026 | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 100
3.4.4 | Module & Table Arrangement (DC Side) | 410-DE-EL-DRW-0027 | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 100
3.4.5 | DC Cable Calculation | 410-DE-EL-CAL-0028 | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 75
3.4.6 | DC Cable List, Labeling Code and MTO | 410-DE-EL-MTO-0029 | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 60; 2026-06-16: 75
3.4.7 | LVAC Cable Calculation | 410-DE-EL-CAL-0030 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 45; 2026-05-12: 60; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.4.8 | LV Cable Termination List and MTO | 410-DE-EL-LST-0031 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.9 | LV Cable List, Labeling Code and MTO | 410-DE-EL-MTO-0032 | 2026-01-11: 0; 2026-04-28: 90; 2026-05-05: 90; 2026-05-12: 90; 2026-05-19: 90; 2026-05-21: 90; 2026-05-26: 90; 2026-06-02: 90; 2026-06-09: 90; 2026-06-16: 100
3.4.10 | MV Cable Calculations | 410-DE-EL-CAL-0033 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 45; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.4.11 | MV Cable List, Labeling Code and MTO | 410-DE-EL-MTO-0034 | 2026-01-11: 0; 2026-04-28: 90; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
3.4.12 | MV Cable Termination List and MTO | 410-DE-EL-LST-0035 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.13 | Electrical Cable Route and Section | 410-DE-EL-DRW-0036 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 75
3.4.14 | Cable Trench Layout | 410-DE-EL-DRW-0037 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.15 | Earthing System Calculation | 410-DE-EL-CAL-0038 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 45; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 60
3.4.16 | Earthing System Layout | 410-DE-EL-DRW-0039 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 45; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 60
3.4.17 | Lightning Protection Calculation | 410-DE-EL-CAL-0040 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 45; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 100; 2026-06-16: 100
3.4.18 | Lightning Protection Layout | 410-DE-EL-DRW-0041 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 45; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 75
3.4.19 | Earthing and Lightning Protection MTO | 410-DE-EL-MTO-0042 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 90
3.4.20 | Protection Single Line Diagram (PSLD) | 410-DE-EL-DRW-0043 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 45; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 60
3.4.21 | CT and PT Calculations | 410-DE-EL-CAL-0044 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.22 | MV Switchgear Logic Diagram | 410-DE-EL-DRW-0045 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 60; 2026-06-16: 60
3.4.23 | Trip Table | 410-DE-EL-REP-0046 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 45; 2026-06-09: 75; 2026-06-16: 75
3.4.24 | Alarm List | 410-DE-EL-LST-0047 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.25 | Indoor and Outdoor Electrical Plan & Details for Building | 410-DE-EL-DRW-0048 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.26 | MV Switchgear MTO | 410-DE-EL-MTO-0049 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.27 | Load List | 410-DE-EL-LST-0050 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.28 | LVAC Auxiliary Panel Single Line Diagram | 410-DE-EL-DRW-0051 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.29 | UPS Calculation | 410-DE-EL-CAL-0052 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.4.30 | AUX Equipment MTO (AUX Transformer, Diesel, UPS, Battery) | 410-DE-EL-MTO-0053 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.31 | Indoor and Outdoor Lighting Calculation | 410-DE-EL-CAL-0058 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.32 | Outdoor Lighting Pole Drawing | 410-DE-EL-DRW-0059 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.4.33 | Outdoor Lighting Layout and Switchboard | 410-DE-EL-DRW-0060 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.34 | Lighting System MTO | 410-DE-EL-MTO-0061 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.35 | Special Tools | 410-DE-EL-REP-0082 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 45; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 100
3.4.36 | MV Switchgear Schematic Diagram | 410-DE-EL-DRW-0128 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.37 | MV Switchgear Front View Drawing | 410-DE-EL-DRW-0129 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.38 | Material Requisition for Indoor Power and Lighting Distribution Panel | 410-DE-EL-MRE-0168 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.4.39 | Material Requisition for Auxiliary Transformer | 410-DE-EL-MRE-0169 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.4.40 | Material Requisition for PCC | 410-DE-EL-MRE-0170 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.4.41 | Material Requisition for MV Switchgear (CT, PT, Relay) | 410-DE-EL-MRE-0171 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.4.42 | Material Requisition for AC Cable | 410-DE-EL-MRE-0172 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.4.43 | Material Requisition for DC Cable | 410-DE-EL-MRE-0173 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.4.44 | Material Requisition for Earthing and Lightning | 410-DE-EL-MRE-0174 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.4.45 | Material Requisition for DC Connection (MC4) | 410-DE-EL-MRE-0175 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.4.46 | Material Requisition for Lighting System | 410-DE-EL-MRE-0176 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.4.47 | Material Requisition for UPS and Battery | 410-DE-EL-MRE-0177 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.4.48 | Material Requisition for Diesel Generator | 410-BE-EL-MRE-0186 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.5 | طراحی و اخذ تاییدیه مکانیکال مطابق MDL ارایه شده |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 5.18; 2026-05-12: 5.18; 2026-05-19: 5.18; 2026-05-21: 5.18; 2026-05-26: 5.18; 2026-06-02: 5.18; 2026-06-09: 31.07; 2026-06-16: 62.42
3.5.1 | Solar Panel Cleaning & Maintenance Procedures | 410-DE-ME-REP-0062 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 60; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 60
3.5.2 | HVAC Equipment Calculation | 410-DE-ME-CAL-0066 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 45
3.5.3 | HVAC Equipment Layout for Building | 410-DE-ME-DRW-0067 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 45
3.5.4 | HVAC and Piping System MTO | 410-DE-ME-MTO-0068 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 45
3.5.5 | Mechanical Drawing (Water Supply and Sewage Systems) | 410-DE-ME-DRW-0095 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 45
3.5.6 | Material Requisition for Septic Tank | 410-BE-ME-MRE-0183 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.5.7 | Material Requisition for Water | 410-BE-ME-MRE-0184 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 60
3.6 | طراحی و اخذ تاییدیه ایمنی مطابق MDL ارایه شده |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 6.28; 2026-05-21: 6.28; 2026-05-26: 6.28; 2026-06-02: 12.56; 2026-06-09: 32.44; 2026-06-16: 66.63
3.6.1 | Fire Fighting Equipment Arrangement of MV Switchgear Buildings | 410-DE-SF-DRW-0069 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.6.2 | Outdoor Fire Fighting Equipment & Shelter Arrangement | 410-DE-SF-DRW-0070 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 45; 2026-05-21: 45; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.6.3 | Fire Alarm System Layout and Block Diagram | 410-DE-SF-DRW-0071 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 45
3.6.4 | Fire and Safety and F & G System MTO | 410-DE-SF-MTO-0072 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 90
3.6.5 | Material Requisition for Fire Alarm System | 410-DE-SF-MRE-0181 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 45
3.6.6 | Material Requisition for Fire Fighting Equipment Arrangement | 410-DE-SF-MRE-0182 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 45
3.7 | طراحی و اخذ تاییدیه ارتباطی مطابق MDL ارایه شده |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 5.39; 2026-05-19: 7.18; 2026-05-21: 7.18; 2026-05-26: 17.03; 2026-06-02: 27.41; 2026-06-09: 33.93; 2026-06-16: 73.55
3.7.1 | CCTV System Block Diagram | 410-DE-TL-DRW-0054 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 60; 2026-06-16: 60
3.7.2 | CCTV System Arrangement & Layout | 410-DE-TL-DRW-0055 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 45
3.7.3 | CCTV Pole Detail Drawing, Switchboard, CAFU Details | 410-DE-TL-DRW-0056 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.7.4 | CCTV System MTO | 410-DE-TL-MTO-0057 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 90
3.7.5 | SCADA System I/O List | 410-DE-TL-LST-0063 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.7.6 | Monitoring System Overall Diagram | 410-DE-TL-DRW-0064 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.7.7 | Telecommunication and Monitoring System MTO | 410-DE-TL-MTO-0065 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 90; 2026-06-09: 90; 2026-06-16: 100
3.7.8 | Material Requisition forTelecommunication and Monitoring Cable | 410-DE-TL-MRE-0178 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 45
3.7.9 | Material Requisition forFiber Optics | 410-BE-TL-MRE-0179 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.7.10 | Material Requisition for CCTV and NVR | 410-DE-TL-MRE-0180 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 100
3.7.11 | Material Requisition for Weather Station | 410-BE-TL-MRE-0185 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 45; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 100
3.8 | مستندات حوزه کیفیت مطابق MDL ارایه شده |  | 2026-01-11: 0; 2026-04-28: 9; 2026-05-05: 4.5; 2026-05-12: 4.5; 2026-05-19: 9; 2026-05-21: 9; 2026-05-26: 15.75; 2026-06-02: 15.75; 2026-06-09: 18; 2026-06-16: 21.75
3.8.1 | Solar Panel Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0073 | 2026-01-11: 0; 2026-04-28: 90; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 90; 2026-06-02: 90; 2026-06-09: 90; 2026-06-16: 100
3.8.2 | Inverter Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0074 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 45; 2026-06-02: 45; 2026-06-09: 45; 2026-06-16: 100
3.8.3 | MV Station Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0075 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 90; 2026-05-21: 90; 2026-05-26: 90; 2026-06-02: 90; 2026-06-09: 90; 2026-06-16: 100
3.8.4 | UPS Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0076 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.5 | AUX Transformer Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0077 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.6 | Diesel Generator Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0078 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.7 | Weather Station Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0079 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 45; 2026-06-16: 45
3.8.8 | Solar Structure Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0080 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.9 | SCADA and Monitoring System Installation Manual & Operation & Maintenance | 410-DE-QA-REP-0081 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.10 | Project O&M General Instructions | 410-DE-QA-REP-0083 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.11 | Test Report of Solar Structure | 410-DE-QA-REP-0118 | 2026-01-11: 0; 2026-04-28: 90; 2026-05-05: 90; 2026-05-12: 90; 2026-05-19: 90; 2026-05-21: 90; 2026-05-26: 90; 2026-06-02: 90; 2026-06-09: 90; 2026-06-16: 90
3.8.12 | Test Reports for PV Modules | 410-DE-QA-REP-0119 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.13 | Test Reports for Inverter | 410-DE-QA-REP-0120 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.14 | Test Reports for MV Sation | 410-DE-QA-REP-0121 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.15 | Test Reports for AC and DC Cables | 410-DE-QA-REP-0122 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.16 | Test Reports for Diesel Generators | 410-DE-QA-REP-0123 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.17 | Test Reports for AUX Transformer | 410-DE-QA-REP-0124 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.18 | Test Reports for Earthing and Ligthtning | 410-DE-QA-REP-0125 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.19 | Test Reports for MV Switchgear (CT, PT, Relay, …) | 410-DE-QA-REP-0126 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.20 | Test Reports for UPS and Battery | 410-DE-QA-REP-0127 | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
3.8.21 | کدگذاری و تحویل مستندات پروژه |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4 | تامین و حمل کالا تجهیزات |  | 2026-01-11: 0; 2026-04-28: 10.53; 2026-05-05: 22.63; 2026-05-12: 22.8; 2026-05-19: 22.95; 2026-05-21: 22.95; 2026-05-26: 23.69; 2026-06-02: 24.62; 2026-06-09: 25.65; 2026-06-16: 25.79
4.1 | خرید و حمل داخلی |  | 2026-01-11: 0; 2026-04-28: 12.58; 2026-05-05: 32.89; 2026-05-12: 33.17; 2026-05-19: 33.43; 2026-05-21: 33.43; 2026-05-26: 34.67; 2026-06-02: 35.2; 2026-06-09: 36.94; 2026-06-16: 37.17
4.1.1 | خرید مصالح و تجهیز کارگاه |  | 2026-01-11: 0; 2026-04-28: 95.88; 2026-05-05: 96.03; 2026-05-12: 98.23; 2026-05-19: 98.23; 2026-05-21: 98.23; 2026-05-26: 98.23; 2026-06-02: 98.23; 2026-06-09: 98.23; 2026-06-16: 100
4.1.1.1 | مصالح ساختمانی و ملزومات عمرانی |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 0; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.1.1.2 | مصالح ،تجهیزات و ملزومات برقی ساختمان ها |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 0; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.1.1.3 | تانک سپتیک و دو مخزن 10 هزار لیتری سه لایه |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 85; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.1.1.4 | کلیه تجهیزات و ملزومات اداری |  | 2026-01-11: 0; 2026-04-28: 85; 2026-05-05: 90; 2026-05-12: 90; 2026-05-19: 90; 2026-05-21: 100; 2026-05-26: 90; 2026-06-02: 90; 2026-06-09: 90; 2026-06-16: 100
4.1.1.5 | سایر خرید تجهیز کارگاه |  | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 75; 2026-05-12: 90; 2026-05-19: 90; 2026-05-21: 100; 2026-05-26: 90; 2026-06-02: 90; 2026-06-09: 90; 2026-06-16: 100
4.1.2 | فنس پیرامونی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 5; 2026-05-12: 5; 2026-05-19: 21; 2026-05-21: 21; 2026-05-26: 49; 2026-06-02: 61; 2026-06-09: 100; 2026-06-16: 100
4.1.2.1 | سفارش گذاری فنس پیرامونی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.1.2.2 | ساخت و بازرسی فنس پیرامونی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 20; 2026-05-21: 20; 2026-05-26: 55; 2026-06-02: 70; 2026-06-09: 100; 2026-06-16: 100
4.1.2.3 | حمل فنس پیرامونی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 100; 2026-06-16: 100
4.1.3 | تابلو های توزیع داخلی و روشنایی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.3.1 | سفارش گذاری تابلو های توزیع داخلی و روشنایی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.3.2 | ساخت و بازرسی تابلو های توزیع داخلی و روشنایی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.3.3 | حمل تابلو های توزیع داخلی و روشنایی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.4 | ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.4.1 | سفارش گذاری ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.4.2 | ساخت و بازرسی ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.4.3 | حمل ترانسفورماتور های مصرف داخلی و دیزل ژنراتور |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.5 | تابلوهای پست سوییچگیر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.5.1 | سفارش گذاری تابلوهای پست سوییچگیر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.5.2 | ساخت و بازرسی تابلوهای پست سوییچگیر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.5.3 | حمل تابلوهای پست سوییچگیر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.6 | ct& pt |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.6.1 | سفارش گذاری ct& pt |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.6.2 | ساخت و بازرسی ct& pt |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.6.3 | حمل ct& pt |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.7 | AC/LV و AC/MV کابل های |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 5; 2026-05-12: 5; 2026-05-19: 2.5; 2026-05-21: 2.5; 2026-05-26: 2.5; 2026-06-02: 2.5; 2026-06-09: 2.5; 2026-06-16: 2.5
4.1.7.1 | AC/LV و AC/MV سفارش گذاری کابل های |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 50; 2026-05-21: 50; 2026-05-26: 50; 2026-06-02: 50; 2026-06-09: 50; 2026-06-16: 50
4.1.7.2 | AC/LV و AC/MV ساخت و بازرسی کابل های |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.7.3 | AC/LV و AC/MV حمل کابل های |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.8 | DC کابل های |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 96.25; 2026-05-12: 96.25; 2026-05-19: 96.25; 2026-05-21: 96.25; 2026-05-26: 96.25; 2026-06-02: 96.25; 2026-06-09: 96.25; 2026-06-16: 96.25
4.1.8.1 | DC سفارش گذاری کابل های |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.1.8.2 | DC ساخت و بازرسی کابل های |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.1.8.3 | DC حمل کابل های |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 75; 2026-05-12: 75; 2026-05-19: 75; 2026-05-21: 75; 2026-05-26: 75; 2026-06-02: 75; 2026-06-09: 75; 2026-06-16: 75
4.1.9 | کابل های ارتباطی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.9.1 | سفارش گذاری کابل های ارتباطی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.9.2 | ساخت و بازرسی کابل های ارتباطی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.9.3 | حمل کابل های ارتباطی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.10 | Fiber Optics (انتقال دیتا داخلی نیروگاه) |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.10.1 | Fiber Optics سفارش گذاری (انتقال دیتا داخلی نیروگاه) |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.10.2 | Fiber Optics ساخت و بازرسی (انتقال دیتا داخلی نیروگاه) |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.10.3 | Fiber Optics حمل (انتقال دیتا داخلی نیروگاه) |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.11 | کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.11.1 | سفارش گذاری کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.11.2 | ساخت و بازرسی کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.11.3 | حمل کابل سیستم زمین و تجهیزات جانبی (ارت) |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.12 | MC4 |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.1.12.1 | MC4 سفارش گذاری |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.1.12.2 | MC4 ساخت و بازرسی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.1.12.3 | MC4 حمل |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.1.13 | و تجهیزات جانبیCCTV سیستم |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.13.1 | و تجهیزات جانبیCCTV سفارش گذاری سیستم |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.13.2 | و تجهیزات جانبیCCTV ساخت و بازرسی سیستم |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.13.3 | و تجهیزات جانبیCCTV حمل سیستم |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.14 | تجهیزات سیستم روشنایی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.14.1 | سفارش گذاری تجهیزات سیستم روشنایی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.14.2 | ساخت و بازرسی تجهیزات سیستم روشنایی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.14.3 | حمل تجهیزات سیستم روشنایی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.15 | UPS سیستم |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.15.1 | UPS سفارش گذاری سیستم |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.15.2 | UPS خرید سیستم |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.15.3 | UPS حمل سیستم |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.16 | سیستم اعلان حریق و تجهیزات جانبی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.16.1 | سفارش گذاری سیستم اعلان حریق و تجهیزات جانبی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.16.2 | ساخت و بازرسی سیستم اعلان حریق و تجهیزات جانبی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.16.3 | حمل سیستم اعلان حریق و تجهیزات جانبی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.17 | سیستم اطفا حریق و تجهیزات جانبی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.17.1 | سفارش گذاری سیستم اطفا حریق و تجهیزات جانبی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.17.2 | ساخت و بازرسی سیستم اطفا حریق و تجهیزات جانبی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.17.3 | حمل سیستم اطفا حریق و تجهیزات جانبی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.18 | ایستگاه هواشناسی و سنسورها |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.18.1 | سفارش گذاری ایستگاه هواشناسی و سنسورها |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.18.2 | ساخت و بازرسی ایستگاه هواشناسی و سنسورها |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.18.3 | حمل ایستگاه هواشناسی و سنسورها |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.1.19 | لوازم یدکی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 1; 2026-06-16: 1
4.1.19.1 | لوازم یدکی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 1; 2026-06-16: 1
4.2 | خرید خارجی، حمل بین المللی و ترخیص |  | 2026-01-11: 0; 2026-04-28: 7.5; 2026-05-05: 7.5; 2026-05-12: 7.5; 2026-05-19: 7.5; 2026-05-21: 7.5; 2026-05-26: 7.5; 2026-06-02: 9; 2026-06-09: 9; 2026-06-16: 9
4.2.1 | خرید سازه های نگهدارنده پنل ها و اینورترها |  | 2026-01-11: 0; 2026-04-28: 7.5; 2026-05-05: 7.5; 2026-05-12: 7.5; 2026-05-19: 7.5; 2026-05-21: 7.5; 2026-05-26: 7.5; 2026-06-02: 9; 2026-06-09: 9; 2026-06-16: 9
4.2.1.1 | استعلام قیمت و سفارش گذاری سازه های نگهدارنده |  | 2026-01-11: 0; 2026-04-28: 50; 2026-05-05: 50; 2026-05-12: 50; 2026-05-19: 50; 2026-05-21: 50; 2026-05-26: 50; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 60
4.2.1.2 | ساخت سازه های نگهدارنده و بازرسی قبل حمل |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.1.3 | حمل خارجی سازه های نگهدارنده |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.1.4 | ترخیص سازه های نگهدارنده |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.1.5 | حمل داخلی سازه های نگهدارنده و تحویل در سایت |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.2 | خرید پنل های خورشیدی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.2.1 | استعلام قیمت و ثبت سفارش پنل های خورشیدی |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.2.2.2 | ساخت پنل های خورشیدی و بازرسی قبل حمل |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.2.2.3 | حمل خارجی پنل های خورشیدی |  | 2026-01-11: 0; 2026-04-28: 50; 2026-05-05: 50; 2026-05-12: 60; 2026-05-19: 60; 2026-05-21: 60; 2026-05-26: 60; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 70
4.2.2.4 | ترخیص پنل های خورشیدی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.2.5 | حمل داخلی پنل های خورشیدی و تحویل در سایت |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.3 | خرید اینورترهای خورشیدی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.3.1 | استعلام قیمت و ثبت سفارش اینورترهای خورشیدی |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.2.3.2 | ساخت اینورترهای خورشیدی و بازرسی قبل حمل |  | 2026-01-11: 0; 2026-04-28: 50; 2026-05-05: 50; 2026-05-12: 80; 2026-05-19: 95; 2026-05-21: 95; 2026-05-26: 95; 2026-06-02: 95; 2026-06-09: 95; 2026-06-16: 95
4.2.3.3 | حمل خارجی اینورترهای خورشیدی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.3.4 | ترخیص اینورترهای خورشیدی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.3.5 | حمل داخلی اینورترهای خورشیدی و تحویل در سایت |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.4 | خرید MV Station |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.4.1 | استعلام قیمت و ثبت سفارش MV Station |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
4.2.4.2 | ساخت MV Station و بازرسی قبل حمل |  | 2026-01-11: 0; 2026-04-28: 30; 2026-05-05: 30; 2026-05-12: 30; 2026-05-19: 30; 2026-05-21: 30; 2026-05-26: 30; 2026-06-02: 30; 2026-06-09: 35; 2026-06-16: 50
4.2.4.3 | حمل خارجی MV Station |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.4.4 | ترخیص MV Station |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
4.2.4.5 | حمل داخلی MV Station و تحویل در سایت |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5 | عملیات اجرایی |  | 2026-01-11: 0; 2026-04-28: 3.73; 2026-05-05: 3.8; 2026-05-12: 3.81; 2026-05-19: 3.83; 2026-05-21: 3.83; 2026-05-26: 3.85; 2026-06-02: 3.89; 2026-06-09: 3.9; 2026-06-16: 3.91
5.1 | تجهیز کارگاه |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 99.39; 2026-05-19: 99.54; 2026-05-21: 99.54; 2026-05-26: 99.54; 2026-06-02: 99.54; 2026-06-09: 99.54; 2026-06-16: 99.54
5.1.1 | عملیات اجرایی |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 99.39; 2026-05-19: 99.54; 2026-05-21: 99.54; 2026-05-26: 99.54; 2026-06-02: 99.54; 2026-06-09: 99.54; 2026-06-16: 99.54
5.1.1.1 | تانک سپتیک و دو مخزن 10 هزار لیتری سه لایه |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
5.1.1.2 | کانکس نگهبانی |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
5.1.1.3 | سایر تجهیز کارگاه |  | 2026-01-11: 0; 2026-04-28: 75; 2026-05-05: 80; 2026-05-12: 80; 2026-05-19: 85; 2026-05-21: 100; 2026-05-26: 85; 2026-06-02: 85; 2026-06-09: 85; 2026-06-16: 85
5.2 | اجرای جاده دسترسی تا جاده اصلی |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
5.2.1 | زیرسازی |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
5.2.2 | شن ریزی |  | 2026-01-11: 0; 2026-04-28: 100; 2026-05-05: 100; 2026-05-12: 100; 2026-05-19: 100; 2026-05-21: 100; 2026-05-26: 100; 2026-06-02: 100; 2026-06-09: 100; 2026-06-16: 100
5.3 | عملیات عمرانی |  | 2026-01-11: 0; 2026-04-28: 0.82; 2026-05-05: 1.63; 2026-05-12: 1.83; 2026-05-19: 2.03; 2026-05-21: 2.03; 2026-05-26: 2.23; 2026-06-02: 2.63; 2026-06-09: 2.74; 2026-06-16: 2.82
5.3.1 | عملیات دسترسی و آماده سازی سایت |  | 2026-01-11: 0; 2026-04-28: 8.25; 2026-05-05: 19.25; 2026-05-12: 22; 2026-05-19: 24.75; 2026-05-21: 24.75; 2026-05-26: 27.5; 2026-06-02: 33; 2026-06-09: 33; 2026-06-16: 34.1
5.3.1.1 | تسطیح و تحکیم زمین |  | 2026-01-11: 0; 2026-04-28: 15; 2026-05-05: 35; 2026-05-12: 40; 2026-05-19: 45; 2026-05-21: 43; 2026-05-26: 50; 2026-06-02: 60; 2026-06-09: 60; 2026-06-16: 62
5.3.1.2 | اجرای گیت ورودی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.1.3 | احداث پارکینگ مسقف |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.2 | اجرای سیستم زهکشی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.2.1 | اجرای سیستم زهکشی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.3 | اجرای فنس پیرامونی |  | 2026-01-11: 0; 2026-04-28: 0.83; 2026-05-05: 0.83; 2026-05-12: 0.83; 2026-05-19: 0.83; 2026-05-21: 0.83; 2026-05-26: 0.83; 2026-06-02: 0.83; 2026-06-09: 1.25; 2026-06-16: 1.25
5.3.3.1 | اجرای فونداسیون و پایه فنس |  | 2026-01-11: 0; 2026-04-28: 10; 2026-05-05: 10; 2026-05-12: 10; 2026-05-19: 10; 2026-05-21: 10; 2026-05-26: 10; 2026-06-02: 10; 2026-06-09: 15; 2026-06-16: 15
5.3.3.2 | اجرای فنس |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.4 | اجرای فونداسیون MV Station |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.4.1 | گودبرداری فونداسیون |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.4.2 | بتن ریزی فونداسیون |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.5 | ساختمان پست سوییچگیر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.5.1 | اجرای فونداسیون ساختمان پست سوییچگیر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.5.2 | سفت کاری ساختمان پست سوییچگیر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.5.3 | اجرای تاسیسات ساختمان پست سوییچگیر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.5.4 | نازک کاری ساختمان پست سوییچگیر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.5.5 | اجرای نمای ساختمان پست سوییچگیر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.5.6 | اجرای سیستم اعلام حریق ساختمان پست سوییچگیر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.5.7 | اجرای سیستم اطفا حریق ساختمان پست سوییچگیر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.6 | ساختمان مانیتورینگ |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.6.1 | اجرای فونداسیون ساختمان مانیتورینگ |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.6.2 | سفت کاری ساختمان مانیتورینگ |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.6.3 | اجرای تاسیسات ساختمان مانیتورینگ |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.6.4 | نازک کاری ساختمان مانیتورینگ |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.6.5 | اجرای نمای ساختمان مانیتورینگ |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.6.6 | اجرای سیستم اعلام حریق ساختمان مانیتورینگ |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.6.7 | اجرای سیستم اطفا حریق ساختمان مانیتورینگ |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.6.8 | کلیه تجهیزات و ملزومات |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.7 | ساختمان نگهبانی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.7.1 | اجرای فونداسیون ساختمان نگهبانی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.7.2 | سفت کاری ساختمان نگهبانی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.7.3 | اجرای تاسیسات ساختمان نگهبانی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.7.4 | نازک کاری ساختمان نگهبانی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.7.5 | اجرای نمای ساختمان نگهبانی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.7.6 | اجرای سیستم اعلام حریق ساختمان نگهبانی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.3.7.7 | اجرای سیستم اطفا حریق ساختمان نگهبانی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.4 | عملیات مکانیکال |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.4.1 | نقشه برداری پایه ها و میخ کوبی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.4.2 | پایه کوبی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.4.3 | نصب متعلقات استراکچرها |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.4.4 | نصب پنل ها |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5 | عملیات الکتریکال |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.1 | اجرای ترانشه و کانال عبور فیبر نوری |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.2 | نصب سازه اینورتر و وایرینگ اینورترهای سایت |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.3 | اجرای سیستم زمین نیروگاه |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.4 | تابلوهای فشار متوسط و کلیه متعلقات |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.5 | تابلوهای فشار ضعیف و کلیه متعلقات |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.6 | کلیه کابل های فشار ضعیف نیروگاهac |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.7 | کلیه کابل های فشار متوسط نیروگاهac |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.8 | کابل dc |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.9 | اجرای کابل های فیبر نوری |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.10 | نصب ایستگاه هواشناسی و سنسورها |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.11 | MV Station نصب |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.12 | اجرای کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و بستر مخابراتی با پست بالادست به جز فیبر نوری |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.13 | نصب ترانسفورماتور کمکی و دیزل |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.14 | نصب یو پی اس |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.15 | سیستم حفاظت صاعقه |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.16 | اجرای کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و ارسال دیتا |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.17 | کلیه متعلقات مربوط به کابل کشی و سیم کشی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.17.1 | نصب لدر |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.17.2 | اجرای لوله پلی اتیلن و فلکسی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.17.3 | اجرای سرسیم و کابل شو |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.17.4 | اجرای سر کابل |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.18 | نصب سیستم روشنایی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.18.1 | اجرای فونداسیون سیستم روشنایی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.18.2 | کابل کشی سیستم روشنایی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.18.3 | نصب پایه ها و چراغ ها |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.19 | CCTV نصب سیستم |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.19.1 | اجرای فونداسیون دوربین |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.19.2 | کابل کشی دوربین ها |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
5.5.19.3 | نصب پایه ها و دوربین ها |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6 | تست و تحویل |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1 | تست و راه اندازی نیروگاه |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.1 | تست کلیه کابل های فشار ضعیف نیروگاهac |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.2 | تست کلیه کابل های فشار متوسط نیروگاهac |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.3 | تست کابل dc |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.4 | تست تابلوهای فشار متوسط و کلیه متعلقات |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.5 | تست کابل شبکه مورد نیازسیستم انتقال دیتا و اسکادا |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.6 | تست سیستم زمین نیروگاه |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.7 | تست کلیه متعلقات مربوط به کابل کشی و سیم کشی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.8 | تست تابلوهای فشار ضعیف و کلیه متعلقات |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.9 | تست کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و بستر مخابراتی با پست بالادست |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.10 | تست کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و ارسال دیتا |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.11 | تست یو پی اس |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.12 | تست کلیه تجهیزات مربوط به دوربین |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.13 | تست سیستم روشنایی |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.14 | تست سیستم اعلام حریق |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.15 | تست سیستم اطفا حریق |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.16 | تست سیستم حفاظت صاعقه |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.1.17 | تست ترانسفورماتور کمکی و دیزل |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.2 | ارایه نقشه های ازبیلت |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.2.1 | ارایه نقشه های ازبیلت الکتریکال |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.2.2 | ارایه نقشه های ازبیلت مکانیکال |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.2.3 | ارایه نقشه های ازبیلت civil |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.3 | راه اندازی، اتصال به شبکه و پلمپ کنتور |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.3.1 | راه اندازی، اتصال به شبکه و پلمپ کنتور |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.4 | آموزش |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.4.1 | آموزش |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.5 | برچیدن کارگاه |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
6.5.1 | برچیدن کارگاه |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0
7 | پایان |  | 2026-01-11: 0; 2026-04-28: 0; 2026-05-05: 0; 2026-05-12: 0; 2026-05-19: 0; 2026-05-21: 0; 2026-05-26: 0; 2026-06-02: 0; 2026-06-09: 0; 2026-06-16: 0

## Sheet1 (hidden)
| Document No. | Task Name | WBS | Cumulative : | Last Period :
|  |  |  | 1405/04/02 | 1405/03/26
2 |  | پروژه احداث نیروگاه خورشیدی 20 مگا واتی زارچ یزد | 0 | 44.29% | 42.33%
3 |  | شروع | 1 | 100% | 100%
4 |  | مایلستون های کلیدی | 2 | 0% | 0%
5 |  | دریافت سایر اطلاعات مقدماتی از کارفرما (آزمایش شیمیایی خاک، تست کشش پایه ها و…) | 2.1 | 100% | 100%
6 |  | واریز اولین پیش پرداخت بخش مهندسی | 2.2 | 100% | 100%
7 |  | دریافت مطالعات ژئوتکنیک | 2.3 | 100% | 100%
8 |  | تحویل زمین | 2.4 | 100% | 100%
9 |  | تاییدیه تجهیزات (پنل، اینورتر و MV Station( | 2.5 | 100% | 100%
10 |  | اتمام طراحی و اخذ تاییدیه | 2.6 | 100% | 100%
11 |  | اتمام استعلام قیمتی و سفارش گذاری خرید خارجی | 2.7 | 100% | 100%
12 |  | اتمام تامین و تحویل خرید خارجی در سایت پروژه | 2.8 | 0% | 0%
13 |  | اتمام تجهیز کارگاه | 2.9 | 100% | 100%
14 |  | اتمام نصب سازه | 2.1 | 0% | 0%
15 |  | اتمام نصب پنل | 2.11 | 0% | 0%
16 |  | اتمام ساختمان مانیتورینگ | 2.12 | 0% | 0%
17 |  | اتمام نصب MV Staion | 2.13 | 0% | 0%
18 |  | اتمام نصب اینورتر | 2.14 | 0% | 0%
19 |  | تست پست بالادست | 2.15 | 0% | 0%
20 |  | مهندسی | 3 | 85.33% | 83.07%
21 |  | مدیریت پروژه | 3.1 | 76.8% | 74.22%
22 | 410-DE-PM-LST-0084 | Master Document List | 3.1.1 | 100% | 100%
23 | 410-DE-PM-REP-0085 | Time Schedule | 3.1.2 | 100% | 100%
24 | 410-DE-PM-CAF-0086 | Cash Flow | 3.1.3 | 100% | 100%
25 | 410-DE-PM-REP-0138 | Monthly Report 410-M-001 | 3.1.4 | 100% | 100%
26 | 410-DE-PM-REP-0139 | Monthly Report 410-M-002 | 3.1.5 | 100% | 100%
27 | 410-DE-PM-REP-0140 | Monthly Report 410-M-003 | 3.1.6 | 100% | 100%
28 | 410-DE-PM-REP-0141 | Monthly Report 410-M-004 | 3.1.7 | 100% | 100%
29 | 410-DE-PM-REP-0142 | Monthly Report 410-M-005 | 3.1.8 | 40% | 0%
30 | 410-DE-PM-REP-0143 | Monthly Report 410-M-006 | 3.1.9 | 0% | 0%
31 | 410-DE-PM-REP-0144 | Monthly Report 410-M-007 | 3.1.10 | 0% | 0%
32 | 410-DE-PM-REP-0145 | Monthly Report 410-M-008 | 3.1.11 | 0% | 0%
33 |  | طراحی و اخذ تاییدیه طراحی پایه | 3.2 | 100% | 100%
34 |  | ارایه و اخذ تاییدیه دیتاشیت ها | 3.2.1 | 100% | 100%
35 | 410-BE-EL-DSH-0146 | Solar Panel Datasheet | 3.2.1.1 | 100% | 100%
36 | 410-BE-EL-DSH-0147 | Inverter Datasheet | 3.2.1.2 | 100% | 100%
37 | 410-BE-EL-DSH-0148 | MV Station Datasheet | 3.2.1.3 | 100% | 100%
38 | 410-BE-EL-DSH-0149 | DC Connection (MC4) Datasheet | 3.2.1.4 | 100% | 100%
39 | 410-BE-EL-DSH-0150 | DC Cable Datasheet | 3.2.1.5 | 100% | 100%
40 | 410-BE-EL-DSH-0151 | LV Cable Datasheet | 3.2.1.6 | 100% | 100%
41 | 410-BE-EL-DSH-0152 | MV Cable Datasheet | 3.2.1.7 | 100% | 100%
42 | 410-BE-EL-DSH-0153 | MV Switchgear (CT, PT, Relay) Datasheet | 3.2.1.8 | 100% | 100%
43 | 410-BE-EL-DSH-0154 | Earthing and Lightning Datasheet | 3.2.1.9 | 100% | 100%
44 | 410-BE-EL-DSH-0155 | Auxiliary Transformer Datasheet | 3.2.1.10 | 100% | 100%
45 | 410-BE-EL-DSH-0156 | UPS and Battery Datasheet | 3.2.1.11 | 100% | 100%
46 | 410-BE-EL-DSH-0157 | Diesel Generator Datasheet | 3.2.1.12 | 100% | 100%
47 | 410-BE-TL-DSH-0158 | Monitoring System Datasheet | 3.2.1.13 | 100% | 100%
48 | 410-BE-TL-DSH-0159 | Data Logger Datasheet | 3.2.1.14 | 100% | 100%
49 | 410-BE-TL-DSH-0160 | Weather Station Datasheet | 3.2.1.15 | 100% | 100%
50 | 410-BE-TL-DSH-0161 | CCTV and NVR Datasheet | 3.2.1.16 | 100% | 100%
51 | 410-BE-ME-DSH-0162 | HVAC Datasheet | 3.2.1.17 | 100% | 100%
52 | 410-BE-ME-DSH-0163 | Piping Material, Plumbing Fittings, Pumps Datasheet | 3.2.1.18 | 100% | 100%
53 | 410-BE-ME-DSH-0164 | Septic Tank Datasheet | 3.2.1.19 | 100% | 100%
54 | 410-BE-ME-DSH-0165 | Water TankDatasheet | 3.2.1.20 | 100% | 100%
55 | 410-BE-SF-DSH-0166 | Fire Alarm System Datasheet | 3.2.1.21 | 100% | 100%
56 |  | ارایه و اخذ تاییدیه مشخصات | 3.2.2 | 100% | 100%
57 | 410-BE-EL-SPC-0001 | Solar Panel Technical Specification | 3.2.2.1 | 100% | 100%
58 | 410-BE-EL-SPC-0002 | Inverter Technical Specification | 3.2.2.2 | 100% | 100%
59 | 410-BE-EL-SPC-0003 | MV Station Technical Specification | 3.2.2.3 | 100% | 100%
60 | 410-BE-EL-SPC-0004 | DC Connection (MC4) Technical Specification | 3.2.2.4 | 100% | 100%
61 | 410-BE-EL-SPC-0005 | DC Cable Technical Specification | 3.2.2.5 | 100% | 100%
62 | 410-BE-EL-SPC-0006 | LV Cable Technical Specification | 3.2.2.6 | 100% | 100%
63 | 410-BE-EL-SPC-0007 | MV Cable Technical Specification | 3.2.2.7 | 100% | 100%
64 | 410-BE-EL-SPC-0008 | MV Switchgear (CT, PT, Relay) Technical Specification | 3.2.2.8 | 100% | 100%
65 | 410-BE-EL-SPC-0009 | Earthing and Lightning Technical Specification | 3.2.2.9 | 100% | 100%
66 | 410-BE-EL-SPC-0013 | Auxiliary Transformer Technical Specification | 3.2.2.10 | 100% | 100%
67 | 410-BE-EL-SPC-0015 | UPS and Battery Technical Specification | 3.2.2.11 | 100% | 100%
68 | 410-BE-EL-SPC-0016 | Diesel Generator Technical Specification | 3.2.2.12 | 100% | 100%
69 | 410-BE-TL-SPC-0010 | Monitoring System Technical Specification | 3.2.2.13 | 100% | 100%
70 | 410-BE-TL-SPC-0011 | Data Logger Technical Specification | 3.2.2.14 | 100% | 100%
71 | 410-BE-TL-SPC-0012 | Weather Station Technical Specification | 3.2.2.15 | 100% | 100%
72 | 410-BE-TL-SPC-0014 | CCTV and NVR Technical Specification | 3.2.2.16 | 100% | 100%
73 | 410-BE-ME-SPC-0017 | HVAC Technical Specification | 3.2.2.17 | 100% | 100%
74 | 410-BE-ME-SPC-0018 | Piping Material, Plumbing Fittings, Pumps Technical Specification | 3.2.2.18 | 100% | 100%
75 | 410-DE-ME-SPC-0096 | Septic Tank Technical Specification | 3.2.2.19 | 100% | 100%
76 | 410-DE-ME-SPC-0097 | Water Tank Technical Specification | 3.2.2.20 | 100% | 100%
77 | 410-BE-SF-SPC-0019 | Fire Alarm System Technical Specification | 3.2.2.21 | 100% | 100%
78 | 410-BE-EL-REP-0023 | PVSYST Report | 3.2.3 | 100% | 100%
79 | 410-BE-EL-DRW-0021 | General Layout | 3.2.4 | 100% | 100%
80 | 410-BE-EL-DRW-0020 | General Single Line Diagram (GSLD) | 3.2.5 | 100% | 100%
81 | 410-BE-EL-REP-0024 | Plant Detailed Report | 3.2.6 | 100% | 100%
82 |  | طراحی و اخذ تاییدیه عمرانی مطابق MDL ارایه شده | 3.3 | 100% | 100%
83 | 410-DE-CV-REP-0087 | Topography of Field | 3.3.1 | 100% | 100%
84 | 410-DE-CV-REP-0088 | Geotechnical Test Report | 3.3.2 | 100% | 100%
85 | 410-DE-CV-REP-0089 | Ramming and Pull-Out Test Report | 3.3.3 | 100% | 100%
86 | 410-DE-CV-REP-0090 | Hydrology Study Report | 3.3.4 | 100% | 100%
87 | 410-DE-CV-DRW-0091 | Site Fence Detail Drawing | 3.3.5 | 100% | 100%
88 | 410-DE-CV-DRW-0092 | Logistic Area | 3.3.6 | 100% | 100%
89 | 410-DE-CV-CAL-0093 | Buildings Foundation & Structure Calculation | 3.3.7 | 100% | 100%
90 | 410-DE-CV-DRW-0094 | Buildings Foundation & Structure Drawing | 3.3.8 | 100% | 100%
91 | 410-DE-CV-DRW-0098 | Parking Foundation & Structure Detail Drawing | 3.3.9 | 100% | 100%
92 | 410-DE-CV-DRW-0099 | Power Plant Entrance Gate Drawing | 3.3.10 | 100% | 100%
93 | 410-DE-CV-DRW-0100 | Parking Architectural Drawing | 3.3.11 | 100% | 100%
94 | 410-DE-CV-DRW-0101 | Landscaping Layout | 3.3.12 | 100% | 100%
95 | 410-DE-CV-DRW-0102 | Buildings Architectural Detail drawing | 3.3.13 | 100% | 100%
96 | 410-DE-CV-MTO-0103 | Fence MTO | 3.3.14 | 100% | 100%
97 | 410-DE-CV-DRW-0104 | Site Grading and Leveling | 3.3.15 | 100% | 100%
98 | 410-DE-CV-DRW-0105 | Drainage For Insite of Plant & Implementation Detail Drawing | 3.3.16 | 100% | 100%
99 | 410-DE-CV-DRW-0106 | Flood Managmant For Outsite of Plant & Implementation Detail Drawing | 3.3.17 | 100% | 100%
100 | 410-DE-CV-DRW-0107 | Internal Road Layout & Implementation Detail Drawing | 3.3.18 | 100% | 100%
101 | 410-DE-CV-DRW-0108 | Access Road Layout & Implementation Detail Drawing | 3.3.19 | 100% | 100%
102 | 410-DE-CV-CAL-0109 | MV Station Foundation Calculation | 3.3.20 | 100% | 100%
103 | 410-DE-CV-DRW-0110 | MV Station Foundation Drawings | 3.3.21 | 100% | 100%
104 | 410-DE-CV-DRW-0111 | Auxiliary Transformer Foundation Detail Drawings | 3.3.22 | 100% | 100%
105 | 410-DE-CV-CAL-0112 | Calculation Report for Structure | 3.3.23 | 100% | 100%
106 | 410-DE-CV-DRW-0113 | Structure Detail Drawings | 3.3.24 | 100% | 100%
107 | 410-DE-CV-DRW-0114 | PV Structure Ramming Location Details Drawing (Stacking) | 3.3.25 | 100% | 100%
108 | 410-DE-CV-MTO-0115 | Solar Module Structure MTO | 3.3.26 | 100% | 100%
109 | 410-DE-CV-DRW-0116 | Table UTM Point | 3.3.27 | 100% | 100%
110 | 410-DE-CV-MTO-0117 | Structure, Entrance Gate and Foundation of Building MTO | 3.3.28 | 100% | 100%
111 | 410-DE-CV-CAL-0130 | System Drainage Calculation | 3.3.29 | 100% | 100%
112 | 410-DE-CV-CAL-0131 | Lighting Foundation Calculation | 3.3.30 | 100% | 100%
113 | 410-DE-CV-CAL-0132 | Lightning Foundation Calculation | 3.3.31 | 100% | 100%
114 | 410-DE-CV-DRW-0133 | Lightning Foundation Drawing | 3.3.32 | 100% | 100%
115 | 410-DE-CV-CAL-0134 | Lighting and CCTV Pole Calculation | 3.3.33 | 100% | 100%
116 | 410-DE-CV-DRW-0135 | Septic Tank Detail Drawing | 3.3.34 | 100% | 100%
117 | 410-DE-CV-DRW-0136 | Water Tank Foundation Detail Drawing | 3.3.35 | 100% | 100%
118 | 410-DE-CV-CAL-0137 | Calculation for Fence | 3.3.36 | 100% | 100%
119 | 410-DE-CV-MRE-0167 | Material Requisition for Fence | 3.3.37 | 100% | 100%
120 |  | طراحی و اخذ تاییدیه الکتریکال مطابق MDL ارایه شده | 3.4 | 100% | 93.58%
121 | 410-BE-EL-MTO-0025 | Solar Module, Connector, Inverter and MV station MTO | 3.4.1 | 100% | 100%
122 | 410-DE-EL-CAL-0022 | PV System Calculation Study (String Size, Optimum Tilt and Pitch) | 3.4.2 | 100% | 100%
123 | 410-DE-EL-DRW-0026 | Strings Connection Diagram & Inverter Arrangement (DC Side) | 3.4.3 | 100% | 100%
124 | 410-DE-EL-DRW-0027 | Module & Table Arrangement (DC Side) | 3.4.4 | 100% | 100%
125 | 410-DE-EL-CAL-0028 | DC Cable Calculation | 3.4.5 | 100% | 100%
126 | 410-DE-EL-MTO-0029 | DC Cable List, Labeling Code and MTO | 3.4.6 | 100% | 100%
127 | 410-DE-EL-CAL-0030 | LVAC Cable Calculation | 3.4.7 | 100% | 100%
128 | 410-DE-EL-LST-0031 | LV Cable Termination List and MTO | 3.4.8 | 100% | 100%
129 | 410-DE-EL-MTO-0032 | LV Cable List, Labeling Code and MTO | 3.4.9 | 100% | 100%
130 | 410-DE-EL-CAL-0033 | MV Cable Calculations | 3.4.10 | 100% | 100%
131 | 410-DE-EL-MTO-0034 | MV Cable List, Labeling Code and MTO | 3.4.11 | 100% | 100%
132 | 410-DE-EL-LST-0035 | MV Cable Termination List and MTO | 3.4.12 | 100% | 100%
133 | 410-DE-EL-DRW-0036 | Electrical Cable Route and Section | 3.4.13 | 100% | 100%
134 | 410-DE-EL-DRW-0037 | Cable Trench Layout | 3.4.14 | 100% | 100%
135 | 410-DE-EL-CAL-0038 | Earthing System Calculation | 3.4.15 | 100% | 100%
136 | 410-DE-EL-DRW-0039 | Earthing System Layout | 3.4.16 | 100% | 100%
137 | 410-DE-EL-CAL-0040 | Lightning Protection Calculation | 3.4.17 | 100% | 100%
138 | 410-DE-EL-DRW-0041 | Lightning Protection Layout | 3.4.18 | 100% | 100%
139 | 410-DE-EL-MTO-0042 | Earthing and Lightning Protection MTO | 3.4.19 | 100% | 100%
140 | 410-DE-EL-DRW-0043 | Protection Single Line Diagram (PSLD) | 3.4.20 | 100% | 100%
141 | 410-DE-EL-CAL-0044 | CT and PT Calculations | 3.4.21 | 100% | 100%
142 | 410-DE-EL-DRW-0045 | MV Switchgear Logic Diagram | 3.4.22 | 100% | 100%
143 | 410-DE-EL-REP-0046 | Trip Table | 3.4.23 | 100% | 100%
144 | 410-DE-EL-LST-0047 | Alarm List | 3.4.24 | 100% | 100%
145 | 410-DE-EL-DRW-0048 | Indoor and Outdoor Electrical Plan & Details for Building | 3.4.25 | 100% | 100%
146 | 410-DE-EL-MTO-0049 | MV Switchgear MTO | 3.4.26 | 100% | 100%
147 | 410-DE-EL-LST-0050 | Load List | 3.4.27 | 100% | 100%
148 | 410-DE-EL-DRW-0051 | LVAC Auxiliary Panel Single Line Diagram | 3.4.28 | 100% | 100%
149 | 410-DE-EL-CAL-0052 | UPS Calculation | 3.4.29 | 100% | 100%
150 | 410-DE-EL-MTO-0053 | AUX Equipment MTO (AUX Transformer, Diesel, UPS, Battery) | 3.4.30 | 100% | 100%
151 | 410-DE-EL-CAL-0058 | Indoor and Outdoor Lighting Calculation | 3.4.31 | 100% | 100%
152 | 410-DE-EL-DRW-0059 | Outdoor Lighting Pole Drawing | 3.4.32 | 100% | 100%
153 | 410-DE-EL-DRW-0060 | Outdoor Lighting Layout and Switchboard | 3.4.33 | 100% | 100%
154 | 410-DE-EL-MTO-0061 | Lighting System MTO | 3.4.34 | 100% | 100%
155 | 410-DE-EL-REP-0082 | Special Tools | 3.4.35 | 100% | 30%
156 | 410-DE-EL-DRW-0128 | MV Switchgear Schematic Diagram | 3.4.36 | 100% | 100%
157 | 410-DE-EL-DRW-0129 | MV Switchgear Front View Drawing | 3.4.37 | 100% | 100%
158 | 410-DE-EL-MRE-0168 | Material Requisition for Indoor Power and Lighting Distribution Panel | 3.4.38 | 100% | 100%
159 | 410-DE-EL-MRE-0169 | Material Requisition for Auxiliary Transformer | 3.4.39 | 100% | 100%
160 | 410-DE-EL-MRE-0170 | Material Requisition for PCC | 3.4.40 | 100% | 100%
161 | 410-DE-EL-MRE-0171 | Material Requisition for MV Switchgear (CT, PT, Relay) | 3.4.41 | 100% | 60%
162 | 410-DE-EL-MRE-0172 | Material Requisition for AC Cable | 3.4.42 | 100% | 90%
163 | 410-DE-EL-MRE-0173 | Material Requisition for DC Cable | 3.4.43 | 100% | 70%
164 | 410-DE-EL-MRE-0174 | Material Requisition for Earthing and Lightning | 3.4.44 | 100% | 60%
165 | 410-DE-EL-MRE-0175 | Material Requisition for DC Connection (MC4) | 3.4.45 | 100% | 80%
166 | 410-DE-EL-MRE-0176 | Material Requisition for Lighting System | 3.4.46 | 100% | 100%
167 | 410-DE-EL-MRE-0177 | Material Requisition for UPS and Battery | 3.4.47 | 100% | 100%
168 | 410-BE-EL-MRE-0186 | Material Requisition for Diesel Generator | 3.4.48 | 100% | 80%
169 |  | طراحی و اخذ تاییدیه مکانیکال مطابق MDL ارایه شده | 3.5 | 100% | 100%
170 | 410-DE-ME-REP-0062 | Solar Panel Cleaning & Maintenance Procedures | 3.5.1 | 100% | 100%
171 | 410-DE-ME-CAL-0066 | HVAC Equipment Calculation | 3.5.2 | 100% | 100%
172 | 410-DE-ME-DRW-0067 | HVAC Equipment Layout for Building | 3.5.3 | 100% | 100%
173 | 410-DE-ME-MTO-0068 | HVAC and Piping System MTO | 3.5.4 | 100% | 100%
174 | 410-DE-ME-DRW-0095 | Mechanical Drawing (Water Supply and Sewage Systems) | 3.5.5 | 100% | 100%
175 | 410-BE-ME-MRE-0183 | Material Requisition for Septic Tank | 3.5.6 | 100% | 100%
176 | 410-BE-ME-MRE-0184 | Material Requisition for Water | 3.5.7 | 100% | 100%
177 |  | طراحی و اخذ تاییدیه ایمنی مطابق MDL ارایه شده | 3.6 | 55.81% | 55.81%
178 | 410-DE-SF-DRW-0069 | Fire Fighting Equipment Arrangement of MV Switchgear Buildings | 3.6.1 | 100% | 100%
179 | 410-DE-SF-DRW-0070 | Outdoor Fire Fighting Equipment & Shelter Arrangement | 3.6.2 | 100% | 100%
180 | 410-DE-SF-DRW-0071 | Fire Alarm System Layout and Block Diagram | 3.6.3 | 100% | 100%
181 | 410-DE-SF-MTO-0072 | Fire and Safety and F & G System MTO | 3.6.4 | 100% | 100%
182 | 410-DE-SF-MRE-0181 | Material Requisition for Fire Alarm System | 3.6.5 | 0% | 0%
183 | 410-DE-SF-MRE-0182 | Material Requisition for Fire Fighting Equipment Arrangement | 3.6.6 | 0% | 0%
184 |  | طراحی و اخذ تاییدیه ارتباطی مطابق MDL ارایه شده | 3.7 | 88.03% | 85.64%
185 | 410-DE-TL-DRW-0054 | CCTV System Block Diagram | 3.7.1 | 100% | 100%
186 | 410-DE-TL-DRW-0055 | CCTV System Arrangement & Layout | 3.7.2 | 100% | 100%
187 | 410-DE-TL-DRW-0056 | CCTV Pole Detail Drawing, Switchboard, CAFU Details | 3.7.3 | 100% | 100%
188 | 410-DE-TL-MTO-0057 | CCTV System MTO | 3.7.4 | 100% | 100%
189 | 410-DE-TL-LST-0063 | SCADA System I/O List | 3.7.5 | 100% | 100%
190 | 410-DE-TL-DRW-0064 | Monitoring System Overall Diagram | 3.7.6 | 100% | 100%
191 | 410-DE-TL-MTO-0065 | Telecommunication and Monitoring System MTO | 3.7.7 | 100% | 100%
192 | 410-DE-TL-MRE-0178 | Material Requisition forTelecommunication and Monitoring Cable | 3.7.8 | 0% | 0%
193 | 410-BE-TL-MRE-0179 | Material Requisition forFiber Optics | 3.7.9 | 100% | 80%
194 | 410-DE-TL-MRE-0180 | Material Requisition for CCTV and NVR | 3.7.10 | 100% | 100%
195 | 410-BE-TL-MRE-0185 | Material Requisition for Weather Station | 3.7.11 | 100% | 100%
196 |  | مستندات حوزه کیفیت مطابق MDL ارایه شده | 3.8 | 20% | 20%
197 | 410-DE-QA-REP-0073 | Solar Panel Installation Manual & Operation & Maintenance | 3.8.1 | 100% | 100%
198 | 410-DE-QA-REP-0074 | Inverter Installation Manual & Operation & Maintenance | 3.8.2 | 0% | 0%
199 | 410-DE-QA-REP-0075 | MV Station Installation Manual & Operation & Maintenance | 3.8.3 | 0% | 0%
200 | 410-DE-QA-REP-0076 | UPS Installation Manual & Operation & Maintenance | 3.8.4 | 0% | 0%
201 | 410-DE-QA-REP-0077 | AUX Transformer Installation Manual & Operation & Maintenance | 3.8.5 | 0% | 0%
202 | 410-DE-QA-REP-0078 | Diesel Generator Installation Manual & Operation & Maintenance | 3.8.6 | 0% | 0%
203 | 410-DE-QA-REP-0079 | Weather Station Installation Manual & Operation & Maintenance | 3.8.7 | 0% | 0%
204 | 410-DE-QA-REP-0080 | Solar Structure Installation Manual & Operation & Maintenance | 3.8.8 | 100% | 100%
205 | 410-DE-QA-REP-0081 | SCADA and Monitoring System Installation Manual & Operation & Maintenance | 3.8.9 | 0% | 0%
206 | 410-DE-QA-REP-0083 | Project O&M General Instructions | 3.8.10 | 0% | 0%
207 | 410-DE-QA-REP-0118 | Test Report of Solar Structure | 3.8.11 | 100% | 100%
208 | 410-DE-QA-REP-0119 | Test Reports for PV Modules | 3.8.12 | 100% | 100%
209 | 410-DE-QA-REP-0120 | Test Reports for Inverter | 3.8.13 | 0% | 0%
210 | 410-DE-QA-REP-0121 | Test Reports for MV Sation | 3.8.14 | 0% | 0%
211 | 410-DE-QA-REP-0122 | Test Reports for AC and DC Cables | 3.8.15 | 0% | 0%
212 | 410-DE-QA-REP-0123 | Test Reports for Diesel Generators | 3.8.16 | 0% | 0%
213 | 410-DE-QA-REP-0124 | Test Reports for AUX Transformer | 3.8.17 | 0% | 0%
214 | 410-DE-QA-REP-0125 | Test Reports for Earthing and Ligthtning | 3.8.18 | 0% | 0%
215 | 410-DE-QA-REP-0126 | Test Reports for MV Switchgear (CT, PT, Relay, …) | 3.8.19 | 0% | 0%
216 | 410-DE-QA-REP-0127 | Test Reports for UPS and Battery | 3.8.20 | 0% | 0%
217 |  | کدگذاری و تحویل مستندات پروژه | 3.8.21 | 0% | 0%
218 |  | تامین و حمل کالا تجهیزات | 4 | 53.45% | 52.17%
219 |  | خرید و حمل داخلی | 4.1 | 21.88% | 19.73%
220 |  | خرید مصالح و تجهیز کارگاه | 4.1.1 | 100% | 100%
221 |  | مصالح ساختمانی و ملزومات عمرانی | 4.1.1.1 | 100% | 100%
222 |  | مصالح ،تجهیزات و ملزومات برقی ساختمان ها | 4.1.1.2 | 100% | 100%
223 |  | تانک سپتیک و دو مخزن 10 هزار لیتری سه لایه | 4.1.1.3 | 100% | 100%
224 |  | کلیه تجهیزات و ملزومات اداری | 4.1.1.4 | 100% | 100%
225 |  | سایر خرید تجهیز کارگاه | 4.1.1.5 | 100% | 100%
226 |  | فنس پیرامونی | 4.1.2 | 100% | 100%
227 |  | سفارش گذاری فنس پیرامونی | 4.1.2.1 | 100% | 100%
228 |  | ساخت و بازرسی فنس پیرامونی | 4.1.2.2 | 100% | 100%
229 |  | حمل فنس پیرامونی | 4.1.2.3 | 100% | 100%
230 |  | تابلو های توزیع داخلی و روشنایی | 4.1.3 | 0% | 0%
231 |  | سفارش گذاری تابلو های توزیع داخلی و روشنایی | 4.1.3.1 | 0% | 0%
232 |  | ساخت و بازرسی تابلو های توزیع داخلی و روشنایی | 4.1.3.2 | 0% | 0%
233 |  | حمل تابلو های توزیع داخلی و روشنایی | 4.1.3.3 | 0% | 0%
234 |  | ترانسفورماتور های مصرف داخلی و دیزل ژنراتور | 4.1.4 | 0% | 0%
235 |  | سفارش گذاری ترانسفورماتور های مصرف داخلی و دیزل ژنراتور | 4.1.4.1 | 0% | 0%
236 |  | ساخت و بازرسی ترانسفورماتور های مصرف داخلی و دیزل ژنراتور | 4.1.4.2 | 0% | 0%
237 |  | حمل ترانسفورماتور های مصرف داخلی و دیزل ژنراتور | 4.1.4.3 | 0% | 0%
238 |  | تابلوهای پست سوییچگیر | 4.1.5 | 26.6% | 17%
239 |  | سفارش گذاری تابلوهای پست سوییچگیر | 4.1.5.1 | 100% | 100%
240 |  | ساخت و بازرسی تابلوهای پست سوییچگیر | 4.1.5.2 | 27% | 15%
241 |  | حمل تابلوهای پست سوییچگیر | 4.1.5.3 | 0% | 0%
242 |  | ct& pt | 4.1.6 | 0% | 0%
243 |  | سفارش گذاری ct& pt | 4.1.6.1 | 0% | 0%
244 |  | ساخت و بازرسی ct& pt | 4.1.6.2 | 0% | 0%
245 |  | حمل ct& pt | 4.1.6.3 | 0% | 0%
246 |  | AC/LV و AC/MV کابل های | 4.1.7 | 4.3% | 0%
247 |  | AC/LV و AC/MV سفارش گذاری کابل های | 4.1.7.1 | 86% | 0%
248 |  | AC/LV و AC/MV ساخت و بازرسی کابل های | 4.1.7.2 | 0% | 0%
249 |  | AC/LV و AC/MV حمل کابل های | 4.1.7.3 | 0% | 0%
250 |  | DC کابل های | 4.1.8 | 0% | 0%
251 |  | DC سفارش گذاری کابل های | 4.1.8.1 | 0% | 0%
252 |  | DC ساخت و بازرسی کابل های | 4.1.8.2 | 0% | 0%
253 |  | DC حمل کابل های | 4.1.8.3 | 0% | 0%
254 |  | کابل های ارتباطی | 4.1.9 | 0% | 0%
255 |  | سفارش گذاری کابل های ارتباطی | 4.1.9.1 | 0% | 0%
256 |  | ساخت و بازرسی کابل های ارتباطی | 4.1.9.2 | 0% | 0%
257 |  | حمل کابل های ارتباطی | 4.1.9.3 | 0% | 0%
258 |  | Fiber Optics (انتقال دیتا داخلی نیروگاه) | 4.1.10 | 0% | 0%
259 |  | Fiber Optics سفارش گذاری (انتقال دیتا داخلی نیروگاه) | 4.1.10.1 | 0% | 0%
260 |  | Fiber Optics ساخت و بازرسی (انتقال دیتا داخلی نیروگاه) | 4.1.10.2 | 0% | 0%
261 |  | Fiber Optics حمل (انتقال دیتا داخلی نیروگاه) | 4.1.10.3 | 0% | 0%
262 |  | کابل سیستم زمین و تجهیزات جانبی (ارت) | 4.1.11 | 0% | 0%
263 |  | سفارش گذاری کابل سیستم زمین و تجهیزات جانبی (ارت) | 4.1.11.1 | 0% | 0%
264 |  | ساخت و بازرسی کابل سیستم زمین و تجهیزات جانبی (ارت) | 4.1.11.2 | 0% | 0%
265 |  | حمل کابل سیستم زمین و تجهیزات جانبی (ارت) | 4.1.11.3 | 0% | 0%
266 |  | MC4 | 4.1.12 | 0% | 0%
267 |  | MC4 سفارش گذاری | 4.1.12.1 | 0% | 0%
268 |  | MC4 ساخت و بازرسی | 4.1.12.2 | 0% | 0%
269 |  | MC4 حمل | 4.1.12.3 | 0% | 0%
270 |  | و تجهیزات جانبیCCTV سیستم | 4.1.13 | 12.2% | 2.15%
271 |  | و تجهیزات جانبیCCTV سفارش گذاری سیستم | 4.1.13.1 | 100% | 43%
272 |  | و تجهیزات جانبیCCTV ساخت و بازرسی سیستم | 4.1.13.2 | 9% | 0%
273 |  | و تجهیزات جانبیCCTV حمل سیستم | 4.1.13.3 | 0% | 0%
274 |  | تجهیزات سیستم روشنایی | 4.1.14 | 12.99% | 2%
275 |  | سفارش گذاری تجهیزات سیستم روشنایی | 4.1.14.1 | 100% | 40%
276 |  | ساخت و بازرسی تجهیزات سیستم روشنایی | 4.1.14.2 | 10% | 0%
277 |  | حمل تجهیزات سیستم روشنایی | 4.1.14.3 | 0% | 0%
278 |  | UPS سیستم | 4.1.15 | 85% | 85%
279 |  | UPS سفارش گذاری سیستم | 4.1.15.1 | 100% | 100%
280 |  | UPS خرید سیستم | 4.1.15.2 | 100% | 100%
281 |  | UPS حمل سیستم | 4.1.15.3 | 0% | 0%
282 |  | سیستم اعلان حریق و تجهیزات جانبی | 4.1.16 | 0% | 0%
283 |  | سفارش گذاری سیستم اعلان حریق و تجهیزات جانبی | 4.1.16.1 | 0% | 0%
284 |  | ساخت و بازرسی سیستم اعلان حریق و تجهیزات جانبی | 4.1.16.2 | 0% | 0%
285 |  | حمل سیستم اعلان حریق و تجهیزات جانبی | 4.1.16.3 | 0% | 0%
286 |  | سیستم اطفا حریق و تجهیزات جانبی | 4.1.17 | 0% | 0%
287 |  | سفارش گذاری سیستم اطفا حریق و تجهیزات جانبی | 4.1.17.1 | 0% | 0%
288 |  | ساخت و بازرسی سیستم اطفا حریق و تجهیزات جانبی | 4.1.17.2 | 0% | 0%
289 |  | حمل سیستم اطفا حریق و تجهیزات جانبی | 4.1.17.3 | 0% | 0%
290 |  | ایستگاه هواشناسی و سنسورها | 4.1.18 | 100% | 97.9%
291 |  | سفارش گذاری ایستگاه هواشناسی و سنسورها | 4.1.18.1 | 100% | 100%
292 |  | ساخت و بازرسی ایستگاه هواشناسی و سنسورها | 4.1.18.2 | 100% | 100%
293 |  | حمل ایستگاه هواشناسی و سنسورها | 4.1.18.3 | 100% | 86%
294 |  | لوازم یدکی | 4.1.19 | 0% | 0%
295 |  | لوازم یدکی | 4.1.19.1 | 0% | 0%
296 |  | خرید خارجی، حمل بین المللی و ترخیص | 4.2 | 100% | 100%
297 |  | خرید سازه های نگهدارنده پنل ها و اینورترها | 4.2.1 | 100% | 100%
298 |  | استعلام قیمت و سفارش گذاری سازه های نگهدارنده | 4.2.1.1 | 100% | 100%
299 |  | ساخت سازه های نگهدارنده و بازرسی قبل حمل | 4.2.1.2 | 100% | 100%
300 |  | حمل خارجی سازه های نگهدارنده | 4.2.1.3 | 100% | 100%
301 |  | ترخیص سازه های نگهدارنده | 4.2.1.4 | 100% | 100%
302 |  | حمل داخلی سازه های نگهدارنده و تحویل در سایت | 4.2.1.5 | 100% | 100%
303 |  | خرید پنل های خورشیدی | 4.2.2 | 0% | 0%
304 |  | استعلام قیمت و ثبت سفارش پنل های خورشیدی | 4.2.2.1 | 100% | 100%
305 |  | ساخت پنل های خورشیدی و بازرسی قبل حمل | 4.2.2.2 | 100% | 100%
306 |  | حمل خارجی پنل های خورشیدی | 4.2.2.3 | 100% | 100%
307 |  | ترخیص پنل های خورشیدی | 4.2.2.4 | 100% | 100%
308 |  | حمل داخلی پنل های خورشیدی و تحویل در سایت | 4.2.2.5 | 100% | 100%
309 |  | خرید اینورترهای خورشیدی | 4.2.3 | 0% | 0%
310 |  | استعلام قیمت و ثبت سفارش اینورترهای خورشیدی | 4.2.3.1 | 100% | 100%
311 |  | ساخت اینورترهای خورشیدی و بازرسی قبل حمل | 4.2.3.2 | 100% | 100%
312 |  | حمل خارجی اینورترهای خورشیدی | 4.2.3.3 | 84% | 69%
313 |  | ترخیص اینورترهای خورشیدی | 4.2.3.4 | 0% | 0%
314 |  | حمل داخلی اینورترهای خورشیدی و تحویل در سایت | 4.2.3.5 | 0% | 0%
315 |  | خرید MV Station | 4.2.4 | 0% | 0%
316 |  | استعلام قیمت و ثبت سفارش MV Station | 4.2.4.1 | 100% | 100%
317 |  | ساخت MV Station و بازرسی قبل حمل | 4.2.4.2 | 100% | 100%
318 |  | حمل خارجی MV Station | 4.2.4.3 | 84% | 69%
319 |  | ترخیص MV Station | 4.2.4.4 | 0% | 0%
320 |  | حمل داخلی MV Station و تحویل در سایت | 4.2.4.5 | 0% | 0%
321 |  | عملیات اجرایی | 5 | 19.79% | 15.9%
322 |  | تجهیز کارگاه | 5.1 | 100% | 100%
323 |  | عملیات اجرایی | 5.1.1 | 100% | 100%
324 |  | تانک سپتیک و دو مخزن 10 هزار لیتری سه لایه | 5.1.1.1 | 100% | 100%
325 |  | کانکس نگهبانی | 5.1.1.2 | 100% | 100%
326 |  | سایر تجهیز کارگاه | 5.1.1.3 | 100% | 100%
327 |  | اجرای جاده دسترسی تا جاده اصلی | 5.2 | 100% | 100%
328 |  | زیرسازی | 5.2.1 | 100% | 100%
329 |  | شن ریزی | 5.2.2 | 100% | 100%
330 |  | عملیات عمرانی | 5.3 | 39.91% | 29.79%
331 |  | عملیات دسترسی و آماده سازی سایت | 5.3.1 | 55% | 55%
332 |  | تسطیح و تحکیم زمین | 5.3.1.1 | 100% | 100%
333 |  | اجرای گیت ورودی | 5.3.1.2 | 0% | 0%
334 |  | احداث پارکینگ مسقف | 5.3.1.3 | 0% | 0%
335 |  | اجرای سیستم زهکشی | 5.3.2 | 68% | 50%
336 |  | اجرای سیستم زهکشی | 5.3.2.1 | 68% | 50%
337 |  | اجرای فنس پیرامونی | 5.3.3 | 42.25% | 23.92%
338 |  | اجرای فونداسیون و پایه فنس | 5.3.3.1 | 100% | 100%
339 |  | اجرای فنس | 5.3.3.2 | 37% | 17%
340 |  | اجرای فونداسیون MV Station | 5.3.4 | 0% | 0%
341 |  | گودبرداری فونداسیون | 5.3.4.1 | 0% | 0%
342 |  | بتن ریزی فونداسیون | 5.3.4.2 | 0% | 0%
343 |  | ساختمان پست سوییچگیر | 5.3.5 | 35.6% | 30.59%
344 |  | اجرای فونداسیون ساختمان پست سوییچگیر | 5.3.5.1 | 100% | 100%
345 |  | سفت کاری ساختمان پست سوییچگیر | 5.3.5.2 | 52% | 40%
346 |  | اجرای تاسیسات ساختمان پست سوییچگیر | 5.3.5.3 | 0% | 0%
347 |  | نازک کاری ساختمان پست سوییچگیر | 5.3.5.4 | 0% | 0%
348 |  | اجرای نمای ساختمان پست سوییچگیر | 5.3.5.5 | 0% | 0%
349 |  | اجرای سیستم اعلام حریق ساختمان پست سوییچگیر | 5.3.5.6 | 0% | 0%
350 |  | اجرای سیستم اطفا حریق ساختمان پست سوییچگیر | 5.3.5.7 | 0% | 0%
351 |  | ساختمان مانیتورینگ | 5.3.6 | 15.85% | 11.33%
352 |  | اجرای فونداسیون ساختمان مانیتورینگ | 5.3.6.1 | 100% | 100%
353 |  | سفت کاری ساختمان مانیتورینگ | 5.3.6.2 | 24% | 10%
354 |  | اجرای تاسیسات ساختمان مانیتورینگ | 5.3.6.3 | 0% | 0%
355 |  | نازک کاری ساختمان مانیتورینگ | 5.3.6.4 | 0% | 0%
356 |  | اجرای نمای ساختمان مانیتورینگ | 5.3.6.5 | 0% | 0%
357 |  | اجرای سیستم اعلام حریق ساختمان مانیتورینگ | 5.3.6.6 | 0% | 0%
358 |  | اجرای سیستم اطفا حریق ساختمان مانیتورینگ | 5.3.6.7 | 0% | 0%
359 |  | کلیه تجهیزات و ملزومات | 5.3.6.8 | 0% | 0%
360 |  | ساختمان نگهبانی | 5.3.7 | 84.17% | 77.41%
361 |  | اجرای فونداسیون ساختمان نگهبانی | 5.3.7.1 | 100% | 100%
362 |  | سفت کاری ساختمان نگهبانی | 5.3.7.2 | 100% | 100%
363 |  | اجرای تاسیسات ساختمان نگهبانی | 5.3.7.3 | 100% | 100%
364 |  | نازک کاری ساختمان نگهبانی | 5.3.7.4 | 100% | 100%
365 |  | اجرای نمای ساختمان نگهبانی | 5.3.7.5 | 100% | 20%
366 |  | اجرای سیستم اعلام حریق ساختمان نگهبانی | 5.3.7.6 | 0% | 0%
367 |  | اجرای سیستم اطفا حریق ساختمان نگهبانی | 5.3.7.7 | 0% | 0%
368 |  | عملیات مکانیکال | 5.4 | 33.63% | 25.67%
369 |  | نقشه برداری پایه ها و میخ کوبی | 5.4.1 | 100% | 100%
370 |  | پایه کوبی | 5.4.2 | 74% | 59%
371 |  | نصب متعلقات استراکچرها | 5.4.3 | 54% | 41%
372 |  | نصب پنل ها | 5.4.4 | 3% | 0%
373 |  | عملیات الکتریکال | 5.5 | 0% | 0%
374 |  | اجرای ترانشه و کانال عبور فیبر نوری | 5.5.1 | 0% | 0%
375 |  | نصب سازه اینورتر و وایرینگ اینورترهای سایت | 5.5.2 | 0% | 0%
376 |  | اجرای سیستم زمین نیروگاه | 5.5.3 | 0% | 0%
377 |  | تابلوهای فشار متوسط و کلیه متعلقات | 5.5.4 | 0% | 0%
378 |  | تابلوهای فشار ضعیف و کلیه متعلقات | 5.5.5 | 0% | 0%
379 |  | کلیه کابل های فشار ضعیف نیروگاهac | 5.5.6 | 0% | 0%
380 |  | کلیه کابل های فشار متوسط نیروگاهac | 5.5.7 | 0% | 0%
381 |  | کابل dc | 5.5.8 | 0% | 0%
382 |  | اجرای کابل های فیبر نوری | 5.5.9 | 0% | 0%
383 |  | نصب ایستگاه هواشناسی و سنسورها | 5.5.10 | 0% | 0%
384 |  | MV Station نصب | 5.5.11 | 0% | 0%
385 |  | اجرای کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و بستر مخابراتی با پست بالادست به جز فیبر نوری | 5.5.12 | 0% | 0%
386 |  | نصب ترانسفورماتور کمکی و دیزل | 5.5.13 | 0% | 0%
387 |  | نصب یو پی اس | 5.5.14 | 0% | 0%
388 |  | سیستم حفاظت صاعقه | 5.5.15 | 0% | 0%
389 |  | اجرای کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و ارسال دیتا | 5.5.16 | 0% | 0%
390 |  | کلیه متعلقات مربوط به کابل کشی و سیم کشی | 5.5.17 | 0% | 0%
391 |  | نصب لدر | 5.5.17.1 | 0% | 0%
392 |  | اجرای لوله پلی اتیلن و فلکسی | 5.5.17.2 | 0% | 0%
393 |  | اجرای سرسیم و کابل شو | 5.5.17.3 | 0% | 0%
394 |  | اجرای سر کابل | 5.5.17.4 | 0% | 0%
395 |  | نصب سیستم روشنایی | 5.5.18 | 0% | 0%
396 |  | اجرای فونداسیون سیستم روشنایی | 5.5.18.1 | 0% | 0%
397 |  | کابل کشی سیستم روشنایی | 5.5.18.2 | 0% | 0%
398 |  | نصب پایه ها و چراغ ها | 5.5.18.3 | 0% | 0%
399 |  | CCTV نصب سیستم | 5.5.19 | 0% | 0%
400 |  | اجرای فونداسیون دوربین | 5.5.19.1 | 0% | 0%
401 |  | کابل کشی دوربین ها | 5.5.19.2 | 0% | 0%
402 |  | نصب پایه ها و دوربین ها | 5.5.19.3 | 0% | 0%
403 |  | تست و تحویل | 6 | 0% | 0%
404 |  | تست و راه اندازی نیروگاه | 6.1 | 0% | 0%
405 |  | تست کلیه کابل های فشار ضعیف نیروگاهac | 6.1.1 | 0% | 0%
406 |  | تست کلیه کابل های فشار متوسط نیروگاهac | 6.1.2 | 0% | 0%
407 |  | تست کابل dc | 6.1.3 | 0% | 0%
408 |  | تست تابلوهای فشار متوسط و کلیه متعلقات | 6.1.4 | 0% | 0%
409 |  | تست کابل شبکه مورد نیازسیستم انتقال دیتا و اسکادا | 6.1.5 | 0% | 0%
410 |  | تست سیستم زمین نیروگاه | 6.1.6 | 0% | 0%
411 |  | تست کلیه متعلقات مربوط به کابل کشی و سیم کشی | 6.1.7 | 0% | 0%
412 |  | تست تابلوهای فشار ضعیف و کلیه متعلقات | 6.1.8 | 0% | 0%
413 |  | تست کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و بستر مخابراتی با پست بالادست | 6.1.9 | 0% | 0%
414 |  | تست کلیه ملزومات و تجهیزات مربوط به ایجاد شبکه انتقال دیتا و ارسال دیتا | 6.1.10 | 0% | 0%
415 |  | تست یو پی اس | 6.1.11 | 0% | 0%
416 |  | تست کلیه تجهیزات مربوط به دوربین | 6.1.12 | 0% | 0%
417 |  | تست سیستم روشنایی | 6.1.13 | 0% | 0%
418 |  | تست سیستم اعلام حریق | 6.1.14 | 0% | 0%
419 |  | تست سیستم اطفا حریق | 6.1.15 | 0% | 0%
420 |  | تست سیستم حفاظت صاعقه | 6.1.16 | 0% | 0%
421 |  | تست ترانسفورماتور کمکی و دیزل | 6.1.17 | 0% | 0%
422 |  | ارایه نقشه های ازبیلت | 6.2 | 0% | 0%
423 |  | ارایه نقشه های ازبیلت الکتریکال | 6.2.1 | 0% | 0%
424 |  | ارایه نقشه های ازبیلت مکانیکال | 6.2.2 | 0% | 0%
425 |  | ارایه نقشه های ازبیلت civil | 6.2.3 | 0% | 0%
426 |  | راه اندازی، اتصال به شبکه و پلمپ کنتور | 6.3 | 0% | 0%
427 |  | راه اندازی، اتصال به شبکه و پلمپ کنتور | 6.3.1 | 0% | 0%
428 |  | آموزش | 6.4 | 0% | 0%
429 |  | آموزش | 6.4.1 | 0% | 0%
430 |  | برچیدن کارگاه | 6.5 | 0% | 0%
431 |  | برچیدن کارگاه | 6.5.1 | 0% | 0%
432 |  | پایان | 7 | 0% | 0%