## Cover
PKSP
20 MW Zarch Solar Power Planet Project
Contract No: PKSP-P2-C2-0410 |  |  | Document No: |  | Rev: |  | Issue date:
Document Title: |  |  | ITP for pv |  |  |  | Page: 1 of 23 (QCP)
ITP for PV Module – Factory Acceptance Test
`
02 |  | Issued for Construction
01 |  | Issued for Construction
00 |  | Issued for Review
Rev. | Date | Purpose of Issue |  | Prepared By |  | Checked By |  | Approved By

## Rev
PKSP
20 MW Zarch Solar Power Planet Project
Contract No: PKSP-P2-C2-0410 |  |  |  |  | Document No: | [12 empty] | Rev: |  |  | Issue date:
Document Title: |  |  |  |  | ITP for PV | [15 empty] | Page: 2 of 23 (QCP)
Tabulation of Revised Page
| Sheet | Revisions | [10 empty] | Sheet | Revisions
|  | 00 | 01 | 02 |  | 03 | 04 | 05 | 06 | 07 | 08 | 09 |  | 00 | 01 | 02 | 03 |  | 04 | 05 | 06 | 07 | 08 | 09
| 1 | [11 empty] | 41
| 2 | [11 empty] | 42
| 3 | [11 empty] | 43
| 4 | [11 empty] | 44
| 5 | [11 empty] | 45
| 6 | [11 empty] | 46
| 7 | [11 empty] | 47
| 8 | [11 empty] | 48
| 9 | [11 empty] | 49
| 10 | [11 empty] | 50
| 11 | [11 empty] | 51
| 12 | [11 empty] | 52
| 13 | [11 empty] | 53
| 14 | [11 empty] | 54
| 15 | [11 empty] | 55
| 16 | [11 empty] | 56
| 17 | [11 empty] | 57
| 18 | [11 empty] | 58
| 19 | [11 empty] | 59
| 20 | [11 empty] | 60
| 21 | [11 empty] | 61
| 22 | [11 empty] | 62
| 23 | [11 empty] | 63
| 24 | [11 empty] | 64
| 25 | [11 empty] | 65
| 26 | [11 empty] | 66
| 27 | [11 empty] | 67
| 28 | [11 empty] | 68
| 29 | [11 empty] | 69
| 30 | [11 empty] | 70
| 31 | [11 empty] | 71
| 32 | [11 empty] | 72
| 33 | [11 empty] | 73
| 34 | [11 empty] | 74
| 35 | [11 empty] | 75
| 36 | [11 empty] | 76
| 37 | [11 empty] | 77
| 38 | [11 empty] | 78
| 39 | [11 empty] | 79
| 40 | [11 empty] | 80

## Act
PKSP
20 MW Zarch Solar Power Planet Project
Contract No: PKSP-P2-C2-0410 |  |  |  | Document No: | Rev: | Issue date:
Document Title: |  |  |  | ITP for PV |  | Page: 3 of 23 (QCP)
1. Purpose
The purpose of this inspection and test plan is to establish the inspections and tests in conjunction with quality plan for site activities at Concrete work
2. Definitions
Project: ZARCH Project
|  | OW | Employer: PKSPCO
|  | SP | Site Supervision :
|  | CO | EPC Contractor:
|  | H | Hold point (Notification required, Presence is mandatory)
|  | W | Witness (Notification required, Presence not mandatory)
|  | RC | Random Check (Notification required, Presence not mandatory)
|  | RD | Review of Documents
|  | A | Approved
|  | SW | Spot Witness (Notification required, Presence not mandatory)
3. References
Codes and standards for inspections and tests shall be in accordance with those specified in the contractual documents, purchase orders, requisitions, specifications, data sheets, drawings and company official instructions. Applicable Standards: IEC 61215, IEC 61730, IEC 61701 (if applicable), IEC 62716 (if applicable)
4.Responsibilities
Contractor is responsible for performance of all inspections and tests and he shall prepare relative documents and inspection reports in accordance with project specification and ITP. Inspections shall be performed by qualified inspectors employed by contractor.
As required by requisition, Subcontractor shall prepare fabrication, execution, inspection and repair procedure and specific method statement and submit to Contractor for review and approval of Contractor/Company prior to use.
The contractor shall control the individual inspection procedures for in process or final inspection / testing and records. The record means work instructions, checklists and test records which give evidence that the work has passed inspection and/or testing with specified acceptance criteria

## ITP 1
PKSP
20 MW Zarch Solar Power Planet Project
Contract No: PKSP-P2-C2-0410 |  |  | Document No: |  |  | Rev: 00 |  | Issue date:
Document Title: |  |  | ITP for PV |  |  |  |  | Page: 5 of 23 (QCP)
Inspection and test plan (ITP)
| Row | Step of inspection / Activity |  | Reference | ACCEPTANCE CRITERIA) | inspection position |  |  |  | Note
|  |  |  | procedure /spec/code |  | ntech | ins |  | pksp
| 1 | DOCUMENT APPROVAL
| 1.1 | CHECK approved drawing for latest revision |  | spec | Fully compliant | H | R |  | R
| 1.2 | IEC 61215 Certificate |  | IEC 61215 | Valid & approved | H | R |  | R
| 1.3 | IEC 61730 Certificate |  | IEC 61730 | Valid & approved | H | R |  | R
| 2 | testing equipment |  |  | Q06-001-COW-03 | H | RC
| 2.1 | mult-imeter
| 2.2 | insulation resistance tester
| 2.3 | level meter, feeler gauge, torque wrench
| 3 | VISUAL INSPECTION(Glass / Frame Condition) |  | IEC 61215 | No cracks or damage | H | H |  | RC
| 4 | ELECTRICAL
| 3.1 | electrolominsans |  | IEC 61215/IEC 61730/ul 1703/ul 61730 |  | H
| 3.2 | iv curve |  | IEC 61215/IEC 61730/ul 1703/ul 61731 |  | H
| 3.3 | insulation resistance test |  | IEC 61215/IEC 61730/ul 1703/ul 61732 |  | H
| 3.4 | PID(POTENTIAL INDUCED DEGRADATION) |  | IEC 61215/IEC 61730/ul 1703/ul 61733 |  | H
| 3.5 | STATIC LOAD TEST |  | IEC 61215/IEC 61730/ul 1703/ul 61734 |  | H
| 3.6 | DYNAMIC LOAD TEST |  | IEC 61215/IEC 61730/ul 1703/ul 61735 |  | H
| 3.7 | DAMP HEAT/THERMAL CYCLING |  | IEC 61215/IEC 61730/ul 1703/ul 61736 |  | H
| 3.8 | LOW IRRADIANCE TEST |  | IEC 61215/IEC 61730/ul 1703/ul 61737 |  | H
| 3.9 | UV TEST |  | IEC 61215/IEC 61730/ul 1703/ul 61738 |  | H

## INSPECTION CHECK LIST
INSPECTION CHECK LIST
1 | Approved Datasheet verified
2 | IEC certificates verified
3 | Visual inspection passed
4 | Flash test within tolerance
5 | EL test acceptable
6 | IR and continuity tests passed
7 | Label and serial number verified
8 | Packing suitable for shipment