## Sheet1
پیوست 2
خدمات مهندسی احداث نیروگاه خورشیدی بظرفیت 10MW
بخش اول | انجام مطالعات عمومی و طراحی پایه
Document Number | Description | Discipline
2026.B.EL.REP.001 | بررسی دستورالعمل‌های موجود در زمینه احداث نیروگاه‌های تجدیدپذیر در ایران | Electrical
2026.B.EL.REP.002 | مطالعه و بررسی تكنولوژي‌هاي روز دنيا در زمینه تجهیزات نیروگاه‌های خورشیدی و مقایسه فنی و اقتصادی میان آن‌ها | Electrical
2026.B.CV.REP.003 | مطالعات زمین شناسی، زلزله شناسی و لرزه خیزی منطقه | Civil
2026.B.EL.REP.004 | مطالعات هواشناسی | Electrical
2026.B.EL.REP.005 | مطالعات تابش خورشید و تولید | Electrical
2026.B.CV.REP.006 | مطالعات هیدرولوژی | Civil
2026.B.EL.REP.007 | مطالعات مقدماتی و بررسی الزامات کلی محیط زیست | Electrical
2026.B.EL.REP.008 | مطالعات کاربری اراضی و طرح های توسعه در منطقه | Electrical
2026.B.EL.REP.009 | مطالعات مقدماتی پدافند غیر عامل و مرور الزامات اولیه پدافند غیر عامل | Electrical
2026.B.EL.REP.010 | مطالعات امکانسنجی نیروگاه خورشیدی شامل مطالعات اقتصادی و توجیه پذیری پروژه | Electrical
2026.B.EL.REP.011 | انجام مطالعات ژئوتکنیک و ژئو الکتریک (حفاری گمانه های ژئوتکنیکی بوسیله کارفرما انجام می­شود.) | Electrical
بخش دوم | اخذ مجوزات مورد نیاز
Document Number | Description | Discipline
2026.B.PR.REP.012 | اخذ مجوز احداث | Process
2026.B.PR.REP.013 | اخذ مجوز ساتبا | Process
2026.B.PR.REP.014 | هماهنگی و نظارت بر انجام مطالعات طرح اتصال نیروگاه به شبکه انتقال نیروی | Process
2026.B.PR.OTH.015 | شرکت در جلسات هماهنگی و بحث و بررسی طرحهای اتصال در شرکت توزیع برق | Process
2026.B.PR.PRC.016 | همکاری در اخذ تائید طرح اتصال به شبکه نیروگاه و ارائه مدارک مربوطه به کارفرما | Process
2026.B.PR.REP.017 | تهیه و ارسال گزارش جامع مطالعات زیست محیطی نیروگاه | Process
2026.B.PR.OTH.018 | پیگیری موضوع، شرکت در جلسات و رفع اشکالات احتمالی گزارش مطالعات | Process
2026.B.PR.PRC.019 | همکاری جهت اخذ مجوز محیط زیست | Process
2026.B.PR.REP.020 | تهیه و ارسال گزارش جامع مطالعات زمین نیروگاه | Process
2026.B.PR.PRC.021 | همکاری جهت اخذ مجوز منابع طبیعی | Process
2026.B.PR.REP.022 | تکمیل فرم های درخواست احداث نیروگاه تجدید پذیر و تنظیم مدارک مورد نیاز با همکاری کارفرما | Process
2026.B.PR.REP.023 | نهایی کردن قرارداد با ساتبا حهت فروش روی تابلو برق سبز و انجام کلیه امور اداری و پیگیری های مربوطه | Process
2026.B.PR.REP.024 | عقد قرارداد با ساتبا | Process
بخش سوم | خدمات مهندسی پایه و تفصیلی (Basic & Detailed)
Document Number | Description | Discipline
2026.D.EL.CAL.025 | PV System Calculation Study (Array and String Sizing, Cable Sizing,...) | Electrical
2026.D.EL.CAL.026 | PVSyst Calculation and Report | Electrical
2026.D.EL.PLP.027 | Plot Plan of Solar Power Plant | Electrical
2026.D.EL.SLD.028 | Solar Power Plant Single Line Diagam | Electrical
2026.D.EL.CAL.029 | Shadow Calculation and Simulation for solar power plant | Electrical
2026.D.EL.SPC.030 | Technical Specification and DataSheet for Solar Inverter | Electrical
2026.D.EL.SPC.031 | Technical Specification and DataSheet for Solar PV Module | Electrical
2026.D.EL.SPC.032 | Technical Specification and DataSheet for AC and DC Combiner Boxes | Electrical
2026.D.EL.SPC.033 | Technical Specification and DataSheet for DC Cable | Electrical
2026.D.EL.SPC.034 | Technical Specification and DataSheet for AC Cable | Electrical
2026.D.EL.SPC.035 | Technical Specification and DataSheet for Auxiliary and Power Transformers | Electrical
2026.D.EL.SPC.035 | Technical Specification and DataSheet for Diesel Generator | Electrical
2026.D.EL.SPC.036 | Technical Specification and DataSheet for CCTV | Electrical
2026.D.EL.SPC.037 | Technical Specification and DataSheet for Lighting System | Electrical
2026.D.EL.SPC.038 | Technical Specification for Monitoring System and SCADA | Electrical
2026.D.EL.SPC.039 | Technical Specification and DataSheet for UPS and Battery | Electrical
2026.D.EL.SPC.040 | Technical Specification and DataSheet for Fire and Safety System | Electrical
2026.D.EL.SPC.041 | Technical Specification and DataSheet for F&G System | Electrical
2026.D.EL.SPC.042 | Technical Specification and DataSheet for LV Switchgear | Electrical
2026.D.EL.SPC.043 | Technical Specification and DataSheet for MV Switchgear | Electrical
2026.D.EL.SPC.044 | Technical Specification for Lightning and Earthing System | Electrical
2026.D.EL.SPC.045 | Technical Specification and DataSheet for Solar Structure and Fence | Electrical
2026.D.EL.SPC.046 | Technical Specification for Cleaning System | Electrical
2026.D.EL.SPC.047 | Technical Specification for Building | Electrical
2026.D.EL.SPC.048 | Technical Specification and DataSheet for HVAC System | Electrical
2026.D.EL.SPC.049 | Technical Specification and DataSheet for Weather Monitoring Station | Electrical
2026.D.EL.VLS.050 | List of Active Vendors in Supporting Solar Power Plant Equipment | Electrical
2026.D.EL.LIT.051 | List of Active EPC Contractors | Electrical
2026.D.EL.MTO.052 | Material Take Off for Solar Power Plant | Electrical
2026.D.EL.CAL.053 | Lighting System Calculation | Electrical
2026.D.EL.DWG.054 | Lighting System Layout | Electrical
2026.D.EL.CAL.055 | Earthing and Lightening Calculation | Electrical
2026.D.EL.DWG.056 | Earthing and Lightening Layout | Electrical
2026.D.EL.DWG.057 | CCTV System Layout | Electrical
2026.D.EL.DWG.058 | Solar Power Plant Cable Route Layout | Electrical
2026.D.EL.DWG.059 | Fire and Safety Equipment Layout | Electrical
2026.D.EL.MTO.060 | Material Take Off for Safety | Electrical
2026.D.EL.BDX.061 | SCADA and Telecommunication System Block Diagram | Electrical
2026.D.EL.DWG.062 | SCADA and Telecommunication System Layout | Electrical
2026.D.EL.LIT.063 | SCADA System I/O List | Electrical
2026.D.EL.MTO.064 | Material Take Off for SCADA and Telecommunication system | Electrical
2026.D.EL.LIT.065 | Cable list | Electrical
2026.D.EL.LIT.066 | Load list | Electrical
2026.D.EL.SLD.067 | General Single Line Diagram for MV Switchgear | Electrical
2026.D.EL.SLD.068 | Control, Protection and Metering Single Line Diagram for Substation | Electrical
2026.D.EL.REP.069 | Cost Estimation Report of Solar Power Plant | Electrical
2026.D.EL.SLD.070 | LVAC Auxiliary Single Line Diagram | Electrical
2026.D.EL.DWG.071 | Equipment Arrangement for MV Switchgear | Electrical
2026.D.EL.SPC.072 | Technical Specification and DataSheet for MV Switchgear(EXTENSION 63/20KV SUB.) | Electrical
2026.D.EL.SLD.073 | PROTECTION & CONTROL SLD for MV Switchgear(EXTENSION 63/20KV SUB.) | Electrical
2026.D.EL.PLAN.074 | PANEL ARRENGEMENT for MV Switchgear(EXTENSION 63/20KV SUB.) | Electrical
2026.D.EL.LIT.075 | تهیه اسناد فنی و بازرگانی مناقصه خط انتقال نیرو (فیمابین نیروگاه و پست 63/20KV ) | Electrical
2026.D.EL.REP.076 | ارزیابی پیمانکاران و تهیه وندور لیست و تهیه گزارش بررسی و ارزیابی مدارک پیمانکاران | Electrical
2026.D.IN.PRC.077 | Guide for Inspection and Test Procedure for PV Panel | Instrument/ Control System
2026.D.IN.PRC.078 | Guide for Inspection and Test Procedure for Inverter | Instrument/ Control System
2026.D.IN.PRC.079 | Guide for Inspection and Test Procedure for DC cables | Instrument/ Control System
2026.D.IN.PRC.080 | Guide for Inspection and Test Procedure for MV cables | Instrument/ Control System
2026.D.IN.PRC.081 | Guide for Inspection and Test Procedure for LV cables | Instrument/ Control System
2026.D.IN.PRC.082 | Guide for Inspection and Test Procedure for MV Switchgear | Instrument/ Control System
2026.D.IN.PRC.083 | Guide for Inspection and Test Procedure for LV Switchgear | Instrument/ Control System
2026.D.IN.PRC.084 | Guide for Inspection and Test Procedure for Transformer and Auxiliary | Instrument/ Control System
2026.D.IN.PRC.085 | Guide for Inspection and Test Procedure for Earthing System Equipment | Instrument/ Control System
2026.D.IN.PRC.086 | Guide for Inspection and Test Procedure for UPS And Batteries | Instrument/ Control System
2026.D.IN.PRC.087 | Guide for Inspection and Test Procedure for Solar Module Structure | Instrument/ Control System
2026.D.IN.PRC.088 | Guide for Inspection and Test Procedure for Disel Generators | Instrument/ Control System
2026.B.GE.TEN.089 | اسناد مناقصه ارزیابی کیفی، فنی و بازرگانی(نیروگاه و توسعه پست) | GENERAL
2026.D.EL.SPC.090 | Technical Specification and Datasheet for MV Station | Electrical
بخش پنجم | بخش جنرال
Document Number | Description | Discipline
2026.A.PC.WBS.091 | تهیه ساختار شکست پروژه (WBS) | Project Control
2026.A.PC.SCH.092 | تهیه برنامه زمانی اجرای پروژه و پایش آن | Project Control