## 1
Procurement Status Report ( نیروگاه خورشیدی 20 مگاواتی ) | [30 empty] | Cut off Date: |  | 2026-05-19
Item | MR No. | MR Description | Discipline | PO No. | QTY | Unit | MR Release Date | Rev | MR Status | RFQ Sent (Tender) | Bid Close Date | TBE Issued Date | CBE Issued Date | Board committee Approval Date | Work Commencement Letter Date | PO Price | P.O. Information Date |  | Vendor Information |  |  | Delivery Condition |  | K.O.M Date | P.I.M Date | ITP/ MPS Approved (Starting) | Inspection Information (Only Final Inspection) |  |  |  | Delivery at Site Dates |  |  | Delivery Information |  |  |  | Current Status | Area of Concerns
[17 empty] | P.O Signed with Vendor | Advance Payment Date | Vendor Name | Manufacturer (Brand) | Origin | Duration | Term |  |  |  | 1st Part | 2nd Part | 3rd Part | 4th Part | Plan | ETA | Actual | 1st Part | 2nd Part | 3rd Part | 4th Part
1 | 410-DE-EL-MRE-0168 | Material Requisition for Indoor Power and Lighting Distribution Panel | Electrical | [27 empty] | 2026-07-29
2 | 410-DE-EL-MRE-0169 | Material Requisition for Auxiliary Transformer | Electrical | [27 empty] | 2026-08-12
3 | 410-DE-EL-MRE-0170 | Material Requisition for PCC | Electrical | [27 empty] | 2026-08-12
4 | 410-DE-EL-MRE-0171 | Material Requisition for MV Switchgear (CT, PT, Relay) | Electrical | [27 empty] | 2026-08-22
5 | 410-DE-EL-MRE-0172 | Material Requisition for AC Cable | Electrical | [27 empty] | 2026-08-06
6 | 410-DE-EL-MRE-0173 | Material Requisition for DC Cable | Electrical | JQR-1017 | 81926.88 | m | ongoing | 0 | ongoing | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-26 | 107600 | 2026-04-26 | 2026-04-26 | JINQISOLAR | JINQISOLAR | CHINA | 10 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-18 | [6 empty] | Delivery to Storage | Delivery to Site
7 | 410-DE-EL-MRE-0174 | Material Requisition for Earthing and Lightning | Electrical | [27 empty] | 2026-08-06
8 | 410-DE-EL-MRE-0175 | Material Requisition for DC Connection (MC4) | Electrical | JQR-1017 | 1051 | Pair | ongoing | 0 | ongoing | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-26 | 45366 | 2026-04-26 | 2026-04-26 | JINQISOLAR | TRINA SOLAR | CHINA | 10 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-06 | - | 2026-05-06 | 2026-05-06 | - | - | - | Delivery to Site | -
9 | 410-DE-EL-MRE-0176 | Material Requisition for Lighting System | Electrical | [27 empty] | 2026-08-08
10 | 410-DE-EL-MRE-0177 | Material Requisition for UPS and Battery | Electrical | [27 empty] | 2026-08-06
11 | 410-BE-EL-MRE-0186 | Material Requisition for Diesel Generator | Electrical | [27 empty] | 2026-08-12
12 | 410-DE-CV-MRE-0167 | Material Requisition for Fence | Civil | SK-CO-1405-11517 | 4260 | m | 2026-02-23 | 0 | Commented | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 53877 | 2026-05-17 | 2026-05-17 | صنایع مفتولی توران گستر | صنایع مفتولی توران گستر | IRAN | 15 | Day | 2026-05-17 | 2026-05-21 | [5 empty] | 2026-06-10 | 2026-06-05 | [5 empty] | Under Construction | Delivery to Site
13 | 410-DE-TL-MRE-0178 | Material Requisition forTelecommunication and Monitoring Cable | Telecom | [27 empty] | 2026-08-21
14 | 410-BE-TL-MRE-0179 | Material Requisition for Fiber Optics | Telecom | [27 empty] | 2026-08-16
15 | 410-DE-TL-MRE-0180 | Material Requisition for CCTV and NVR | Telecom | [27 empty] | 2026-08-04
16 | 410-BE-TL-MRE-0185 | Material Requisition for Weather Station | Telecom | [27 empty] | 2026-06-17
17 | 410-BE-ME-MRE-0183 | Material Requisition for Septic Tank | Mechanical | [27 empty] | 2026-04-03
18 | 410-BE-ME-MRE-0184 | Material Requisition for Water Tank | Mechanical | - | 2 | PCS (10000Lit) | ongoing | 0 | ongoing | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2000 | 2026-02-25 | 2026-02-25 | AZIN ALVAND | AZIN ALVAND | IRAN | 1 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-03 | - | 2026-02-27 | 2026-02-27 | - | - | - | Delivery to Site
19 | 410-DE-SF-MRE-0181 | Material Requisition for Fire Alarm System | Safety | [27 empty] | 2026-08-21
20 | 410-DE-SF-MRE-0182 | Material Requisition for Fire Fighting Equipment Arrangement | Safety | [27 empty] | 2026-08-11