## Rev-0
Procurement Status Report ( نیروگاه خورشیدی 20 مگاواتی ) | [27 empty] | REV: 4 |  |  |  | Cut off Date: |  |  | 1405/03/19 |  |  |  | 20% | 20% | 20% | 20% | 20% | Before P.O Progress | 10% | 5% | 15% | 45% | 10% | 10% | 5% | After P.O Progress
Item | MR No. | MR Description | PRODUCT MODEL | Discipline | PI No. | QTY | UNIT | QTY/PALLET | PALLET/40' HC | CONTAINER TYPE | TOTAL CONTAINERS | MR Release Date | Rev | MR Status | RFQ Sent (Tender) | Bid Close Date | TBE Issued Date | CBE Issued Date | PI UNIT PRICE | P.I TOTAL PRICE | P.I. Information Date |  | Vendor Information |  |  | Delivery Condition |  | K.O.M Date | P.I.M Date | ITP/ MPS Approved (Starting) | Inspection Information | Delivery Dates |  |  |  | Delivery Information | Current Status | Area of Concerns | Inquiry | TCL | TBE | Bid Winner | PO % |  | Engineering Progress | Material Suborder Progress | Material Receipt Progress | Manufacturing Progress | IRN Progress | MRS Progress | Final Book
[21 empty] | P.I Signed with Vendor | Advance Payment Completion Date | Vendor Name | Manufacturer (Brand) | Origin | Duration | Term |  |  |  |  | At Site (Esimate) | At Port of Destination (Estimate) | At Site Actual | At Port of Destination (Actual)
1 | -- | SOLAR MODULE | TRINA SOLAR NEG21C.20 | Electrical | JQI-1003 | 4752 | PCS | 33 | 18 | 40' HC | 8 | 1404/10/22 | -- | -- | 1404/10/26 | 1404/10/29 | 1404/11/01 | 1404/11/02 | 82.49 | 391992.48 | 1404/10/20 | 1404/11/16 | JINQI SOLAR | TRINA SOLAR | CHINA | IN STOCK | CIF | 1404/10/30 | 1404/11/15 | Approved | Passed | 1405/04/25 | 1405/04/10 |  |  | The goods are being stored at Jebel Ali warehouse and waiting for a new shipment to Bandar Abbas. | Jebel Ali (Dubai), UAE | U.S. Army Blockade | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 85%
2 | -- | SOLAR MODULE | TRINA SOLAR NEG21C.20 | Electrical | JQI-1003 | 5940 | PCS | 33 | 18 | 40' HC | 10 | 1404/10/22 | -- | -- | 1404/10/26 | 1404/10/29 | 1404/11/01 | 1404/11/02 | 82.49 | 489990.6 | 1404/10/20 | 1404/11/16 | JINQI SOLAR | TRINA SOLAR | CHINA | IN STOCK | CIF | 1404/10/30 | 1404/11/15 | Approved | Passed | 1405/04/25 | 1405/04/10 |  |  | The goods are being stored at Jebel Ali warehouse and waiting for a new shipment to Bandar Abbas. | Jebel Ali (Dubai), UAE | U.S. Army Blockade | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 85%
3 | -- | SOLAR MODULE | TRINA SOLAR NEG21C.20 | Electrical | JQI-1003 | 17226 | PCS | 33 | 18 | 40' HC | 29 | 1404/10/22 | -- | -- | 1404/10/26 | 1404/10/29 | 1404/11/01 | 1404/11/02 | 82.49 | 1420972.74 | 1404/10/20 | 1404/11/16 | JINQI SOLAR | TRINA SOLAR | CHINA | IN STOCK | CIF | 1404/10/30 | 1404/11/15 | Approved | Passed | 1405/04/01 | 1405/04/10 |  |  | 16X40' containers are moving from Zhuhai Port to Bandar Abbas. Bill of Lading is provided to MC. 13X40' containers are moving from Zhuhai Port to Bandar Abbas. Bill of Lading is provided to MC. MC: After arrival at port, 10-15 days for discharge. 2 days for transit. | On Freight to Bandar Abbas | U.S. Army Blockade | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 85%
4 | -- | INVERTER | SOLIS - 350 6 MPPT INVERTER | Electrical | JQI-1003 | 62 | PCS | 1 | 62 | 40' HC | 1 | 1404/05/11 | -- | -- | 1404/11/09 | 1404/11/13 | 1405/01/08 | 1405/01/09 | 10500 | 651000 | 1404/10/20 | 1404/11/16 | JINQI SOLAR | SOLIS | CHINA | 60 WORKING DAYS | CIF | 1404/10/30 | Pending | Pending |  | 1405/05/16 | 1405/05/01 |  |  | - | Production Finished -Waiting on Documents for Inspection |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  |  | 75%
5 | -- | MV STATION | SOLIS - 6500 KVA MV STATION | Electrical | JQI-1003 | 3 | PCS | 1 | 1 | 20' HD | 3 | 1404/29/11 | -- | -- | 1404/12/03 | 1404/12/06 | 1405/01/08 | 1405/01/09 | 193000 | 579000 | 1404/10/20 | 1404/11/16 | JINQI SOLAR | SOLIS | CHINA | 90 WORKING DAYS | CIF | 1404/10/30 | Pending | Pending |  | 1405/08/30 | 1405/08/15 |  |  | Delivery time based on ABB ABB Procurement time : 12 Weeks | Under Production |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 40% |  |  |  | 48%

## Report
Discipline | Total MR | Issued MR | TBE | P.O | RawMat. | Manufac. | I.R.N | Delivery to Site
Piping
Mechanical
Pipeline
Instrument
Electrical | 5 | N/A | 5 | 5 | 5 | 5 | 3
Safety
Telecom
Process
Architectural
MR Description | Report
SOLAR MODULE (QTY 4752) | تعداد 18 کانتینر در انبار جبل علی + 29 کانتینر در تاریخ 1405/03/06 به مقصد بندرعباس حمل گردید
SOLAR MODULE (QTY 5940)
SOLAR MODULE (QTY 17226)
INVERTER | ساخت تکمیل شده و در انتظار معرفی بازرس کارفرما جهت بازرسی و مجوز حمل می باشد.
MV STATION | تاریخ پیش بینی پایان ساخت و بازرسی طبق مکاتبات با چین ، اواسط تیر ماه 1405 و پیش بینی حمل اواسط شهریور ماه 1405 می باشد. در صورت انتخاب برند ABB ، پیش بینی ساخت و حمل اواسط آبان ماه 1405 می باشد. (MC: برند ABB انتخاب شد)