## 1
Procurement Status Report ( نیروگاه خورشیدی 20 مگاواتی ) | [30 empty] | Cut off Date: |  | 1405/03/19
Item | MR No. | MR Description | Discipline | PO No. | QTY | Unit | MR Release Date | Rev | MR Status | RFQ Sent (Tender) | Bid Close Date | TBE Issued Date | CBE Issued Date | Board committee Approval Date | Work Commencement Letter Date | PO Price | P.O. Information Date |  | Vendor Information |  |  | Delivery Condition |  | K.O.M Date | P.I.M Date | ITP/ MPS Approved (Starting) | Inspection Information (Only Final Inspection) |  |  |  | Delivery at Site Dates |  |  | Delivery Information |  |  |  | Current Status | Area of Concerns | 20% | 20% | 20% | 20% | 20% | Before P.O Progress | 10% | 5% | 15% | 45% | 10% | 10% | 5% | After P.O Progress
[17 empty] | P.O Signed with Vendor | Advance Payment Date | Vendor Name | Manufacturer (Brand) | Origin | Duration | Term |  |  |  | 1st Part | 2nd Part | 3rd Part | 4th Part | Plan | ETA | Actual | 1st Part | 2nd Part | 3rd Part | 4th Part |  |  | Inquiry | TCL | TBE | Bid Winner | PO % |  | Engineering Progress | Material Suborder Progress | Material Receipt Progress | Manufacturing Progress | IRN Progress | MRS Progress | Final Book
1 | 410-DE-EL-MRE-0168 | Material Requisition for Indoor Power and Lighting Distribution Panel | Electrical |  |  |  | 1405/03/16 | 0 | IFC | [21 empty] | 1405/05/07 | [13 empty] | 0% | [7 empty] | 0%
2 | 410-DE-EL-MRE-0169 | Material Requisition for Auxiliary Transformer | Electrical |  |  |  | 1405/03/17 | 0 | IFC | [21 empty] | 1405/05/21 | [13 empty] | 0% | [7 empty] | 0%
3 | 410-DE-EL-MRE-0170 | Material Requisition for PCC | Electrical |  | - | - |  |  | Deleted | [21 empty] | 1405/05/21 | [13 empty] | 0% | [7 empty] | 0%
4 | 410-DE-EL-MRE-0171 | Material Requisition for MV Switchgear (CT, PT, Relay) | Electrical |  |  |  | 1405/03/16 | 0 | IFC | [21 empty] | 1405/05/31 | [13 empty] | 0% | [7 empty] | 0%
5 | 410-DE-EL-MRE-0172 | Material Requisition for AC Cable | Electrical |  |  |  | 1405/03/13 | 0 | IFC | [21 empty] | 1405/05/15 | [13 empty] | 0% | [7 empty] | 0%
6 | 410-DE-EL-MRE-0173 | Material Requisition for DC Cable | Electrical | JQR-1017 | 81926.88 | m | 1405/03/13 | 0 | IFC | 1405/02/03 | 1405/02/04 | 1405/02/05 | 1405/02/05 | 1405/02/05 | 1405/02/06 | 107600 | 1405/02/06 | 1405/02/06 | JINQISOLAR | JINQISOLAR | CHINA | 10 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/04/27 | [6 empty] | Delivery to Storage |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 85%
7 | 410-DE-EL-MRE-0174 | Material Requisition for Earthing and Lightning | Electrical |  |  |  | 1405/03/16 | 0 | IFC | [21 empty] | 1405/05/15 | [13 empty] | 0% | [7 empty] | 0%
8 | 410-DE-EL-MRE-0175 | Material Requisition for DC Connection (MC4) | Electrical | JQR-1017 | 1051 | Pair | 1405/03/13 | 0 | IFC | 1405/02/03 | 1405/02/04 | 1405/02/05 | 1405/02/05 | 1405/02/05 | 1405/02/06 | 45366 | 1405/02/06 | 1405/02/06 | JINQISOLAR | TRINA SOLAR | CHINA | 10 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/05/15 | - | 1405/02/16 | 1405/02/16 | - | - | - | Delivery to Site |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 85%
9 | 410-DE-EL-MRE-0176 | Material Requisition for Lighting System | Electrical |  |  |  | 1405/03/16 | 0 | IFC | [21 empty] | 1405/05/17 | [13 empty] | 0% | [7 empty] | 0%
10 | 410-DE-EL-MRE-0177 | Material Requisition for UPS and Battery | Electrical |  |  |  | 1405/03/16 | 0 | IFC | [21 empty] | 1405/05/15 | [13 empty] | 0% | [7 empty] | 0%
11 | 410-BE-EL-MRE-0186 | Material Requisition for Diesel Generator | Electrical |  |  |  | 1405/03/16 | 0 | IFC | [21 empty] | 1405/05/21 | [13 empty] | 0% | [7 empty] | 0%
12 | 410-DE-CV-MRE-0167 | Material Requisition for Fence | Civil | SK-CO-1405-11517 | 4260 | m | 1405/03/17 | 0 | IFC | 1405/02/12 | 1405/02/13 | 1405/02/14 | 1405/02/15 | 1405/02/15 | 1405/02/15 | 53877 | 1405/02/27 | 1405/02/27 | صنایع مفتولی توران گستر | صنایع مفتولی توران گستر | IRAN | 15 | Day | N/A | N/A | N/A | 1405/03/11 | 1405/03/16 | 1405/03/17 | 1405/03/19 | 1405/03/20 | - | 1405/03/19 | 1405/03/11 | 1405/03/16 | 1405/03/17 | 1405/03/19 | Delivery to Site |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% |  | 93%
13 | 410-DE-TL-MRE-0178 | Material Requisition forTelecommunication and Monitoring Cable | Telecom | [27 empty] | 1405/05/30 | [13 empty] | 0% | [7 empty] | 0%
14 | 410-BE-TL-MRE-0179 | Material Requisition for Fiber Optics | Telecom | [27 empty] | 1405/05/25 | [13 empty] | 0% | [7 empty] | 0%
15 | 410-DE-TL-MRE-0180 | Material Requisition for CCTV and NVR | Telecom |  |  |  | 1405/03/13 | 0 | IFC | [21 empty] | 1405/05/13 | [13 empty] | 0% | [7 empty] | 0%
16 | 410-BE-TL-MRE-0185 | Material Requisition for Weather Station | Telecom |  |  |  | 1405/03/13 | 1 | IFA | [21 empty] | 1405/03/27 | [13 empty] | 0% | [7 empty] | 0%
17 | 410-BE-ME-MRE-0183 | Material Requisition for Septic Tank | Mechanical | - | 1 | PCS (2000Lit) | 1405/03/16 | 0 | IFC | 1405/03/9 | 1405/03/10 | 1405/03/11 | 1405/03/12 | 1405/03/12 | 1405/03/12 | 449 | 1405/03/12 | 1405/03/18 | تانکرسازی زیارتی | زیارتی | IRAN | 1 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/01/14 | - | 1405/03/20 | 1405/03/20 | - | - | - | Delivery to Site |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 95%
18 | 410-BE-ME-MRE-0184 | Material Requisition for Water Tank | Mechanical | - | 2 | PCS (10000Lit) | 1405/03/18 | 0 | IFC | 1404/12/03 | 1404/12/04 | 1404/12/05 | 1404/12/06 | 1404/12/06 | 1404/12/06 | 2000 | 1404/12/06 | 1404/12/06 | آذین الوند آسیا | AZIN ALVAND | IRAN | 1 | Day | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1405/01/14 | - | 1404/12/08 | 1404/12/08 | - | - | - | Delivery to Site |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 95%
19 | 410-DE-SF-MRE-0181 | Material Requisition for Fire Alarm System | Safety |  |  |  | 1405/03/19 | 0 | IFC | [21 empty] | 1405/05/30 | [13 empty] | 0% | [7 empty] | 0%
20 | 410-DE-SF-MRE-0182 | Material Requisition for Fire Fighting Equipment Arrangement | Safety |  |  |  | 1405/03/19 | 0 | IFC | [21 empty] | 1405/05/20 | [13 empty] | 0% | [7 empty] | 0%

## Report
Discipline | Total MR | Issued MR | TBE | P.O | RawMat. | Manufac. | I.R.N | Delivery to Site
Electrical | 10 | 10 | 2 | 2 | 2 | 2 | 2 | 1
Civil | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Telecom | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Mechanical | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Safety | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
MR Description | Report
Material Requisition for Indoor Power and Lighting Distribution Panel
Material Requisition for Auxiliary Transformer
Material Requisition for PCC | این مدرک حذف گردید
Material Requisition for MV Switchgear (CT, PT, Relay) | درحال استعلام قیمت و انتخاب تامین کننده
Material Requisition for AC Cable | درحال استعلام قیمت و انتخاب تامین کننده
Material Requisition for DC Cable | تجهیز فوق خریداری و به انبار تهران ارسال شده است
Material Requisition for Earthing and Lightning
Material Requisition for DC Connection (MC4) | تجهیز فوق خریداری و به سایت ارسال شده است
Material Requisition for Lighting System
Material Requisition for UPS and Battery | درحال استعلام قیمت و انتخاب تامین کننده
Material Requisition for Diesel Generator | درحال استعلام قیمت و انتخاب تامین کننده
Material Requisition for Fence | ساخت و خرید فنس ، پایه ها و متعلقات مربوطه به پایان رسید و تمامی قطعات از تاریخ 1405/03/11 تا تاریخ 1405/03/19 به سایت ارسال گردید.
Material Requisition forTelecommunication and Monitoring Cable | درحال استعلام قیمت و انتخاب تامین کننده
Material Requisition for Fiber Optics | درحال استعلام قیمت و انتخاب تامین کننده
Material Requisition for CCTV and NVR | درحال استعلام قیمت و انتخاب تامین کننده
Material Requisition for Weather Station | درحال استعلام قیمت و انتخاب تامین کننده
Material Requisition for Septic Tank | تجهیز فوق خریداری و به سایت ارسال شده است
Material Requisition for Water Tank | تجهیز فوق خریداری و به سایت ارسال شده است
Material Requisition for Fire Alarm System
Material Requisition for Fire Fighting Equipment Arrangement